## Slide 1
Passivation Timeline for Equipment train
 | Step | Passivation Completion Date | Solvent Run Completion Date | Equipment Ready Date
L1 140019 | 1 | 09/22/2026 | 09/24/2026 | 09/25/2026
 | 2 | 09/30/2026 | 10/05/2026 | 10/08/2026
L2 140020 | 1 | 09/20/2026 | 09/22/2026 | 09/23/2026
 | 2 | 09/30/2026 | 10/05/2026 | 10/08/2026
L3 140021 | 1 | 09/19/2026 | 09/21/2026 | 09/22/2026
 | 2 | 09/30/2026 | 10/05/2026 | 10/08/2026
 | 3 | 09/30/2026 | 10/05/2026 | 10/10/2026
GG917 139788 | 1 | 09/21/2026 | 09/24/2026 | 09/26/2026
 | 2 | 09/30/2026 | It is expected to be completed in mid-October. | 
 | 3 | All equipment has been passivated. |  | 
Passivation of the main body of the Synthesizer, Cleavage Reactor, Stainless steel Reactor and AFD has been performed by the equipment manufacturer.
For others, like tanks, pipeline, passivation will be done, and solvent run will be conducted. Timeline meet the use.

## Slide 2
Passivation discussion for Solvent Tank Farm
Solvent | Tank farm supply | Tanks | Lilly trains / steps supplied | Need by | Passivation approach
Isopropyl acetate, toluene, n-heptane, ethyl acetate, 2-MeTHF | Lilly dedicated | 5 x 30 m³ | 140019 / 140020 / 140021 / 139788 step 1 - step 3 | 09/25 - 10/28 | Tanks and transfer lines emptied and passivated directly - no impact on other buildings
Acetonitrile (prep grade) | Shared Bldg 11 + Bldg 12 | 3 x 30 m³ | 140021 step 1, 139788 step 1 + step 3 | 10/15 | Bldg 12 is fed by a dedicated line: 1 x 30 m³ tank emptied and passivated
Piperidine | Shared Bldg 11 + Bldg 12 | 1 x 10 m³ | 140019 / 140020 / 140021 / 139788 step 1 | 09/25 | Single tank still needed by Bldg 11 - not passivated; Lilly runs on drummed solvent
MTBE | Shared Bldg 11 + Bldg 12 | 1 x 30 m³ | 140019 / 140020 / 140021 / 139788 step 1 | 09/25 | Not passivated; drummed solvent until the phase 2 tank farm is connected
DMF | Shared Bldg 11 + Bldg 12 | 3 x 30 m³ | 140019 / 140020 / 140021 / 139788 step 1 | 09/25 | Line modification required first - no tank can be released today
DMF line modification - TF01 and TF02 both feed Bldg 11 and Bldg 12, so no tank can be released today
DMF tank | Today | After modification
TF01 | Feeds Bldg 11 and Bldg 12 | Bldg 12 only - emptied and passivated
TF04 | Backup only, no dedicated line | New line built to Bldg 11: piping 10 d + software change and verification 10 d
TF02 | Feeds Bldg 11 and Bldg 12 | Unchanged
Bldg 11 supply has to be cut over during the tie-in: 20 d delay for 139166 / 150168 / 148235.
After the change the Lilly synthesizers are fed from one DMF tank with no backup - high consumption requires continuous replenishment.
Piperidine and MTBE stay on 200 L drums for Bldg 12 until the phase 2 tank farm starts up.

## Slide 3
Passivation Sequence, Duration and Project Impact
Passivation sequence - 75 days per batch of tanks
# | Activity | Days
1 | Emptying of storage tank contents | 2
2 | Tank pretreatment: water wash, flammable gas check | 4
3 | Liquid alkali charge | 2
4 | Rinse until pH neutral | 10
5 | Storage tank passivation | 7
6 | Inlet / outlet pipeline passivation | 3
7 | Draining of passivation medium | 2
8 | Pipeline inspection (NDT) | 3
9 | Rinse with tap water until pH neutral | 10
10 | Cleanliness confirmation of the tank | 2
11 | Solvent water content determination | 30
 | Total per batch | 75
Impact on projects
Building | Projects affected | Impact
Bldg 11 | 139166 (Roche), 150168, 148235 (Pfizer) - step 1 | Start delayed 20 d DMF line tie-in
Bldg 12 | 140019 / 140020 / 140021 / 139788 PPQ step 1; 139788 full scale demo step 3; 149744 (AbbVie), 136877 (Lilly) step 1C, 142316 (Vertex) step 1 | Start delayed 75 d tank farm out of service
7 tanks passivated in 2 batches - 75 days per batch, last batch released around day 85
Batch 1 - 2 tanks
Day 1 - 76
Batch 2 - 5 tanks
Day 12 - 85
Day 1
Day 85
Nitric acid available on site is not sufficient for all seven tanks; a new purchase is required, so the tanks are passivated in two batches.
Why the cycle is long
Tanks have no spray balls: operators must enter the tank and spray the passivation solution until the test passes; pipelines are passivated by soaking.
The caustic wash removes residual oil from the piping, and each rinse back to neutral pH takes 10 days.
Solvent water content determination is the critical path at 30 days - low points in the welded lines hold water and the ≤ 0.1 % w/w spec is hard to reach, a high risk for the CTC resin in step 1.
Operational impact during passivation
Bldg 12 has no tank farm supply - all solvents move to 200 L drums; drum handling safety is the key control.
DMF and deprotection solutions are made up manually: lower throughput.
Automatic solvent top-up is unavailable - levels are checked and topped up manually.