## Overview
Peptide Building 2 (Project 139788)
Customer findings, equipment rectification and retrofit options – status 17 Sep 2026
English version of the rectification working file dated 09-17-2026. Layout, colour coding and Gantt bars follow the original; only the wording was translated, the row heights were re-fitted for English text, and rows and columns that were hidden by filters in the original are shown.
What is in this workbook
1. Lead Times | Supplier lead times per item for the two piping scenarios: existing system all-316L, and the new batch system partly Hastelloy / partly 316L.
2. Replace Existing (Opt.2) | Purchasing list for replacing the existing equipment and piping (no new CIP etc.), with the installation, qualification and cleaning durations and the day-by-day schedule from October to February.
3. New Batch System (Opt.1) | Purchasing list for a completely new batch solution preparation system, installed to the P&ID.
4. Option 1 - Retrofit Only | Modify the existing installation only, to meet the requirements from the latest customer meeting; target completion around 30 Nov 2026. Includes the modification requirement, sub-options and current status per item.
5. Option 2 - New Batch System | New batch solution preparation system reusing the 3000 L Hastelloy reactor released by Peptide Building 3, with the associated schedule.
6. Option 3 - All New | All vessels, pumps and piping replaced by new equipment (316L + Hastelloy), with the associated schedule.
7. Customer Findings | Core assessment table: per equipment tag and per component (body, piping, instruments, pumps, valves) the customer finding, the internal rectification plan, the current status, and the procurement, installation, qualification and cleaning durations.
8. Open Work & Site Punch List | Retrofit work packages already executed and still open, per round of additional requirements, with duration, status, blocking factors, supplier and responsible person.
9. Auxiliary Equipment | Purchasing list for filters, cartridges, local laminar flow units and WFI hoses.
How to read the assessment
• Findings are grouped per equipment tag and then per component: equipment body, piping, instruments, pumps and valves.
• “2D” is the drainability criterion: a dead leg may not be longer than two pipe diameters. Most findings are either a 2D breach, a dead leg, a non-BPE line, or a ball valve that has to become a diaphragm valve.
• “Assessment shows no issue; raised by the customer on site” means the point came from the customer walk-down and our own assessment did not confirm a gap.
• Yellow fills in the schedules mark delivery dates that Purchasing still has to confirm; the schedules assume the retrofit starts after production ends in mid / late October.
Open points that need a customer decision
• The TC connections on several vessels on site were made in-house; the customer has to confirm whether they are acceptable.
• Whether 316L may be used for the concentrated-salt lines instead of Hastelloy, which drives both cost and lead time.
• The high-pressure preparative system: BPE piping is rated 0.7 MPa while the system operates at 7 MPa (design 10 MPa), so quick-connect fittings cannot replace the threaded and compression connections.
• Ultrafiltration: agitator design, 3 m² Sartorius cassettes instead of 0.6 m², deleting valve V305, and the methanol dip tube length.
• The single-shaft rotary sifter has not yet been assessed by the customer and currently does not meet the BPE and hygienic design requirements.
Abbreviations
BPE | ASME BPE, Bioprocessing Equipment standard
2D | Dead leg no longer than two pipe diameters
TC / NA | Tri-clamp quick-connect / flare (NA) type sanitary nozzle
IQ / OQ / PQ / EOQ | Installation, operational, performance and enhanced operational qualification
C22 / C276 / HC | Hastelloy alloy grades / Hastelloy in general
CNC / Grade C / D | Controlled not classified area / cleanroom grades
TFF | Tangential flow filtration (ultrafiltration) skid
TCU | Temperature control unit
DCS | Distributed control system
WFI / PW | Water for injection / purified water
T-valve | Tank bottom or zero-dead-leg valve used to keep the 2D requirement
Translation notes: supplier and personnel names are transliterated from the original (Yingde, Chengxin, Tongbo, Longma, Xinlai, Watson, Furuide, Yuanxi, Nuomeng, Weiterui, Shouke, Ternp, Tofflon, Yaguang, Sartorius, Ailipu). Vessel names follow the tag list of the original file; where the Chinese text contained typos or shorthand, the intended meaning was used.

## 1. Lead Times (hidden)
Retrofit of the existing preparation system – all piping in 316L
No. | Item | Material | Quantity | Lead time (days) | Remarks
1 | Solution preparation vessel (BPE) | C22 | See attachment | 100 | Lead time from Zhejiang Chengxin | Replacement scope to be confirmed by Production?
2 | Centrifugal pump (quick-connect, BPE) | 316L | See attachment | 60 | To be confirmed, estimated lead time | Replacement scope to be confirmed by Production?
3 | Mass flow meter (quick-connect, BPE) | 316L | See attachment | 30 | Shouke 4 weeks, Watson 5–6 weeks
4 | Pneumatic diaphragm control valve (quick-connect, BPE) | 316L | See attachment | 42 | Xinlai: 6 weeks for explosion-proof pneumatic 316L; 10 weeks for explosion-proof pneumatic in special alloy
5 | Pneumatic diaphragm on/off valve (quick-connect, BPE) | 316L | See attachment | 42 | Xinlai: 6 weeks for explosion-proof pneumatic 316L; 10 weeks for explosion-proof pneumatic in special alloy
6 | Pneumatic control valve (quick-connect, BPE) | 316L | See attachment | 42 | Weiterui 6–8 weeks
7 | Pneumatic on/off valve (quick-connect, BPE) | 316L | See attachment | 49 | Zhejiang Sanfang 7 weeks
8 | Radar level transmitter | 316L | See attachment | 20 | Furuide 2–3 weeks
9 | Tuning-fork level switch | 316L | See attachment | 20 | Furuide 2–3 weeks
10 | Temperature instrument | 316L | See attachment | 20 | Furuide 2–3 weeks
11 | pH instrument | 316L | See attachment | 42 | Ternp 6–8 weeks
12 | Pressure instrument | 316L | See attachment | 60 | Furuide 2–3 weeks
13 | Manual diaphragm valve | 316L | See attachment | 45 | Xinlai: 6 weeks for manual 316L; 10 weeks for manual in special alloy
14 | BPE piping and fittings | 316L | See attachment | 25 | Yuanxi 3 weeks
Retrofit of the new batch preparation / solution system – piping partly Hastelloy, partly 316L
No. | Item | Material | Quantity | Lead time (days) | Remarks
1 | Solution preparation vessel (BPE) | C22 | See attachment | 100 | Lead time from Zhejiang Chengxin
2 | Centrifugal pump (quick-connect, BPE) | C22 | See attachment | 75 | To be confirmed, estimated lead time
3 | Mass flow meter (quick-connect, BPE) | C22 | See attachment | 35 | Watson 5–6 weeks
4 | Pneumatic diaphragm control valve (quick-connect, BPE) | C22 | See attachment | 70 | Xinlai: 6 weeks for explosion-proof pneumatic 316L; 10 weeks for explosion-proof pneumatic in special alloy
5 | Pneumatic diaphragm on/off valve (quick-connect, BPE) | C22 | See attachment | 70 | Xinlai: 6 weeks for explosion-proof pneumatic 316L; 10 weeks for explosion-proof pneumatic in special alloy
6 | Manual diaphragm valve | C22 | See attachment | 70 | Xinlai: 6 weeks for manual 316L; 10 weeks for manual in special alloy
7 | BPE fittings | C22 | See attachment | 60 | Nuomeng 8 weeks
8 | Centrifugal pump (quick-connect, BPE) | 316L | See attachment | 60 | To be confirmed, estimated lead time
9 | Mass flow meter (quick-connect, BPE) | 316L | See attachment | 35 | Watson 5–6 weeks
10 | Pneumatic diaphragm control valve (quick-connect, BPE) | 316L | See attachment | 42 | Xinlai: 6 weeks for explosion-proof pneumatic 316L; 10 weeks for explosion-proof pneumatic in special alloy
11 | Pneumatic diaphragm on/off valve (quick-connect, BPE) | 316L | See attachment | 42 | Xinlai: 6 weeks for explosion-proof pneumatic 316L; 10 weeks for explosion-proof pneumatic in special alloy
12 | Pneumatic control valve (quick-connect, BPE) | 316L | See attachment | 42 | Weiterui 6–8 weeks
13 | Pneumatic on/off valve (quick-connect, BPE) | 316L | See attachment | 49 | Zhejiang Sanfang 7 weeks
14 | Radar level transmitter | 316L | See attachment | 20 | Furuide 2–3 weeks
15 | Tuning-fork level switch | 316L | See attachment | 20 | Furuide 2–3 weeks
16 | Temperature instrument | 316L | See attachment | 20 | Furuide 2–3 weeks
17 | pH instrument | 316L | See attachment | 42 | Ternp 6–8 weeks
18 | Pressure instrument | 316L | See attachment | 60 | Furuide 2–3 weeks
19 | Manual diaphragm valve | 316L | See attachment | 45 | Xinlai: 6 weeks for manual 316L; 10 weeks for manual in special alloy
20 | BPE piping and fittings | 316L | See attachment | 25 | Yuanxi 3 weeks

## 2. Replace Existing (Opt.2) (hidden)
Peptide Building 2, replacement of existing equipment – purchasing list – covers replacement of existing equipment and piping only, excluding anything else (such as a new CIP system)
Preparation system – continuous solution preparation – CNC area – equipment list
No. | Equipment tag | Equipment name | Technical parameters | Equipment material | Process medium | Unit | Quantity | Equipment source | Procurement lead time (days) | Installation duration | Qualification duration | Total time including 3 days of cleaning | Technical requirements |  | Provisionally assumes that the retrofit starts after the equipment arrives around 20 October; to be adjusted according to the actual end of the production campaign. The delivery dates highlighted in yellow below still have to be confirmed by Purchasing.
1 | 1213-R05 | Hastelloy reactor | 3000 L Hastelloy reactor | C276 | Concentrated salt solution | unit | 1 | N/A | 100 | 30 | 19 d (loop check 2 d, software commissioning 5 d + pump commissioning 3 d + qualification 9 d) IQ runs in parallel with installation; IQ is closed after the loop check and is completed during software commissioning | 52d | 1. The equipment shall comply with ASME BPE, including but not limited to: (1) NA-type connections meeting the 2D drainability requirement; connection sizes and quantities as per the approved drawings; (2) Spray port with spray ball, giving full coverage and passing the riboflavin coverage test; (3) Diaphragm valve welded to the outlet, meeting the 2D requirement; (4) External surface roughness < 0.8 µm, internal surface roughness < 0.4 µm; (5) Raw materials, components, manufacturing and acceptance strictly in line with ASME BPE, with the supporting documentation provided; 2. Motor and gearbox: (1) Well-known domestic brand; fully stainless-steel clad to sanitary standard; (2) Explosion protection Ex d IIB T4 Gb, ingress protection not lower than IP55; motor efficiency class 2 or better; 3. Double-end sanitary dry-running mechanical seal from a well-known domestic brand; 4. Agitator material identical to the vessel; agitator design as per the approved drawings; |  | Retrofit of the continuous solution preparation system – rework of the 3000 L Hastelloy reactor nozzles, replacement of 8 vessels (316L), BPE piping
2 | 1211-HPPC03-AT01 | Solution preparation agitated vessel (non-jacketed) | Working volume 500 L, operating temperature −20 to 100 °C, operating pressure −0.098 to 0.099 MPa | C22 or C276 | Concentrated salt solution | unit | 1 | N/A | —— | [5 empty] | No. | Activity | Equipment / material | Lead time / duration | Expected delivery date | October | [11 empty] | November | [29 empty] | December
3 | 1211-HPPC03-AT02 | Solution preparation agitated vessel (non-jacketed) | Working volume 500 L, operating temperature −20 to 100 °C, operating pressure −0.098 to 0.099 MPa | C22 or C276 | Concentrated salt solution | unit | 1 | N/A | —— | [10 empty] | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | Remarks
4 | 1211-HPPC03-AT01 | Solution preparation agitated vessel (non-jacketed) | Working volume 500 L, operating temperature −20 to 100 °C, operating pressure −0.098 to 0.099 MPa | SS316L | Concentrated salt solution | unit | 1 | Reuse Yingde 600 L storage tank (11) – 6-week modification (add agitator, explosion-proof motor, bottom outlet valve) | 42 | [5 empty] | 1 | Equipment procurement | Delivery of the 3000 L Hastelloy reactor parts | 40 | 20 Oct | [49 empty] | Ordered
5 | 1211-HPPC03-AT02 | Solution preparation agitated vessel (non-jacketed) | Working volume 500 L, operating temperature −20 to 100 °C, operating pressure −0.098 to 0.099 MPa | SS316L | Concentrated salt solution | unit | 1 | Reuse Yingde 600 L storage tank (11) – 7-week modification (add agitator, explosion-proof motor, bottom outlet valve) | 42 | [5 empty] | 2 |  | Delivery of the YD storage tanks (316L) | 40 | 20 Oct | [49 empty] | Ordered
6 | 1211-HPPC03-T01 | Purified water storage tank (non-jacketed) | Working volume 1000 L, operating temperature −20 to 100 °C, operating pressure −0.098 to 0.099 MPa | SS316L | Purified water | unit | 1 | Reuse Yingde 1000 L storage tank (8) – 6-week modification, add bottom outlet valve | 42 |  |  |  | The equipment shall comply with ASME BPE, including but not limited to: (1) NA-type connections meeting the 2D drainability requirement; connection sizes and quantities as per the approved drawings; (2) Spray port with spray ball, giving full coverage and passing the riboflavin coverage test; (3) Diaphragm valve welded to the outlet, meeting the 2D requirement; (4) External surface roughness < 0.8 µm, internal surface roughness < 0.4 µm; (5) Raw materials, components, manufacturing and acceptance strictly in line with ASME BPE, with the supporting documentation provided; |  | 3 |  | Delivery of the centrifugal pumps (316L) | 42 | 25 Oct | [49 empty] | Not ordered yet, estimated delivery date
7 | 1211-HPPC03-T02 | Acetonitrile storage tank (non-jacketed) | Working volume 1000 L, operating temperature −20 to 100 °C, operating pressure −0.098 to 0.099 MPa | SS316L | Fresh acetonitrile, spare | unit | 2 | Reuse Yingde 1500 L storage tanks (12, 13) – 6-week modification, add bottom outlet valve | 42 | [5 empty] | 4 |  | Delivery of the four-head diaphragm pumps (316L) | 25 | 10 Oct | [49 empty] | Ordered
8 | 1211-HPPC03-T03 | Mobile phase A storage tank (non-jacketed) | Working volume 1000 L, operating temperature −20 to 100 °C, operating pressure −0.098 to 0.099 MPa | SS316L | Mobile phase A | unit | 1 | Reuse Yingde 1000 L storage tank (9) – 6-week modification (change to explosion-proof motor, bottom outlet valve) | 42 | [5 empty] | 5 |  | Procurement of control valves / instruments (316L) | 42 | 25 Oct | [49 empty] | Partly ordered, partly not ordered; estimated delivery date
9 | 1211-HPPC03-T04 | Mobile phase B storage tank (non-jacketed) | Working volume 1000 L, operating temperature −20 to 100 °C, operating pressure −0.098 to 0.099 MPa | SS316L | Mobile phase B | unit | 1 | Reuse Yingde 1000 L storage tank (10) – 6-week modification (change to explosion-proof motor, bottom outlet valve) | 42 | [5 empty] | 6 |  | Procurement of BPE fittings (316L) | 30 | 15 Oct | [49 empty] | Ordered
10 | 1211-HPPC03-T05 | Methanol storage tank (non-jacketed) | Working volume 1000 L, operating temperature −20 to 100 °C, operating pressure −0.098 to 0.099 MPa | SS316L | Methanol | unit | 1 | 1000 L storage tank – 6-week modification, add bottom outlet valve. This tank is planned to be cancelled | 42 | [5 empty] | 7 |  | BPE manual valves (316L) | 30 | 15 Oct | [49 empty] | Ordered
11 | 1211-HPPC03-T03-P01 | Sanitary centrifugal pump | Rated flow 2.5 m³/h, head 25 m, clamp connection | SS316L | Mobile phase A | unit | 2 | Newly purchased | 45 |  |  |  | The equipment shall comply with ASME BPE, including but not limited to: (1) NA-type connections meeting the 2D drainability requirement, with a fully drainable equipment body; (2) External surface roughness < 0.8 µm, internal surface roughness < 0.4 µm; (3) Raw materials, components, manufacturing and acceptance strictly in line with ASME BPE, with the supporting documentation provided; |  | 8 |  | BPE fittings (Hastelloy) | 60 | 10 Nov | [49 empty] | Ordered
12 | 1211-HPPC03-T03-P02 | Sanitary centrifugal pump | Rated flow 3.2 m³/h, head 25 m, clamp connection | SS316L | Mobile phase B | unit | 2 | Newly purchased | 45 | [5 empty] | 9 | On-site modification | On-site nozzle modification of the 3000 L Hastelloy reactor | 10 | [50 empty] | Cut the vessel nozzles in advance
13 | 1211-HPPC03-T04-P01 | Sanitary centrifugal pump | Rated flow 2.5 m³/h, head 25 m, clamp connection | SS316L | Mobile phase B / fresh acetonitrile | unit | 2 | Newly purchased | 45 | [5 empty] | 10 |  | Piping of the 3000 L Hastelloy reactor | 4 | [50 empty] | Waiting for delivery of the Hastelloy parts
14 | 1211-HPPC03-WT01-P01 | Sanitary centrifugal pump | Rated flow 3.2 m³/h, head 20 m, clamp connection | SS316L | Preparation waste liquid | unit | 2 | Newly purchased | 45 | [5 empty] | 11 |  | Removal and installation of 8 vessels | 3 | [50 empty] | Waiting for delivery of the storage tanks
15 | 1211-HPPC03-WT02-P01 | Sanitary centrifugal pump | Rated flow 3.2 m³/h, head 20 m, clamp connection | SS316L | Preparation waste liquid | unit | 2 | Newly purchased | 45 | [5 empty] | 12 |  | Replacement of pumps and BPE piping | 20 | [50 empty] | ——
16 | 1211-HPPC03-AT01-P01 | Sanitary four-head diaphragm pump | Rated flow 3.2 m³/h, head 30 m, clamp connection | C22 or C276 | Concentrated salt solution | unit | 2 | Newly purchased | 45 | [5 empty] | 13 |  | Electrical and instrumentation installation | 10 | [50 empty] | ——
17 | 1211-HPPC03-AT02-P01 | Sanitary four-head diaphragm pump | Rated flow 3.2 m³/h, head 30 m, clamp connection | C22 or C276 | Concentrated salt solution | unit | 2 | Newly purchased | 45 | [5 empty] | 14 |  | Floor work and sealant application | 3 | [50 empty] | ——
18 | 1211-HPPC03-T01-P01 | Sanitary four-head diaphragm pump | Rated flow 5 m³/h, head 30 m, clamp connection | SS316L | Purified water | unit | 2 | Newly purchased | 45 | [5 empty] | 15 | Qualification + cleaning | IQ | [51 empty] | IQ runs in parallel with installation; IQ is closed after the loop check and is completed during software commissioning
19 | 1211-HPPC03-T01-P02 | Sanitary four-head diaphragm pump | Rated flow 3.2 m³/h, head 30 m, clamp connection | SS316L | Purified water | unit | 2 | Newly purchased | 45 | [5 empty] | 16 |  | Loop check | [51 empty] | ——
20 | 1211-HPPC03-T02-P01 | Sanitary four-head diaphragm pump | Rated flow 3.2 m³/h, head 30 m, clamp connection | SS316L | Fresh acetonitrile | unit | 2 | Newly purchased | 45 | [5 empty] | 17 |  | Software commissioning | [51 empty] | ——
21 | 1211-HPPC03-T02-P02 | Sanitary four-head diaphragm pump | Rated flow 5 m³/h, head 30 m, clamp connection | SS316L | Fresh acetonitrile | unit | 2 | Newly purchased | 45 | [5 empty] | 18 |  | Pump commissioning | [51 empty] | ——
22 | Components | Mass flow meter (quick-connect, BPE) | See attachment | 316L | —— | unit | See attachment | Newly purchased | 30 |  |  |  | BPE requirements |  | 19 |  | OQ / PQ | [51 empty] | ——
23 |  | Pneumatic diaphragm control valve (quick-connect, BPE) | See attachment | 316L | —— | unit | See attachment | Newly purchased | 42
24 |  | Pneumatic diaphragm on/off valve (quick-connect, BPE) | See attachment | 316L | —— | unit | See attachment | Newly purchased | 42 | [5 empty] | Retrofit of the fraction receiving vessels – conversion of 6 storage tanks to 2D connections, BPE piping
25 |  | Pneumatic control valve (quick-connect, BPE) | See attachment | 316L | —— | unit | See attachment | Newly purchased | 42 | [5 empty] | No. | Activity | Equipment / material | Lead time / duration | Expected delivery date | October | [11 empty] | November | [29 empty] | December
26 |  | Pneumatic on/off valve (quick-connect, BPE) | See attachment | 316L | —— | unit | See attachment | Newly purchased | 42 | [10 empty] | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | Remarks
27 |  | Radar level transmitter | See attachment | 316L | —— | unit | See attachment | Newly purchased | 20 | [5 empty] | 1 | Equipment procurement | Delivery of the storage tank parts | 40 | 20 Oct | [49 empty] | Ordered
28 |  | Tuning-fork level switch | See attachment | 316L | —— | unit | See attachment | Newly purchased | 20 | [5 empty] | 2 |  | Delivery of the centrifugal pumps (316L) | 42 | 25 Oct | [49 empty] | Not ordered yet, estimated delivery date
29 |  | Temperature instrument | See attachment | 316L | —— | unit | See attachment | Newly purchased | 20 | [5 empty] | 3 |  | Procurement of control valves / instruments (316L) | 42 | 25 Oct | [49 empty] | Partly ordered, partly not ordered; estimated delivery date
30 |  | pH instrument | See attachment | 316L | —— | unit | See attachment | Newly purchased | 42 | [5 empty] | 4 |  | Procurement of BPE fittings (316L) | 30 | 15 Oct | [49 empty] | Ordered
31 |  | Pressure instrument | See attachment | 316L | —— | unit | See attachment | Newly purchased | 21 | [5 empty] | 5 |  | BPE manual valves (316L) | 30 | 15 Oct | [49 empty] | Ordered
32 |  | Manual diaphragm valve | See attachment | 316L | —— | unit | See attachment | Newly purchased | 45 | [5 empty] | 6 | On-site modification | Nozzle modification of 6 vessels | 20 | [50 empty] | There are many nozzles, and reworking the measurement and bottom nozzles means removing insulation and jackets, which is very difficult
33 |  | BPE piping and fittings | See attachment | 316L | —— | unit | See attachment | Newly purchased | 35 | [5 empty] | 7 |  | Replacement of pumps and BPE piping | 15 | [50 empty] | ——
Preparation system – Grade D area – equipment list | [14 empty] | 8 |  | Electrical and instrumentation installation | 10 | [50 empty] | ——
No. | Equipment tag | Equipment name | Technical parameters | Equipment material | Process medium | Unit | Quantity | Option | Procurement lead time | Installation duration | Qualification duration | Total time | Technical requirements |  | 9 |  | Floor work and sealant treatment | 5 | [50 empty] | Large working area; the floor is assumed to be redone
1 | 1211-HPPC03-AT03 | Fraction receiving agitated vessel (jacketed) | 1. Working volume 8000 L; 2. Vessel design temperature −20 to 150 °C, jacket design temperature −25 to 180 °C; 3. Vessel design pressure −0.1 to 0.1 MPa; jacket operating pressure 0.6 MPa; | Product contact: 316L stainless steel; Jacket: 304 stainless steel; Insulation: perlite powder; Insulation cladding: 304 stainless steel; | Various organic solvents | unit | 1 | Equipment stays in place; convert to quick-connect flare (NA) nozzles, purchase the parts | 25 | 30 | 4 d, 24 h IQ runs in parallel with installation; IQ 1 d, OQ 3 d | 37d | 1. The equipment shall comply with ASME BPE, including but not limited to: (1) NA-type connections meeting the 2D drainability requirement; connection sizes and quantities as per the approved drawings; (2) Spray port with spray ball, giving full coverage and passing the riboflavin coverage test; (3) Diaphragm valve welded to the outlet, meeting the 2D requirement; (4) External surface roughness < 0.8 µm, internal surface roughness < 0.4 µm; (5) Raw materials, components, manufacturing and acceptance strictly in line with ASME BPE, with the supporting documentation provided; 2. Motor and gearbox: (1) Well-known domestic brand; fully stainless-steel clad to sanitary standard; (2) Explosion protection Ex d IIB T4 Gb, ingress protection not lower than IP55; motor efficiency class 2 or better; 3. Double-end sanitary dry-running mechanical seal from a well-known domestic brand; 4. Agitator material identical to the vessel; agitator design as per the approved drawings; 5. Insulation thickness to suit the temperature requirement; cladding in 3 mm stainless steel with an external surface roughness < 0.8 µm, |  | 10 | Qualification + cleaning | IQ | [51 empty] | IQ runs in parallel with installation
2 | 1211-HPPC03-AT04/AT05 | Fraction receiving agitated vessel (jacketed) | 1. Working volume 3000 L; 2. Vessel design temperature −20 to 150 °C, jacket design temperature −25 to 180 °C; 3. Vessel design pressure −0.1 to 0.1 MPa; jacket operating pressure 0.6 MPa; | Product contact: 316L stainless steel; Jacket: 304 stainless steel; Insulation: perlite powder; Insulation cladding: 304 stainless steel; | Various organic solvents | unit | 2 | Equipment stays in place; convert to quick-connect flare (NA) nozzles, purchase the parts | 25 | [5 empty] | 11 |  | OQ
3 | 1211-HPPC03-AT06 | Sample agitated vessel (jacketed) | 1. Working volume 1000 L; 2. Vessel design temperature −20 to 150 °C, jacket design temperature −25 to 180 °C; 3. Vessel design pressure −0.1 to 0.1 MPa; jacket operating pressure 0.6 MPa; | Product contact: 316L stainless steel; Jacket: 304 stainless steel; Insulation: perlite powder; Insulation cladding: 304 stainless steel; | Various organic solvents | unit | 1 | Equipment stays in place; convert to quick-connect flare (NA) nozzles, purchase the parts | 25
4 | 1211-HPPC03-T06 | Top-fraction sample agitated vessel (jacketed) | 1. Working volume 1000 L; 2. Vessel design temperature −20 to 150 °C, jacket design temperature −25 to 180 °C; 3. Vessel design pressure −0.1 to 0.1 MPa; jacket operating pressure 0.6 MPa; | Product contact: 316L stainless steel; Jacket: 304 stainless steel; Insulation: perlite powder; Insulation cladding: 304 stainless steel; | Various organic solvents | unit | 1 | Equipment stays in place; convert to quick-connect flare (NA) nozzles, purchase the parts | 25
5 | *** | Fraction receiving storage tank (non-jacketed) | Working volume 100 L, operating temperature −20 to 100 °C, operating pressure −0.098 to 0.099 MPa | SS316L | Various organic solvents | unit | 12 | Confirmed that new units can be delivered within 6–8 weeks, with little impact on the overall schedule | ? |  |  |  | The equipment shall comply with ASME BPE, including but not limited to: (1) NA-type connections meeting the 2D drainability requirement; connection sizes and quantities as per the approved drawings; (2) Spray port with spray ball, giving full coverage and passing the riboflavin coverage test; (3) Diaphragm valve welded to the outlet, meeting the 2D requirement; (4) External surface roughness < 0.8 µm, internal surface roughness < 0.4 µm; (5) Raw materials, components, manufacturing and acceptance strictly in line with ASME BPE, with the supporting documentation provided;
6 | *** | Pneumatic diaphragm pump | 5 m³/h, 25 m, quick-connect | SS316L | Various organic solvents | unit | 10 | Purchase new and install | 15 |  |  |  | The equipment shall comply with ASME BPE, including but not limited to: (1) NA-type connections meeting the 2D drainability requirement, with a fully drainable equipment body; (2) External surface roughness < 0.8 µm, internal surface roughness < 0.4 µm; (3) Raw materials, components, manufacturing and acceptance strictly in line with ASME BPE, with the supporting documentation provided;
21 | Components | Mass flow meter (quick-connect, BPE) | See attachment | 316L | —— | unit | See attachment | Newly purchased | 30 | [5 empty] | Retrofit of the ultrafiltration area – replacement of 1 storage tank (316L), BPE piping
22 |  | Pneumatic diaphragm control valve (quick-connect, BPE) | See attachment | 316L | —— | unit | See attachment | Newly purchased | 42 | [5 empty] | No. | Activity | Equipment / material | Lead time / duration | Expected delivery date | October | [11 empty] | November | [29 empty] | December
23 |  | Pneumatic diaphragm on/off valve (quick-connect, BPE) | See attachment | 316L | —— | unit | See attachment | Newly purchased | 42 | [10 empty] | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | Remarks
24 |  | Pneumatic control valve (quick-connect, BPE) | See attachment | 316L | —— | unit | See attachment | Newly purchased | 42 | [5 empty] | 1 | Equipment procurement | Delivery of the YD storage tanks (316L) | 40 | 20 Oct | [49 empty] | Ordered
25 |  | Pneumatic on/off valve (quick-connect, BPE) | See attachment | 316L | —— | unit | See attachment | Newly purchased | 42 | [5 empty] | 2 |  | Procurement of control valves / instruments (316L) | 42 | 25 Oct | [49 empty] | Partly ordered, partly not ordered; estimated delivery date
26 |  | Radar level transmitter | See attachment | 316L | —— | unit | See attachment | Newly purchased | 20 | [5 empty] | 3 |  | Procurement of BPE fittings (316L) | 30 | 15 Oct | [49 empty] | Ordered
27 |  | Tuning-fork level switch | See attachment | 316L | —— | unit | See attachment | Newly purchased | 20 | [5 empty] | 4 |  | BPE manual valves (316L) | 30 | 15 Oct | [49 empty] | Ordered
28 |  | Temperature instrument | See attachment | 316L | —— | unit | See attachment | Newly purchased | 20 | [5 empty] | 5 | On-site modification | Removal of sandwich panels, | 1 | [50 empty] | Remove in advance
29 |  | pH instrument | See attachment | 316L | —— | unit | See attachment | Newly purchased | 42 | [5 empty] | 6 |  | Removal and installation of the storage tank | 1 | [50 empty] | ——
30 |  | Pressure instrument | See attachment | 316L | —— | unit | See attachment | Newly purchased | 21 | [5 empty] | 7 |  | Replacement of BPE piping | 5 | [50 empty] | ——
31 |  | Manual diaphragm valve | See attachment | 316L | —— | unit | See attachment | Newly purchased | 45 | [5 empty] | 8 |  | Electrical and instrumentation installation | 3 | [50 empty] | ——
32 |  | BPE piping and fittings | See attachment | 316L | —— | unit | See attachment | Newly purchased | 35 | [5 empty] | 9 |  | Floor work and sealant treatment | 5 | [50 empty] | Equipment replacement; the floor is assumed to be redone
Ultrafiltration system equipment list | [14 empty] | 10 | Qualification + cleaning | Commissioning
No. | Equipment tag | Equipment name | Technical parameters | Equipment material | Process medium | Unit | Quantity | Option | Procurement lead time | Installation duration | Qualification duration | Total time | Technical requirements |  | 11 |  | IQ | [51 empty] | IQ runs in parallel with installation
1 | 1211-TFF01-T01 | Ultrafiltration receiving storage tank (jacketed) | 1. Working volume 1000 L; 2. Vessel design temperature −20 to 150 °C, jacket design temperature −25 to 180 °C; 3. Vessel design pressure −0.1 to 0.1 MPa; jacket operating pressure 0.6 MPa; | SS316L | Various organic solvents | unit | 1 | Reuse Yingde 1500 L storage tank (7) – 6-week modification (change to explosion-proof motor, bottom outlet valve) | 42 | 10 | 6 d, 24 h IQ runs in parallel with installation and is closed during commissioning; commissioning 1 d, EOQ + OQ 3 d, PQ 2 d | 19d | The equipment shall comply with ASME BPE, including but not limited to: (1) NA-type connections meeting the 2D drainability requirement; connection sizes and quantities as per the approved drawings; (2) Spray port with spray ball, giving full coverage and passing the riboflavin coverage test; (3) Diaphragm valve welded to the outlet, meeting the 2D requirement; (4) External surface roughness < 0.8 µm, internal surface roughness < 0.4 µm; (5) Raw materials, components, manufacturing and acceptance strictly in line with ASME BPE, with the supporting documentation provided; |  | 12 |  | OPQ
2 | Components | Mass flow meter (quick-connect, BPE) | See attachment | 316L | —— | unit | See attachment | Newly purchased | 30
3 |  | Pneumatic diaphragm control valve (quick-connect, BPE) | See attachment | 316L | —— | unit | See attachment | Newly purchased | 42
4 |  | Pneumatic diaphragm on/off valve (quick-connect, BPE) | See attachment | 316L | —— | unit | See attachment | Newly purchased | 42
5 |  | Manual diaphragm valve | See attachment | 316L | —— | unit | See attachment | Newly purchased | 45
6 |  | BPE piping and fittings | See attachment | 316L | —— | unit | See attachment | Newly purchased | 35 | [5 empty] | Retrofit of the precipitation area – replacement of the 2000 L Hastelloy reactor, filter-dryer (Hastelloy), 600 L storage tank, 80 L storage tank, BPE piping
Precipitation reactor area equipment list | [14 empty] | No. | Activity | Equipment / material | Lead time / duration | Expected delivery date | December | [16 empty] | January | [30 empty] | February
No. | Equipment tag | Equipment name | Technical parameters | Equipment material | Process medium | Unit | Quantity | Option | Procurement lead time | Installation duration | Qualification duration | Total time | Technical requirements | [6 empty] | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | Remarks
1 | 1211-R01 | Crystallizer | 1. Working volume 2000 L; 2. Reactor design temperature −25 to 200 °C, jacket design temperature −25 to 220 °C; 3. Reactor design pressure −0.1 to 0.4 MPa; jacket operating pressure 0.6 MPa; | Product contact: 304 stainless steel lined with C22 or C276; Jacket: 304 stainless steel; Insulation: perlite powder; Insulation cladding: 304 stainless steel; | Various organic solvents, acids, bases, etc. | unit | 1 | Purchase new and install | 100 | 30 | 18 d (qualification 18 d), 24 h Reactor / filter-dryer Requalification required Commissioning 1 d, HVAC EOQ + OQ 5 d, PQ 12 d, dead time | 51d | 1. The equipment shall comply with ASME BPE, including but not limited to: (1) NA-type connections meeting the 2D drainability requirement; connection sizes and quantities as per the approved drawings; (2) Spray port with spray ball, giving full coverage and passing the riboflavin coverage test; (3) Diaphragm valve welded to the outlet, meeting the 2D requirement; (4) External surface roughness < 0.8 µm, internal surface roughness < 0.4 µm; (5) Raw materials, components, manufacturing and acceptance strictly in line with ASME BPE, with the supporting documentation provided; 2. Motor and gearbox: (1) Well-known domestic brand; fully stainless-steel clad to sanitary standard; (2) Explosion protection Ex d IIB T4 Gb, ingress protection not lower than IP55; motor efficiency class 2 or better; 3. Double-end sanitary dry-running mechanical seal from a well-known domestic brand; 4. Agitator material identical to the vessel; agitator design as per the approved drawings; 5. Insulation thickness to suit the temperature requirement; cladding in 3 mm stainless steel with an external surface roughness < 0.8 µm, |  | 1 | Equipment procurement | Delivery of the 2000 L Hastelloy reactor | 100 | 25 Dec | [49 empty] | Ordered
2 | 1211-R01 | Crystallizer | 1. Working volume 2000 L; 2. Reactor design temperature −25 to 200 °C, jacket design temperature −25 to 220 °C; 3. Reactor design pressure −0.1 to 0.4 MPa; jacket operating pressure 0.6 MPa; | Product contact: 316L stainless steel; Jacket: 304 stainless steel; Insulation: perlite powder; Insulation cladding: 304 stainless steel; | Various organic solvents, acids, bases, etc. | unit | 1 | Purchase new and install | 100 | [5 empty] | 2 |  | Delivery of the DN1200 filter-dryer | 100 | 25 Dec | [49 empty] | Ordered
3 | 1211-AT01 | Agitated vessel | 1. Working volume 600 L; 2. Vessel design temperature −25 to 200 °C, jacket design temperature −25 to 220 °C; 3. Vessel design pressure −0.1 to 0.1 MPa; jacket operating pressure 0.6 MPa; | Product contact: 316L stainless steel; Jacket: 304 stainless steel; Insulation: perlite powder; Insulation cladding: 304 stainless steel; | Various organic solvents, salt solutions, etc. | unit | 1 | Purchase new and install | 75 | [5 empty] | 3 |  | Delivery of the storage tanks (316L) | 90 | 15 Dec | [49 empty] | Not ordered yet, estimated delivery date
4 | 1211-AT02 | Agitated vessel | 1. Working volume 80 L; 2. Vessel design temperature −25 to 200 °C, jacket design temperature −25 to 220 °C; 3. Vessel design pressure −0.1 to 0.1 MPa; jacket operating pressure 0.6 MPa; | Product contact: 316L stainless steel; Jacket: 304 stainless steel; Insulation: perlite powder; Insulation cladding: 304 stainless steel; | Various organic solvents, acids, bases, etc. | unit | 1 | Reuse Yingde 600 L storage tank (6) – 6-week modification (double-end mechanical seal, explosion-proof motor, bottom outlet valve) | 75 | [5 empty] | 4 |  | Delivery of the centrifugal pumps (316L) | 42 | 25 Oct | [49 empty] | Not ordered yet, estimated delivery date
5 | 1211-Fd01 | Filter-dryer | 1. Equipment size DN1200; 2. Vessel design temperature −25 to 200 °C, jacket design temperature −25 to 220 °C; 3. Vessel design pressure −0.1 to 0.1 MPa; jacket operating pressure 0.6 MPa; | Product contact: 304 stainless steel lined with C22 or C276; Jacket: 304 stainless steel; Insulation: perlite powder; Insulation cladding: 304 stainless steel; | Various organic solvents, acids, bases, etc. | unit | 1 | Purchase new and install | 120 |  |  |  | 1. The equipment shall comply with ASME BPE, including but not limited to: (1) NA-type connections meeting the 2D drainability requirement; connection sizes and quantities as per the approved drawings; (2) Spray port with spray ball, giving full coverage and passing the riboflavin coverage test; (3) Diaphragm valve welded to the outlet, meeting the 2D requirement; (4) External surface roughness < 0.8 µm, internal surface roughness < 0.4 µm; (5) Raw materials, components, manufacturing and acceptance strictly in line with ASME BPE, with the supporting documentation provided; 2. Motor and gearbox: (1) Well-known domestic brand; fully stainless-steel clad to sanitary standard; (2) Explosion protection Ex d IIB T4 Gb, ingress protection not lower than IP55; motor efficiency class 2 or better; 3. Double-end sanitary dry-running mechanical seal from a well-known imported brand such as John Crane or Burgmann; 4. Agitator material identical to the vessel; agitator design as per the approved drawings; 5. Insulation thickness to suit the temperature requirement; cladding in 3 mm stainless steel with an external surface roughness < 0.8 µm, |  | 5 |  | Procurement of control valves / instruments (316L) | 42 | 25 Oct | [49 empty] | Partly ordered, partly not ordered; estimated delivery date
6 | 1211-Fd01 | Filter-dryer | 1. Equipment size DN1200; 2. Vessel design temperature −25 to 200 °C, jacket design temperature −25 to 220 °C; 3. Vessel design pressure −0.1 to 0.1 MPa; jacket operating pressure 0.6 MPa; | Product contact: 316L stainless steel; Jacket: 304 stainless steel; Insulation: perlite powder; Insulation cladding: 304 stainless steel; | Various organic solvents, acids, bases, etc. | unit | 1 | Purchase new and install | 120 | [5 empty] | 6 |  | Procurement of BPE fittings (316L) | 30 | 15 Oct | [49 empty] | Ordered
7 | *** | Rotary sifter | Throughput 200 kg/h. | SS316L | Solids | unit | 1 | Purchase new and install | ? |  |  |  | 1. The equipment shall comply with ASME BPE, including but not limited to: (1) External surface roughness < 0.8 µm, internal surface roughness < 0.4 µm; (2) Raw materials, components, manufacturing and acceptance strictly in line with ASME BPE, with the supporting documentation provided; | Requirement to be confirmed by Production | 7 |  | BPE manual valves (316L) | 30 | 15 Oct | [49 empty] | Ordered
8 | Components | Mass flow meter (quick-connect, BPE) | See attachment | 316L | —— | unit | See attachment | Newly purchased | 30 | [5 empty] | 8 |  | BPE fittings (Hastelloy) | 60 | 30 Nov | [49 empty] | Ordered
9 |  | Pneumatic diaphragm control valve (quick-connect, BPE) | See attachment | 316L | —— | unit | See attachment | Newly purchased | 42 | [5 empty] | 9 | On-site modification | Removal of piping, electrics and sandwich panels | 4 | [50 empty] | Remove one week before the equipment arrives
10 |  | Pneumatic diaphragm on/off valve (quick-connect, BPE) | See attachment | 316L | —— | unit | See attachment | Newly purchased | 42 | [5 empty] | 10 |  | Removal of the steel platform | 2
11 |  | Manual diaphragm valve | See attachment | 316L | —— | unit | See attachment | Newly purchased | 45 | [5 empty] | 11 |  | Removal of the external wall | 1
12 |  | BPE piping and fittings | See attachment | 316L | —— | unit | See attachment | Newly purchased | 35 | [5 empty] | 12 |  | Equipment removal | 1
[15 empty] | 13 |  | Equipment lifting and assembly | 2 | [50 empty] | ——
[15 empty] | 14 |  | Reinstatement of the steel platform and the external wall | 5 | [50 empty] | ——
[15 empty] | 15 |  | Reinstatement of the sandwich panels | 5 | [50 empty] | ——
[15 empty] | 16 |  | Installation of equipment and piping | 10 | [50 empty] | ——
[15 empty] | 17 |  | Electrical and instrumentation installation | 5 | [50 empty] | ——
[15 empty] | 18 |  | Floor work and sealant treatment | 7 | [50 empty] | Large damaged area; the floor has to be redone, including detail work
[15 empty] | 19 | Qualification | HVAC commissioning + OQ / PQ

## 3. New Batch System (Opt.1) (hidden)
Peptide Building 2, new batch solution preparation system – equipment purchasing list – installed according to the P&ID
Preparation / solution system equipment list
No. | Equipment tag | Equipment name | Technical parameters | Equipment material | Process medium | Unit | Quantity | Equipment source | Procurement lead time | Installation duration | Qualification duration | Total time | Technical requirements
1 | *** | Salt solution agitated vessel (jacketed) | 1. Working volume 3000 L; 2. Vessel design temperature −20 to 150 °C, jacket design temperature −25 to 180 °C; 3. Vessel design pressure −0.1 to 0.1 MPa; jacket operating pressure 0.6 MPa; | Product contact: 304 stainless steel lined with C22 or C276; Jacket: 304 stainless steel; Insulation: perlite powder; Insulation cladding: 304 stainless steel; | Various organic solvents, acids, bases, etc. | unit | 2 | Newly purchased | 100 | 23 | 1. Engineering loop check 3 d; commissioning and qualification 15 d in total (software commissioning 4 d + pump commissioning 3 d + qualification 8 d: OQ 4 d, software EOQ 2 d, PQ 2 d) 2. The environment of the preparation area is affected (wall penetration welding is involved), so the corresponding microbial monitoring has to be repeated in parallel with the solution system; this does not affect the overall release date 3. The HVAC of the CNC area has to be re-qualified (OQ); this does not affect the overall release date |  | 1. The equipment shall comply with ASME BPE, including but not limited to: (1) NA-type connections meeting the 2D drainability requirement; connection sizes and quantities as per the approved drawings; (2) Spray port with spray ball, giving full coverage and passing the riboflavin coverage test; (3) Diaphragm valve welded to the outlet, meeting the 2D requirement; (4) External surface roughness < 0.8 µm, internal surface roughness < 0.4 µm; (5) Raw materials, components, manufacturing and acceptance strictly in line with ASME BPE, with the supporting documentation provided; 2. Motor and gearbox: (1) Well-known domestic brand; fully stainless-steel clad to sanitary standard; (2) Explosion protection Ex d IIB T4 Gb, ingress protection not lower than IP55; motor efficiency class 2 or better; 3. Double-end sanitary dry-running mechanical seal from a well-known domestic brand; 4. Agitator material identical to the vessel; agitator design as per the approved drawings; 5. Insulation thickness to suit the temperature requirement; cladding in 3 mm stainless steel with an external surface roughness < 0.8 µm,
2 | *** | Salt solution agitated vessel (jacketed) | 1. Working volume 3000 L; 2. Vessel design temperature −20 to 150 °C, jacket design temperature −25 to 180 °C; 3. Vessel design pressure −0.1 to 0.1 MPa; jacket operating pressure 0.6 MPa; | Product contact: 316L stainless steel; Jacket: 304 stainless steel; Insulation: perlite powder; Insulation cladding: 304 stainless steel; | Various organic solvents, acids, bases, etc. | unit | 2 | Newly purchased | 75
3 | *** | Mobile phase A agitated vessel (jacketed) | 1. Working volume 3000 L; 2. Vessel design temperature −20 to 150 °C, jacket design temperature −25 to 180 °C; 3. Vessel design pressure −0.1 to 0.1 MPa; jacket operating pressure 0.6 MPa; | Product contact: 316L stainless steel; Jacket: 304 stainless steel; Insulation: perlite powder; Insulation cladding: 304 stainless steel; | Various organic solvents, acids, bases, etc. | unit | 2 | Newly purchased | 75
4 | *** | Mobile phase B agitated vessel (jacketed) | 1. Working volume 3000 L; 2. Vessel design temperature −20 to 150 °C, jacket design temperature −25 to 180 °C; 3. Vessel design pressure −0.1 to 0.1 MPa; jacket operating pressure 0.6 MPa; | Product contact: 316L stainless steel; Jacket: 304 stainless steel; Insulation: perlite powder; Insulation cladding: 304 stainless steel; | Various organic solvents, acids, bases, etc. | unit | 3 | Newly purchased | 75
5 | *** | Acetonitrile storage tank (non-jacketed) | Working volume 1000 L, operating temperature −20 to 100 °C, operating pressure −0.098 to 0.099 MPa | SS316L | Fresh acetonitrile | unit | 2 | Newly purchased | 75 |  |  |  | The equipment shall comply with ASME BPE, including but not limited to: (1) NA-type connections meeting the 2D drainability requirement; connection sizes and quantities as per the approved drawings; (2) Spray port with spray ball, giving full coverage and passing the riboflavin coverage test; (3) Diaphragm valve welded to the outlet, meeting the 2D requirement; (4) External surface roughness < 0.8 µm, internal surface roughness < 0.4 µm; (5) Raw materials, components, manufacturing and acceptance strictly in line with ASME BPE, with the supporting documentation provided;
6 | *** | Methanol storage tank (non-jacketed) | Working volume 1000 L, operating temperature −20 to 100 °C, operating pressure −0.098 to 0.099 MPa | SS316L | Fresh methanol | unit | 1 | Newly purchased | 75
7 | *** | Purified water storage tank (non-jacketed) | Working volume 1000 L, operating temperature −20 to 100 °C, operating pressure −0.098 to 0.099 MPa | SS316L | Purified water | unit | 1 | Newly purchased | 75
8 | *** | Sanitary centrifugal pump | Rated flow 12.5 m³/h, head 25 m, clamp connection | C22 or C276 | Concentrated salt solution | unit | 2 | Newly purchased | 45 |  |  |  | The equipment shall comply with ASME BPE, including but not limited to: (1) NA-type connections meeting the 2D drainability requirement, with a fully drainable equipment body; (2) External surface roughness < 0.8 µm, internal surface roughness < 0.4 µm; (3) Raw materials, components, manufacturing and acceptance strictly in line with ASME BPE, with the supporting documentation provided;
9 | *** | Sanitary centrifugal pump | Rated flow 12.5 m³/h, head 25 m, clamp connection | SS316L | Mobile phase A | unit | 3 | Newly purchased | 45
10 | *** | Sanitary centrifugal pump | Rated flow 12.5 m³/h, head 25 m, clamp connection | SS316L | Mobile phase B | unit | 3 | Newly purchased | 45
11 | *** | Sanitary centrifugal pump | Rated flow 12.5 m³/h, head 25 m, clamp connection | SS316L | Purified water | unit | 2 | Newly purchased | 45
12 | *** | Sanitary centrifugal pump | Rated flow 3.2 m³/h, head 25 m, clamp connection | SS316L | Acetonitrile | unit | 2 | Newly purchased | 45
13 | *** | Sanitary centrifugal pump | Rated flow 5 m³/h, head 30 m, clamp connection | SS316L | Methanol | unit | 3 | Newly purchased | 45
14 | *** | Sanitary centrifugal pump | Rated flow 5 m³/h, head 30 m, clamp connection | SS316L | Waste liquid | unit | 2 | Newly purchased | 45
21 | Components | Mass flow meter (quick-connect, BPE) | See attachment | 316L | —— | unit | See attachment | Newly purchased | 30 |  |  |  | BPE requirements
22 |  | Pneumatic diaphragm control valve (quick-connect, BPE) | See attachment | 316L | —— | unit | See attachment | Newly purchased | 42
23 |  | Pneumatic diaphragm on/off valve (quick-connect, BPE) | See attachment | 316L | —— | unit | See attachment | Newly purchased | 42
24 |  | Pneumatic control valve (quick-connect, BPE) | See attachment | 316L | —— | unit | See attachment | Newly purchased | 42
25 |  | Pneumatic on/off valve (quick-connect, BPE) | See attachment | 316L | —— | unit | See attachment | Newly purchased | 42
26 |  | Radar level transmitter | See attachment | 316L | —— | unit | See attachment | Newly purchased | 20
27 |  | Tuning-fork level switch | See attachment | 316L | —— | unit | See attachment | Newly purchased | 20
28 |  | Temperature instrument | See attachment | 316L | —— | unit | See attachment | Newly purchased | 20
29 |  | pH instrument | See attachment | 316L | —— | unit | See attachment | Newly purchased | 42
30 |  | Pressure instrument | See attachment | 316L | —— | unit | See attachment | Newly purchased | 21
31 |  | Manual diaphragm valve | See attachment | 316L | —— | unit | See attachment | Newly purchased | 45
32 |  | BPE piping and fittings | See attachment | 316L | —— | unit | See attachment | Newly purchased | 35

## 4. Option 1 - Retrofit Only (hidden)
Peptide Building 2, replacement of existing equipment – purchasing list – covers only the modification of the existing installation to meet the latest customer meeting requirements, completion around 30 Nov 2026
Preparation system – continuous solution preparation – CNC area – equipment list – customer requirements | [14 empty] | Assumes the retrofit starts when production finishes, around 15 October; | [47 empty] | Assumes the retrofit starts when production finishes, around 15 October;
No. | Equipment tag | Equipment name | Technical parameters | Equipment material | Process medium | Unit | Quantity | Equipment source | Modification requirement | Procurement lead time (days) | Status as of 09/17 | Modification duration | Qualification duration | Total time including 3 days of cleaning | Retrofit of the continuous solution preparation system – convert the 3000 L Hastelloy reactor to TC connections, replace the 2 concentrated-salt vessels with YD storage tanks (316L), BPE piping (316L). Open points: the TC connections on the existing site tanks were made in-house, so the customer's opinion is needed; it must be assessed whether 316L is acceptable for the concentrated-salt piping. | [47 empty] | Retrofit of the continuous solution preparation system – convert the flanges of the 3000 L Hastelloy reactor to TC, convert the flanges of the 2 Hastelloy concentrated-salt vessels to TC, BPE piping (316L + Hastelloy). Open point: the TC connections on the existing site tanks were made in-house, so the customer's opinion is needed.
1 | 1213-R05 | Hastelloy reactor | 3000 L Hastelloy reactor | C276 | Concentrated salt solution | unit | 1 | Existing installed equipment | All nozzles of this reactor are flanged and have to be changed to quick-connect fittings so that the whole unit meets the Category 4 piping and equipment requirements. This includes the water charging line of the reactor and the discharge lines to AT01 and AT02, which have to meet the Category 4 piping requirements in C276. Production has no window for a return-to-factory repair, because the area is producing the three fragment peptides for Eli Lilly. An on-site modification concept is therefore needed. | Option 1: reuse the unit from Peptide Building 3, expected to arrive end of October Option 2: return-to-factory modification, 60 days (the vendor has not confirmed an exact time; based on Peptide Building 3). Repeated discussions with the vendor confirmed that on-site modification is not possible. Option 3: buy new, 100 days | The modification concept for the vessel body, agitator, manway and bottom outlet is fixed; the vendor is expected on site in mid-October; drawings are being aligned. Hastelloy valve models are being confirmed and procurement is starting; delivery is expected to take 50 days. A set of Hastelloy ball valves will be supplied together with the reactor from Peptide Building 3. The reactor has no pH port; whether one has to be added is being confirmed today. | 20 days of installation work after the equipment and materials arrive | Option 1: 15 d Option 2: 7 d Option 3: 15 d | Option 1: 39 d Option 2: 31 d Option 3: 39 d | No. | Activity | Equipment / material | Lead time / duration | Expected delivery date | October | [16 empty] | November | [25 empty] | No. | Activity | Equipment / material | Lead time / duration | Expected delivery date | October | [16 empty] | November | [21 empty] | December | [18 empty] | 2027-01-01
2 | 1211-HPPC03-AT01 | Solution preparation agitated vessel (non-jacketed) | Working volume 500 L, operating temperature −20 to 100 °C, operating pressure −0.098 to 0.099 MPa | C276 | Concentrated salt solution | unit | 1 | Existing installed equipment | The bottom discharge valve and part of the top piping of this tank remain; they have to be changed to quick-connect, NA or flare connections in Hastelloy, executed to the Category 4 equipment requirements. This includes the piping from the tank via the static mixer to phases A and B, executed to the Category 4 piping requirements. | Option 1: modify a Yingde 316L storage tank, 40 days (provided that 316L is acceptable; under assessment by Production) Option 2: return-to-factory modification, 60 days (the vendor has not confirmed an exact time; based on Peptide Building 3) Option 3: buy new, 100 days | Option 1: the Yingde tank is in production; the 30 + 20 day delivery schedule is being pushed; drawings have been returned to the vendor Option 2: drawings are being confirmed; the large ring flange has to be reworked at the factory and no lead time has been given yet |  | Option 1: 4 d Option 2: 4 d Option 3: 6 d | Option 1: 28 d Option 2: 28 d Option 3: 30 d | [5 empty] | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | Remarks | [5 empty] | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 5 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 5 | 10 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | Remarks
3 | 1211-HPPC03-AT02 | Solution preparation agitated vessel (non-jacketed) | Working volume 300 L, operating temperature −20 to 100 °C, operating pressure −0.098 to 0.099 MPa | C276 | Concentrated salt solution | unit | 1 | Existing installed equipment | The bottom discharge valve and part of the top piping of this tank remain; they have to be changed to quick-connect, NA or flare connections in Hastelloy, executed to the Category 4 equipment requirements. This includes the piping from the tank via the static mixer to phases A and B, executed to the Category 4 piping requirements. |  | Top and bottom flanges; the vendor will modify them on site. The drawings can be finalised today. |  |  |  | 1 | Equipment procurement | Delivery of the 3000 L Hastelloy reactor parts | 40 | 20 Oct | [42 empty] | Ordered | 1 | Equipment procurement | Delivery of the 3000 L Hastelloy reactor parts | 40 | 20 Oct | [63 empty] | Ordered
5 | 1211-HPPC03-T01 | Purified water storage tank (non-jacketed) | Working volume 1000 L, operating temperature −20 to 100 °C, operating pressure −0.098 to 0.099 MPa | SS316L | Purified water | unit | 1 | Existing installed equipment | Already compliant | —— | Already compliant |  | - |  | 2 |  | Delivery of the YD storage tanks (316L) | 40 | 20 Oct | [42 empty] | Ordered | 2 |  | Convert the concentrated-salt vessel flanges to TC (Hastelloy) | 40 | 20 Oct | [63 empty] | Ordered
6 | 1211-HPPC03-T02 | Acetonitrile storage tank (non-jacketed) | Working volume 1000 L, operating temperature −20 to 100 °C, operating pressure −0.098 to 0.099 MPa | SS316L | Fresh acetonitrile, spare | unit | 1 | Existing installed equipment | Already compliant | —— | Already compliant |  | - |  | 3 |  | Delivery of the centrifugal pumps (316L) | 42 | 25 Oct | [42 empty] | Not ordered yet, estimated delivery date | 3 |  | Delivery of the centrifugal pumps (316L) | 42 | 25 Oct | [63 empty] | Not ordered yet, estimated delivery date
7 | 1211-HPPC03-T03 | Mobile phase A storage tank (non-jacketed) | Working volume 1000 L, operating temperature −20 to 100 °C, operating pressure −0.098 to 0.099 MPa | SS316L | Mobile phase A | unit | 1 | Existing installed equipment | Already compliant | —— | Already compliant |  | - |  | 4 |  | Delivery of the four-head diaphragm pumps (316L) | 25 | 10 Oct | [42 empty] | Ordered | 4 |  | Delivery of the four-head diaphragm pumps (316L) | 25 | 10 Oct | [63 empty] | Ordered
8 | 1211-HPPC03-T04 | Mobile phase B storage tank (non-jacketed) | Working volume 1000 L, operating temperature −20 to 100 °C, operating pressure −0.098 to 0.099 MPa | SS316L | Mobile phase B | unit | 1 | Existing installed equipment | Already compliant | —— | Already compliant |  | - |  | 5 |  | Procurement of control valves / instruments (316L) | 42 | 25 Oct | [42 empty] | Partly ordered, partly not ordered; estimated delivery date | 5 |  | Delivery of the four-head diaphragm pumps (Hastelloy) | 90 | 15 Dec | [63 empty] | Not ordered yet, estimated delivery date
9 | 1211-HPPC03-T05 | Acetonitrile storage tank (non-jacketed) | Working volume 1000 L, operating temperature −20 to 100 °C, operating pressure −0.098 to 0.099 MPa | SS316L | Acetonitrile | unit | 1 | Existing installed equipment | Already compliant | —— | Already compliant |  | - |  | 6 |  | Procurement of BPE fittings (316L) | 30 | 15 Oct | [42 empty] | Ordered | 6 |  | Procurement of control valves / instruments (316L) | 42 | 25 Oct | [63 empty] | Partly ordered, partly not ordered; estimated delivery date
10 | 1211-HPPC03-T03-P01 | Sanitary centrifugal pump | Rated flow 2.5 m³/h, head 25 m, clamp connection | SS316L | Mobile phase A | unit | 1 | Supplied by the equipment vendor | Purchase replacement centrifugal pumps; quotations in progress | Estimated 35 days | To be sent to the vendor once the drawings are signed; the procurement approval was completed today. The contract is to be confirmed as soon as possible. |  | 8 d (dosing accuracy, uniformity and RSD all have to be re-qualified) |  | 7 |  | BPE manual valves (316L) | 30 | 15 Oct | [42 empty] | Ordered | 7 |  | Procurement of BPE fittings (316L) | 30 | 15 Oct | [63 empty] | Ordered
11 | 1211-HPPC03-T03-P02 | Sanitary centrifugal pump | Rated flow 3.2 m³/h, head 25 m, clamp connection, fixed speed | SS316L | Metered transfer of mobile phase A | unit | 1 | New purchase required | [6 empty] | 8 | On-site modification | On-site nozzle modification of the 3000 L Hastelloy reactor | 10 |  | Nozzle cutting | [41 empty] | Cut the vessel nozzles in advance | 8 |  | Procurement of BPE fittings (Hastelloy) | 60 | 15 Oct | [63 empty] | Ordered
12 | 1211-HPPC03-T04-P01 | Sanitary centrifugal pump | Rated flow 2.5 m³/h, head 25 m, clamp connection | SS316L | Mobile phase B / fresh acetonitrile | unit | 1 | Supplied by the equipment vendor | [6 empty] | 9 |  | Piping of the 3000 L Hastelloy reactor (316L) | 4 | [43 empty] | Everything except the dip tube is 316L | 9 | On-site modification | On-site conversion of the 3000 L Hastelloy reactor to TC connections | 13 |  | Cut the nozzles in advance | [5 empty] | Welding and polishing | [56 empty] | Cut the vessel nozzles in advance
13 | 1211-HPPC03-WT01-P01 | Centrifugal pump | Rated flow 3.2 m³/h, head 20 m, clamp connection | 304 | Preparation waste liquid | unit | 1 | Existing installed equipment | [6 empty] | 10 |  | Removal / installation of the concentrated-salt vessels | 2 | [43 empty] | Waiting for delivery of the storage tanks | 10 |  | Piping of the 3000 L Hastelloy reactor (Hastelloy) | 4 | [64 empty] | Waiting for delivery of the Hastelloy parts
14 | 1211-HPPC03-WT02-P01 | Centrifugal pump | Rated flow 3.2 m³/h, head 20 m, clamp connection | 304 | Preparation waste liquid | unit | 1 | Existing installed equipment | [6 empty] | 11 |  | Replacement of pumps and BPE piping | 19 | [43 empty] | —— | 11 |  | On-site conversion of the concentrated-salt vessel flanges to TC | 13 |  | Cut the nozzles in advance | [5 empty] | Welding and polishing | [56 empty] | Only the flanged nozzles are modified; the existing quick-connect nozzles stay as they are
15 | 1211-HPPC03-AT01-P01 | Sanitary four-head diaphragm pump | Rated flow 3.0 L/min, BPE connection, clamp connection | 316L or C276 | Concentrated salt solution | unit | 1 | New purchase required | Purchase replacement four-head diaphragm pumps | Estimated 20 days | The 316L units are ordered and are expected end of September; the request was raised by Production (Guo Zepeng). The Hastelloy units have a 3-month lead time and are expected in December; the order is placed. |  | 8 d (dosing accuracy, uniformity and RSD all have to be re-qualified) |  | 12 |  | Electrical and instrumentation installation | 10 | [43 empty] | —— | 12 |  | Change the pumps and the Hastelloy piping of the concentrated-salt vessels | 4 | [64 empty] | Replace once the Hastelloy pumps arrive
16 | 1211-HPPC03-AT02-P01 | Sanitary four-head diaphragm pump | Rated flow 2.0 L/min, BPE connection, clamp connection | 316L or C276 | Concentrated salt solution | unit | 1 | New purchase required | [6 empty] | 13 | Qualification | Commissioning | [44 empty] | IQ runs in parallel with installation; IQ is closed after the loop check and is completed during software commissioning | 13 |  | Change the pumps and the BPE piping of the other storage tanks | 20
17 | 1211-HPPC03-T01-P01 | Sanitary four-head diaphragm pump | Rated flow 35 L/min, BPE connection, clamp connection | SS316L | Purified water | unit | 1 | New purchase required | [6 empty] | 14 |  | Loop check | [44 empty] | —— | 14 |  | Electrical and instrumentation installation | 10 | [64 empty] | ——
18 | 1211-HPPC03-T01-P02 | Sanitary four-head diaphragm pump | Rated flow 3.0 L/min, BPE connection, clamp connection | SS316L | Purified water | unit | 1 | New purchase required | [6 empty] | 15 |  | OQ | [44 empty] | —— | 18 | Qualification | Commissioning
19 | 1211-HPPC03-T02-P01 | Sanitary four-head diaphragm pump | Rated flow 5.0 L/min, BPE connection, clamp connection | SS316L | Fresh acetonitrile | unit | 1 | New purchase required | [6 empty] | 16 |  | PQ | [44 empty] | —— | 19 |  | Loop check
20 | 1211-HPPC03-T02-P02 | Sanitary four-head diaphragm pump | Rated flow 35 L/min, BPE connection, clamp connection | SS316L | Fresh acetonitrile | unit | 1 | New purchase required |  |  |  |  | Can be qualified together with the equipment |  | 17 | Equipment preparation | Cleaning | [44 empty] | —— | 20 |  | OQ
| TJ4S-1213-R05-P01 | Sanitary four-head diaphragm pump | Rated flow 35 L/min, BPE connection, clamp connection | 316L or C276 | Concentrated salt solution | unit | 1 | New purchase required | [54 empty] | 21 |  | PQ
21 | Components | Mass flow meter (quick-connect, BPE) | See attachment | 316L | —— | unit | See attachment | Existing installed equipment | Acceptable | —— | Acceptable | [51 empty] | 22 | Equipment preparation | Cleaning
22 |  | Pneumatic diaphragm control valve (quick-connect, BPE) | See attachment | 316L | —— | unit | See attachment | Existing installed equipment | Purchase quick-connect diaphragm control valves | 42 days | All have been issued for purchase; delivery dates are estimates, |  |  |  | Retrofit of the fraction receiving area – replace the pumps (316L) and the BPE piping (316L). Open point: the TC connections on the existing site tanks were made in-house, so the customer's opinion is needed. | [47 empty] | 23 | Supplementary qualification | Supplementary IQ (materials, nameplates, P&ID) | [45 empty] | No additional time needed
23 |  | Pneumatic diaphragm on/off valve (quick-connect, BPE) | See attachment | 316L | —— | unit | See attachment | Existing installed equipment | Purchase quick-connect diaphragm control valves | 42 days | All have been issued for purchase, |  |  |  | No. | Activity | Equipment / material | Lead time / duration | Expected delivery date | October | [11 empty] | November | [30 empty] | 24 |  | Commissioning (pumps, software)
24 |  | Pneumatic control valve (quick-connect, BPE) | See attachment | 316L | —— | unit | See attachment | Existing installed equipment | Purchase quick-connect diaphragm control valves | 35 days | All have been issued for purchase, | [8 empty] | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | Remarks | 25 |  | OQ (pressure-hold leak test, pump flow accuracy)
25 |  | Pneumatic on/off valve (quick-connect, BPE) | See attachment | 316L | —— | unit | See attachment | Existing installed equipment | Purchase quick-connect diaphragm control valves | 35 days | All have been issued for purchase, |  |  |  | 1 | Equipment procurement | Delivery of the centrifugal pumps (316L) | 42 | 25 Oct | [42 empty] | Not ordered yet, estimated delivery date | 26 |  | PQ (solution preparation confirmation)
26 |  | Radar level transmitter | See attachment | 316L | —— | unit | See attachment | Existing installed equipment | Acceptable | —— | Acceptable |  |  |  | 2 |  | Procurement of control valves / instruments (316L) | 42 | 25 Oct | [42 empty] | Partly ordered, partly not ordered; estimated delivery date | 27 | Equipment preparation | Cleaning
27 |  | Tuning-fork level switch | See attachment | 316L | —— | unit | See attachment | Existing installed equipment | Acceptable | —— | Acceptable |  |  |  | 3 |  | Procurement of BPE fittings (316L) | 30 | 15 Oct | [42 empty] | Ordered
28 |  | Temperature instrument | See attachment | 316L | —— | unit | See attachment | Existing installed equipment | Acceptable | —— | Acceptable |  |  |  | 4 |  | BPE manual valves (316L) | 30 | 15 Oct | [42 empty] | Ordered
29 |  | pH instrument | See attachment | 316L | —— | unit | See attachment | Existing installed equipment | Acceptable | —— | Acceptable |  |  |  | 5 | On-site modification | Removal of the existing pumps and piping | 1 | [43 empty] | ——
30 |  | Pressure instrument | See attachment | 316L | —— | unit | See attachment | Existing installed equipment | Acceptable | —— | Acceptable |  |  |  | 6 |  | Replacement with new pumps and BPE piping | 15 | [43 empty] | ——
31 |  | Manual diaphragm valve | See attachment | 316L | —— | unit | See attachment | Existing installed equipment | Acceptable | —— | Acceptable |  |  |  | 7 |  | Electrical and instrumentation installation | 7 | [43 empty] | ——
32 |  | BPE piping and fittings | See attachment | 316L | —— | unit | See attachment | Existing installed equipment | The piping is replaced entirely to BPE standard, meeting the 2D and drainability requirements for Category 4 piping | BPE fittings 28 days; BPE valves 42 days; Hastelloy parts 60 days (to be confirmed whether 316L can be used instead) | All have been issued for purchase, |  |  |  | 8 | Qualification | HVAC | [18 empty] | Hot work is involved, so one at-rest and one in-operation monitoring run with 5-day incubation is required | [25 empty] | IQ runs in parallel with installation
Preparation system – Grade D area – equipment list – customer requirements | [14 empty] | 9 |  | Storage tanks and piping | [44 empty] | ——
No. | Equipment tag | Equipment name | Technical parameters | Equipment material | Process medium | Unit | Quantity | Option | Modification requirement | Procurement lead time |  | Installation duration | Qualification duration | Total time | 10 | Equipment preparation | Cleaning
1 | 1211-HPPC03-AT03 | Fraction receiving agitated vessel (jacketed) | 1. Working volume 8000 L; 2. Vessel design temperature −20 to 150 °C, jacket design temperature −25 to 180 °C; 3. Vessel design pressure −0.1 to 0.1 MPa; jacket operating pressure 0.6 MPa; | Product contact: 316L stainless steel; Jacket: 304 stainless steel; Insulation: perlite powder; Insulation cladding: 304 stainless steel; | Various organic solvents | unit | 1 | Existing installed equipment | Acceptable | —— | Acceptable | 15 days of installation work after the equipment and materials arrive | 3d | 21d
2 | 1211-HPPC03-AT04/AT05 | Fraction receiving agitated vessel (jacketed) | 1. Working volume 3000 L; 2. Vessel design temperature −20 to 150 °C, jacket design temperature −25 to 180 °C; 3. Vessel design pressure −0.1 to 0.1 MPa; jacket operating pressure 0.6 MPa; | Product contact: 316L stainless steel; Jacket: 304 stainless steel; Insulation: perlite powder; Insulation cladding: 304 stainless steel; | Various organic solvents | unit | 2 | Existing installed equipment | Acceptable | —— | Acceptable
3 | 1211-HPPC03-AT06 | Sample agitated vessel (jacketed) | 1. Working volume 1000 L; 2. Vessel design temperature −20 to 150 °C, jacket design temperature −25 to 180 °C; 3. Vessel design pressure −0.1 to 0.1 MPa; jacket operating pressure 0.6 MPa; | Product contact: 316L stainless steel; Jacket: 304 stainless steel; Insulation: perlite powder; Insulation cladding: 304 stainless steel; | Various organic solvents | unit | 1 | Existing installed equipment | Acceptable | —— | Acceptable |  |  |  | Retrofit of the ultrafiltration area – replace the BPE piping (316L). Open point: the TC connections on the existing site tanks were made in-house, so the customer's opinion is needed.
4 | 1211-HPPC03-T06 | Top-fraction sample agitated vessel (jacketed) | 1. Working volume 1000 L; 2. Vessel design temperature −20 to 150 °C, jacket design temperature −25 to 180 °C; 3. Vessel design pressure −0.1 to 0.1 MPa; jacket operating pressure 0.6 MPa; | Product contact: 316L stainless steel; Jacket: 304 stainless steel; Insulation: perlite powder; Insulation cladding: 304 stainless steel; | Various organic solvents | unit | 1 | Existing installed equipment | Acceptable | —— | Acceptable |  |  |  | No. | Activity | Equipment / material | Lead time / duration | Expected delivery date | October | [11 empty] | November
5 | *** | Fraction receiving storage tank (non-jacketed) | Working volume 100 L, operating temperature −20 to 100 °C, operating pressure −0.098 to 0.099 MPa | SS316L | Various organic solvents | unit | 12 | Existing installed equipment | Acceptable | —— | Acceptable | [8 empty] | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | Remarks
| 1211-HPPC03-AT03-P01 | Sanitary centrifugal pump | Rated flow 12.5 m³/h, head 25 m, clamp connection, variable speed | SS316L | Various organic solvents | unit | 1 | New purchase required |  |  | To be sent to the vendor once the drawings are signed; the procurement approval was completed today. The contract is to be confirmed as soon as possible. |  |  |  | 1 | Equipment procurement | Procurement of control valves / instruments (316L) | 42 | 25 Oct | [42 empty] | Partly ordered, partly not ordered; estimated delivery date
| 1211-HPPC03-AT03-P02 | Sanitary centrifugal pump, to ultrafiltration | Rated flow 2 m³/h, head 20 m, clamp connection, fixed speed | SS316L | Various organic solvents | unit | 1 | New purchase required | [6 empty] | 2 |  | Procurement of BPE fittings (316L) | 30 | 15 Oct | [42 empty] | Ordered
| 1211-HPPC03-AT04-P01 | Sanitary centrifugal pump | Rated flow 12.5 m³/h, head 25 m, clamp connection, variable speed | SS316L | Various organic solvents | unit | 1 | New purchase required | [6 empty] | 3 |  | BPE manual valves (316L) | 30 | 15 Oct | [42 empty] | Ordered
| 1211-HPPC03-AT05-P01 | Sanitary centrifugal pump | Rated flow 12.5 m³/h, head 25 m, clamp connection, variable speed | SS316L | Various organic solvents | unit | 1 | New purchase required | [6 empty] | 4 | On-site modification | Replacement of BPE piping | 5 | [43 empty] | ——
| 1211-HPPC03-AT06-P01 | Sanitary centrifugal pump | Rated flow 12.5 m³/h, head 25 m, clamp connection, variable speed | SS316L | Various organic solvents | unit | 1 | New purchase required | [6 empty] | 5 |  | Electrical and instrumentation installation | 3 | [43 empty] | ——
| 1211-HPPC03-T06-P01 | Sanitary centrifugal pump | Rated flow 3.2 m³/h, head 25 m, clamp connection, fixed speed | SS316L | Various organic solvents | unit | 1 | New purchase required | [6 empty] | 6 | Qualification | HVAC | [10 empty] | Hot work is involved, so one at-rest and one in-operation monitoring run with 5-day incubation is required | [33 empty] | IQ runs in parallel with installation
6 | *** | Pneumatic diaphragm pump | 5 m³/h, 25 m, quick-connect | SS316L | Various organic solvents | unit | 2 | Existing installed equipment | Charging and discharging of the homogenisation vessel | 35 days | Completed |  |  |  | 7 |  | Storage tanks and piping | [44 empty] | ——
| *** | Sanitary centrifugal pump | Rated flow 2 m³/h, head 20 m, clamp connection, fixed speed | SS316L | In-spec fractions | unit | 1 |  |  |  | To be sent to the vendor once the drawings are signed; the procurement approval was completed today. The contract is to be confirmed as soon as possible. |  |  |  | 8 | Equipment preparation | Cleaning
| *** | Pneumatic diaphragm pump | Rated flow 5 m³/h, head 25 m, clamp connection | SS316L | Out-of-spec fractions | unit | 1 |  |  |  | Fit for use
7 | Components | Mass flow meter (quick-connect, BPE) | See attachment | 316L | —— | unit | See attachment | Existing installed equipment | Acceptable | —— | Acceptable
8 |  | Pneumatic diaphragm control valve (quick-connect, BPE) | See attachment | 316L | —— | unit | See attachment | Existing installed equipment | Purchase quick-connect control valves | 42 days | All have been issued for purchase,
9 |  | Pneumatic diaphragm on/off valve (quick-connect, BPE) | See attachment | 316L | —— | unit | See attachment | Existing installed equipment | Purchase quick-connect on/off valves | 42 days | All have been issued for purchase, |  |  |  | Retrofit of the precipitation area – replace the 80 L storage tank (316L) and the BPE piping (316L). Open point: the TC connections on the existing site equipment (reactor, filter-dryer, storage tanks) were made in-house, so the customer's opinion is needed.
10 |  | Pneumatic control valve (quick-connect, BPE) | See attachment | 316L | —— | unit | See attachment | Existing installed equipment | Purchase quick-connect control valves | 35 days | All have been issued for purchase, |  |  |  | No. | Activity | Equipment / material | Lead time / duration | Expected delivery date | October | [11 empty] | November
11 |  | Pneumatic on/off valve (quick-connect, BPE) | See attachment | 316L | —— | unit | See attachment | Existing installed equipment | Purchase quick-connect on/off valves | 35 days | All have been issued for purchase, | [8 empty] | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | Remarks
12 |  | Radar level transmitter | See attachment | 316L | —— | unit | See attachment | Existing installed equipment | Acceptable | —— | Acceptable |  |  |  | 1 | Equipment procurement | Delivery of the YD 150 L storage tank (316L) | 40 | 20 Oct | [42 empty] | Ordered
13 |  | Tuning-fork level switch | See attachment | 316L | —— | unit | See attachment | Existing installed equipment | Acceptable | —— | Acceptable |  |  |  | 2 |  | Delivery of the centrifugal pumps (316L) | 42 | 25 Oct | [42 empty] | Not ordered yet, estimated delivery date
14 |  | Temperature instrument | See attachment | 316L | —— | unit | See attachment | Existing installed equipment | Acceptable | —— | Acceptable |  |  |  | 3 |  | Procurement of control valves / instruments (316L) | 42 | 25 Oct | [42 empty] | Partly ordered, partly not ordered; estimated delivery date
15 |  | pH instrument | See attachment | 316L | —— | unit | See attachment | Existing installed equipment | Acceptable | —— | Acceptable |  |  |  | 4 |  | Procurement of BPE fittings (316L) | 30 | 15 Oct | [42 empty] | Ordered
16 |  | Pressure instrument | See attachment | 316L | —— | unit | See attachment | Existing installed equipment | Acceptable | —— | Acceptable |  |  |  | 5 |  | BPE manual valves (316L) | 30 | 15 Oct | [42 empty] | Ordered
17 |  | Manual diaphragm valve | See attachment | 316L | —— | unit | See attachment | Existing installed equipment | Acceptable | —— | Acceptable |  |  |  | 6 |  | Removal / installation of the 80 L vessel, installation of the wet nitrogen supply | 1 | [43 empty] | Waiting for delivery of the storage tanks
18 |  | BPE piping and fittings | See attachment | 316L | —— | unit | See attachment | Existing installed equipment | The piping is replaced entirely to BPE standard, meeting the 2D and drainability requirements for Category 4 piping | BPE fittings 28 days; BPE valves 42 days | All have been issued for purchase; a supplementary order for the T-valves is being placed today. |  |  |  | 7 |  | Replacement of pumps and BPE piping | 15 | [43 empty] | ——
Ultrafiltration system equipment list – internal assessment | [14 empty] | 8 |  | Electrical and instrumentation installation | 7 | [43 empty] | ——
No. | Equipment tag | Equipment name | Technical parameters | Equipment material | Process medium | Unit | Quantity | Option | Modification requirement | Procurement lead time |  | Installation duration | Qualification duration | Total time | 9 | Qualification | HVAC | [18 empty] | Hot work is involved, so one at-rest and one in-operation monitoring run with 5-day incubation is required | [25 empty] | IQ runs in parallel with installation
1 | 1211-TFF01-T01 | Ultrafiltration receiving storage tank (jacketed) | 1. Working volume 1000 L; 2. Vessel design temperature −20 to 150 °C, jacket design temperature −25 to 180 °C; 3. Vessel design pressure −0.1 to 0.1 MPa; jacket operating pressure 0.6 MPa; | SS316L | Various organic solvents | unit | 1 | Existing installed equipment | Acceptable | —— | Acceptable | Around 5 days of installation work after the fittings arrive | 3d | 11d | 10 |  | Storage tanks and piping | [44 empty] | ——
2 | Components | Mass flow meter (quick-connect, BPE) | See attachment | 316L | —— | unit | See attachment | Existing installed equipment | Acceptable | —— | Acceptable |  |  |  | 11 | Equipment preparation | Cleaning
3 |  | Pneumatic diaphragm control valve (quick-connect, BPE) | See attachment | 316L | —— | unit | See attachment | Existing installed equipment | Acceptable | —— | Acceptable
4 |  | Pneumatic diaphragm on/off valve (quick-connect, BPE) | See attachment | 316L | —— | unit | See attachment | Existing installed equipment | Acceptable | —— | Acceptable
5 |  | Manual diaphragm valve | See attachment | 316L | —— | unit | See attachment | Existing installed equipment | Acceptable | —— | Acceptable
6 |  | BPE piping and fittings | See attachment | 316L | —— | unit | See attachment | Existing installed equipment | Assess whether the methanol, acetonitrile / water and sodium hydroxide solution lines have to be changed to BPE piping. | BPE fittings 28 days; BPE valves 42 days | All have been issued for purchase; a supplementary order for the T-valves is being placed today.
| *** | Pneumatic diaphragm pump | Rated flow 5 m³/h, head 25 m, clamp connection | SS316L |  | unit | 1 |  |  |  | Acceptable
| TJ4S-1211-TFF02-WTK01-MP01 | Centrifugal pump | Rated flow 3.2 m³/h, head 20 m | 304 | Ultrafiltration waste liquid | unit | 1 | Existing installed equipment |  |  | Acceptable
| TJ4S-1211-TFF02-WTK01-MP02 | Centrifugal pump | Rated flow 3.2 m³/h, head 20 m | 304 | Ultrafiltration waste liquid | unit | 1 | Existing installed equipment |  |  | Acceptable
Precipitation reactor area equipment list – internal assessment
No. | Equipment tag | Equipment name | Technical parameters | Equipment material | Process medium | Unit | Quantity | Option | Modification requirement | Procurement lead time | Status as of 09/17 | Installation duration | Qualification duration | Total time
1 | 1211-R01 | Crystallizer | 1. Working volume 2000 L; 2. Reactor design temperature −25 to 200 °C, jacket design temperature −25 to 220 °C; 3. Reactor design pressure −0.1 to 0.4 MPa; jacket operating pressure 0.6 MPa; | Product contact: 304 stainless steel lined with C22 or C276; Jacket: 304 stainless steel; Insulation: perlite powder; Insulation cladding: 304 stainless steel; | Various organic solvents, acids, bases, etc. | unit | 1 | Existing installed equipment | Acceptable | —— | Acceptable | 15 days of installation work after the equipment and materials arrive
3 | 1211-AT01 | Agitated vessel | 1. Working volume 600 L; 2. Vessel design temperature −25 to 200 °C, jacket design temperature −25 to 220 °C; 3. Vessel design pressure −0.1 to 0.1 MPa; jacket operating pressure 0.6 MPa; | Product contact: 316L stainless steel; Jacket: 304 stainless steel; Insulation: perlite powder; Insulation cladding: 304 stainless steel; | Various organic solvents, salt solutions, etc. | unit | 1 | Existing installed equipment | The piping has to meet the BPE standard and is modified to the Category 4 piping requirements. Piping and drainability do not meet 2D | BPE fittings 28 days; BPE valves 42 days | All have been issued for purchase; a supplementary order for the T-valves is being placed today. |  | Option 1: 3 d Option 2: 7 d | Option 1: 21 d Option 2: 25 d
4 | 1211-AT02 | Agitated vessel | 1. Working volume 80 L; 2. Vessel design temperature −25 to 200 °C, jacket design temperature −25 to 220 °C; 3. Vessel design pressure −0.1 to 0.1 MPa; jacket operating pressure 0.6 MPa; | Product contact: 316L stainless steel; Jacket: 304 stainless steel; Insulation: perlite powder; Insulation cladding: 304 stainless steel; | Various organic solvents, acids, bases, etc. | unit | 1 | Existing installed equipment | There is a flange at the bottom outlet that has to be modified. It is confirmed that the caustic dosing line has to be changed to BPE piping. | Option 1: modify a Yingde stock tank, 40 days (provided the salt preparation vessel is not replaced) Option 2: the existing unit is Hastelloy, so the modification material takes 60 days; a pressure-vessel modification is involved | Option 1: modify the 150 L vessel; the Tofflon tank was dropped after the procurement discussions. Option 2: Yaguang will send fitters for the on-site modification.
| TJ4S-1211-AT02-P02 | Pneumatic diaphragm pump | Rated flow 5 m³/h, head 25 m, clamp connection | SS316L |  | unit | 1 |  |  |  | Acceptable
15 | TJ4S-1211-AT01-P01 | Sanitary four-head diaphragm pump | Rated flow 200 L/h, BPE connection, clamp connection | 316L | Concentrated salt solution | unit | 1 | New purchase required | Purchase replacement four-head diaphragm pumps |  | Purchased, expected end of September
16 | TJ4S-1211-AT02-P01 | Sanitary four-head diaphragm pump | Rated flow 20 L/h, BPE connection, clamp connection | 316L | Concentrated salt solution | unit | 1 | New purchase required |  |  | Purchased, expected end of September
5 | 1211-Fd01 | Filter-dryer | 1. Equipment size DN1200; 2. Vessel design temperature −25 to 200 °C, jacket design temperature −25 to 220 °C; 3. Vessel design pressure −0.1 to 0.1 MPa; jacket operating pressure 0.6 MPa; | Product contact: 304 stainless steel lined with C22 or C276; Jacket: 304 stainless steel; Insulation: perlite powder; Insulation cladding: 304 stainless steel; | Various organic solvents, acids, bases, etc. | unit | 1 | Existing installed equipment | Acceptable | —— | Acceptable
7 | *** | Rotary sifter | Throughput 200 kg/h. | SS316L | Solids | unit | 1 | Purchase new and install | Still being sourced on the market; | —— | Production is still sourcing it on the market; |  | 15d | 33d
8 | Components | Mass flow meter (quick-connect, BPE) | See attachment | 316L | —— | unit | See attachment | Newly purchased | Acceptable | —— | Acceptable |  | - | -
9 |  | Pneumatic diaphragm control valve (quick-connect, BPE) | See attachment | 316L | —— | unit | See attachment | Newly purchased | Acceptable | —— | Acceptable
10 |  | Pneumatic diaphragm on/off valve (quick-connect, BPE) | See attachment | 316L | —— | unit | See attachment | Newly purchased | Acceptable | —— | Acceptable
11 |  | Manual diaphragm valve | See attachment | 316L | —— | unit | See attachment | Newly purchased | Acceptable | —— | Acceptable
12 |  | BPE piping and fittings | See attachment | 316L | —— | unit | See attachment | Newly purchased | The spray piping of the filter-dryer does not meet BPE; the piping of the 600 L vessel does not comply; the piping has to meet the BPE standard and is modified to the Category 4 piping requirements. Piping and drainability do not meet 2D | BPE fittings 28 days; BPE valves 42 days | All have been issued for purchase; a supplementary order for the T-valves is being placed today. |  | 3d | 21d
| TJ4S-1211-FD01-Tr01-P01 | Pneumatic diaphragm pump | Rated flow 5 m³/h, head 30 m, clamp connection | Corrosion-resistant |  | unit | 1 |  |  |  | Acceptable
| TJ4S-1211-FD01-Tr01-P02 | Pneumatic diaphragm pump | Rated flow 5 m³/h, head 30 m, clamp connection | Corrosion-resistant |  | unit | 1 |  |  |  | Acceptable
| TJ4S-1212-FD06-Tr01-P01 | Pneumatic diaphragm pump | Rated flow 5 m³/h, head 30 m, clamp connection | Corrosion-resistant |  | unit | 1 |  |  |  | Acceptable
| *** | Sanitary centrifugal pump | Rated flow 2 m³/h, head 20 m, clamp connection, fixed speed | SS316L |  | unit | 2 |  | Water-for-injection pump |  | Already purchased.

## 5. Option 2 - New Batch System (hidden)
Peptide Building 2, new batch solution preparation system – equipment purchasing list – installed according to the P&ID
Preparation / solution system equipment list
No. | Equipment tag | Equipment name | Technical parameters | Equipment material | Process medium | Unit | Quantity | Equipment source | Status as of 09/17/2026 | Procurement lead time | Installation duration | Qualification duration | Total time including 3 days of cleaning | Technical requirements
1 | *** | Salt solution agitated vessel (jacketed) | 1. Working volume 3000 L; 2. Vessel design temperature −20 to 150 °C, jacket design temperature −25 to 180 °C; 3. Vessel design pressure −0.1 to 0.1 MPa; jacket operating pressure 0.6 MPa; | Product contact: 304 stainless steel lined with C22 or C276; Jacket: 304 stainless steel; Insulation: perlite powder; Insulation cladding: 304 stainless steel; | Various organic solvents, acids, bases, etc. | unit | 0 | Assumes the BPE-compliant 3000 L Hastelloy reactor released by the Peptide Building 3 retrofit | Arrives end of October; the impact of adding a pH port on the lead time is being confirmed; the vendor is fitting the valves at the same time | End of October | 30 | 1. Engineering loop check 3 d; commissioning and qualification 15 d in total (software commissioning 4 d + pump commissioning 3 d + qualification 8 d: OQ 4 d, software EOQ 2 d, PQ 2 d) 2. The environment of the preparation area is affected (wall penetration welding is involved), so the corresponding microbial monitoring has to be repeated in parallel with the solution system; this does not affect the overall release date 3. The HVAC of the CNC area has to be re-qualified (OQ); this does not affect the overall release date | 51d | 1. The equipment shall comply with ASME BPE, including but not limited to: (1) NA-type connections meeting the 2D drainability requirement; connection sizes and quantities as per the approved drawings; (2) Spray port with spray ball, giving full coverage and passing the riboflavin coverage test; (3) Diaphragm valve welded to the outlet, meeting the 2D requirement; (4) External surface roughness < 0.8 µm, internal surface roughness < 0.4 µm; (5) Raw materials, components, manufacturing and acceptance strictly in line with ASME BPE, with the supporting documentation provided; 2. Motor and gearbox: (1) Well-known domestic brand; fully stainless-steel clad to sanitary standard; (2) Explosion protection Ex d IIB T4 Gb, ingress protection not lower than IP55; motor efficiency class 2 or better; 3. Double-end sanitary dry-running mechanical seal from a well-known domestic brand; 4. Agitator material identical to the vessel; agitator design as per the approved drawings; 5. Insulation thickness to suit the temperature requirement; cladding in 3 mm stainless steel with an external surface roughness < 0.8 µm, | Batch solution preparation system – use the 3000 L Hastelloy reactor from Peptide Building 3 and YD storage tanks (316L). Open points: the TC connections on the existing site reactor were made in-house, so the customer's opinion is needed; it must be assessed whether 316L is acceptable for the concentrated-salt piping. | [61 empty] | Batch solution preparation system – use the 3000 L Hastelloy reactor from Peptide Building 3 and YD storage tanks (316L). Open point: the TC connections on the existing site reactor were made in-house, so the customer's opinion is needed.
2 | *** | Salt solution agitated vessel (jacketed) | 1. Working volume 3000 L; 2. Vessel design temperature −20 to 150 °C, jacket design temperature −25 to 180 °C; 3. Vessel design pressure −0.1 to 0.1 MPa; jacket operating pressure 0.6 MPa; | Product contact: 316L stainless steel; Jacket: 304 stainless steel; Insulation: perlite powder; Insulation cladding: 304 stainless steel; | Various organic solvents, acids, bases, etc. | unit | 1 | Reuse 5000 L storage tank (1) – 6-week modification (add agitator, explosion-proof motor, bottom outlet valve) | 30 + 20 day lead time; manufacturing has started | 42 |  |  |  |  | No. | Activity | Equipment / material | Lead time / duration | Expected delivery date | October | [21 empty] | November | [29 empty] | December |  |  |  | Remarks | No. | Activity | Equipment / material | Lead time / duration | Expected delivery date | October | [21 empty] | November | [29 empty] | December | [18 empty] | 2027-01-01 | [7 empty] | Remarks
3 | *** | Mobile phase A agitated vessel (jacketed) | 1. Working volume 3000 L; 2. Vessel design temperature −20 to 150 °C, jacket design temperature −25 to 180 °C; 3. Vessel design pressure −0.1 to 0.1 MPa; jacket operating pressure 0.6 MPa; | Product contact: 316L stainless steel; Jacket: 304 stainless steel; Insulation: perlite powder; Insulation cladding: 304 stainless steel; | Various organic solvents, acids, bases, etc. | unit | 1 | Reuse 5000 L storage tank (2) – 6-week modification (add agitator, explosion-proof motor, bottom outlet valve) | 30 + 20 day lead time; manufacturing has started | 42 | [9 empty] | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 1 | 2 | 3 | 4 | [6 empty] | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 5 | 10 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8
4 | *** | Mobile phase B agitated vessel (jacketed) | 1. Working volume 3000 L; 2. Vessel design temperature −20 to 150 °C, jacket design temperature −25 to 180 °C; 3. Vessel design pressure −0.1 to 0.1 MPa; jacket operating pressure 0.6 MPa; | Product contact: 316L stainless steel; Jacket: 304 stainless steel; Insulation: perlite powder; Insulation cladding: 304 stainless steel; | Various organic solvents, acids, bases, etc. | unit | 1 | Reuse 5000 L storage tank (3) – 6-week modification (add agitator, explosion-proof motor, bottom outlet valve) | 30 + 20 day lead time; manufacturing has started | 42 |  |  |  |  | 1 | Equipment procurement | Delivery of the 3000 L Hastelloy reactor (from Peptide Building 3) | 50 | 31 Oct | [56 empty] | Ordered | 1 | Equipment procurement | Delivery of the 3000 L Hastelloy reactor (from Peptide Building 3) | 50 | 31 Oct | [79 empty] | Ordered | bar: October 10 to October 31
5 | *** | Acetonitrile storage tank (non-jacketed) | Working volume 1000 L, operating temperature −20 to 100 °C, operating pressure −0.098 to 0.099 MPa | SS316L | Fresh acetonitrile | unit | 1 | Reuse 1500 L storage tank (4) – 6-week modification (add agitator, explosion-proof motor, bottom outlet valve) | 30 + 20 day lead time; manufacturing has started | 42 |  |  |  | The equipment shall comply with ASME BPE, including but not limited to: (1) NA-type connections meeting the 2D drainability requirement; connection sizes and quantities as per the approved drawings; (2) Spray port with spray ball, giving full coverage and passing the riboflavin coverage test; (3) Diaphragm valve welded to the outlet, meeting the 2D requirement; (4) External surface roughness < 0.8 µm, internal surface roughness < 0.4 µm; (5) Raw materials, components, manufacturing and acceptance strictly in line with ASME BPE, with the supporting documentation provided; | 2 |  | Delivery of the YD storage tanks (316L) | 30 | 15 Oct | [56 empty] | Ordered | 2 |  | Delivery of the YD storage tanks (316L) | 30 | 15 Oct | [79 empty] | Ordered | bar: October 10 to October 15
6 | *** | Methanol storage tank (non-jacketed) | Working volume 1000 L, operating temperature −20 to 100 °C, operating pressure −0.098 to 0.099 MPa | SS316L | Fresh methanol | unit | 0 | —— | —— | 42 |  |  |  |  | 3 |  | Delivery of the centrifugal pumps (316L) | 42 | 25 Oct | [56 empty] | Not ordered yet, estimated delivery date | 3 |  | Delivery of the centrifugal pumps (316L) | 42 | 25 Oct | [79 empty] | Not ordered yet, estimated delivery date | bar: October 10 to October 25
7 | *** | Purified water storage tank (non-jacketed) | Working volume 1000 L, operating temperature −20 to 100 °C, operating pressure −0.098 to 0.099 MPa | SS316L | Purified water | unit | 1 | Reuse 1500 L storage tank (5) – 6-week modification (add agitator, explosion-proof motor, bottom outlet valve) | 30 + 20 day lead time; manufacturing has started | 42 |  |  |  |  | 4 |  | Procurement of control valves / instruments (316L) | 42 | 25 Oct | [56 empty] | Partly ordered, partly not ordered; estimated delivery date | 4 |  | Delivery of the centrifugal pumps (Hastelloy) | 90 | 15 Dec | [79 empty] | Not ordered yet, estimated delivery date | bar: October 10 to December 15
8 | 1211-HPPC03-AT07-P01 | Sanitary four-head diaphragm pump | Rated flow 10.0 L/min, BPE connection, clamp connection | C276 | Concentrated salt solution | unit | 1 | Newly purchased | The 316L units are ordered and are expected end of September; the request was raised by Production (Guo Zepeng). The Hastelloy units have a 3-month lead time and are expected in December; the order is placed. | 45 |  |  |  | The equipment shall comply with ASME BPE, including but not limited to: (1) NA-type connections meeting the 2D drainability requirement, with a fully drainable equipment body; (2) External surface roughness < 0.8 µm, internal surface roughness < 0.4 µm; (3) Raw materials, components, manufacturing and acceptance strictly in line with ASME BPE, with the supporting documentation provided; | 5 |  | Procurement of BPE fittings (316L) | 30 | 15 Oct | [56 empty] | Ordered | 5 |  | Procurement of control valves / instruments (316L) | 42 | 25 Oct | [79 empty] | Partly ordered, partly not ordered; estimated delivery date | bar: October 10 to October 25
9 | 1211-HPPC03-AT08-P01 | Sanitary centrifugal pump | Rated flow 12.5 m³/h, head 25 m, clamp connection; variable speed | SS316L | Mobile phase A | unit | 1 | Newly purchased | Drawings are being confirmed; the contract will be chased today and tomorrow; delivery is expected in the second half of October. | 35 |  |  |  |  | 6 |  | Supply of the DCS system | 45 | 31 Oct | [56 empty] | Not ordered yet, estimated delivery date | 6 |  | Procurement of BPE fittings (316L) | 30 | 15 Oct | [79 empty] | Ordered | bar: October 10 to October 15
| 1211-HPPC03-AT08-P02 | Sanitary centrifugal pump | Rated flow 3.2 m³/h, head 25 m, clamp connection; fixed speed | SS316L | Mobile phase A | unit | 1 |  |  | 35 |  |  |  |  | 7 |  | BPE fittings (Hastelloy) | 60 | 10 Nov | [56 empty] | Ordered; the Hastelloy items have a long lead time | 7 |  | Supply of the DCS system | 45 | 31 Oct | [79 empty] | Not ordered yet, estimated delivery date | bar: October 10 to October 31
10 | 1211-HPPC03-AT09-P01 | Sanitary centrifugal pump | Rated flow 12.5 m³/h, head 25 m, clamp connection; variable speed | SS316L | Mobile phase B | unit | 1 | Newly purchased |  | 35 |  |  |  |  | 8 | On-site modification | Erection of the main steel platform frame | 5 | [57 empty] | Carry out the work before the equipment arrives | 8 | On-site modification | BPE fittings (Hastelloy) | 60 | 10 Nov | [79 empty] | Ordered; the Hastelloy items have a long lead time | bar: October 10 to November 10
11 | 1211-HPPC03-AT11-P01 | Sanitary centrifugal pump | Rated flow 12.5 m³/h, head 25 m, clamp connection; variable speed | SS316L | Purified water | unit | 1 | Newly purchased |  | 35 |  |  |  |  | 9 |  | Removal of sandwich panels and the external wall | 2 | [58 empty] | 9 |  | Erection of the main steel platform frame | 5 | [80 empty] | Carry out the work before the equipment arrives | bar: October 10 to October 14
12 | 1211-HPPC03-AT10-P01 | Sanitary centrifugal pump | Rated flow 3.2 m³/h, head 25 m, clamp connection; fixed speed | SS316L | Acetonitrile | unit | 1 | Newly purchased |  | 35 |  |  |  |  | 11 |  | Steel platform erection and decking | 5 | [57 empty] | —— | 11 |  | Lifting the storage tanks into place, lifting the Hastelloy reactor | 2+1 | [80 empty] | Waiting for delivery of the Hastelloy reactor | bar: October 16 to October 17; November 1
14 | 1211-HPPC03-AT07-P02 | Sanitary pneumatic diaphragm pump | Rated flow 5 m³/h, head 25 m, clamp connection | SS316L | Waste liquid | unit | 1 | Newly purchased | Reuse stock available in the workshop; completed | 0 |  |  |  |  | 12 |  | Reinstatement of the external wall and the sandwich panels | 2 | [57 empty] | —— | 12 |  | Steel platform erection and decking | 5 | [80 empty] | —— | bar: October 18 to October 22; November 2 to November 3
21 | Components | Mass flow meter (quick-connect, BPE) | See attachment | 316L | —— | unit | See attachment | Newly purchased | Ordered; delivery date to be confirmed. | 30 |  |  |  | BPE requirements | 13 |  | Piping installation | 15 | [57 empty] | —— | 13 |  | Reinstatement of the external wall and the sandwich panels | 2 | [80 empty] | —— | bar: November 2 to November 3
22 |  | Pneumatic diaphragm control valve (quick-connect, BPE) | See attachment | 316L | —— | unit | See attachment | Newly purchased | The request has been submitted; delivery date to be confirmed. | 42 |  |  |  |  | 14 |  | Electrical and instrumentation installation | 10 | [57 empty] | —— | 14 |  | Piping installation | 15 | [80 empty] | The Hastelloy pumps are replaced last | bar: October 22 to November 5; December 16
23 |  | Pneumatic diaphragm on/off valve (quick-connect, BPE) | See attachment | 316L | —— | unit | See attachment | Newly purchased | The request has been submitted; delivery date to be confirmed. | 42 |  |  |  |  | 15 |  | Floor work and sealant application | 5 | [57 empty] | —— | 15 |  | Electrical and instrumentation installation | 10 | [80 empty] | —— | bar: October 29 to November 7
24 |  | Pneumatic control valve (quick-connect, BPE) | See attachment | 316L | —— | unit | See attachment | Newly purchased | The request has been submitted; delivery date to be confirmed. | 42 |  |  |  |  | 16 |  | Piping of the Hastelloy reactor | 5 | [57 empty] | Waiting for the Hastelloy parts | 16 |  | Floor work and sealant application | 5 | [80 empty] | —— | bar: November 8 to November 10
25 |  | Pneumatic on/off valve (quick-connect, BPE) | See attachment | 316L | —— | unit | See attachment | Newly purchased | The request has been submitted; delivery date to be confirmed. | 42 |  |  |  |  | 17 | Qualification | Commissioning | [58 empty] | IQ runs in parallel with installation; IQ is closed after the loop check and is completed during software commissioning | 17 |  | Piping of the Hastelloy reactor | 5 | [80 empty] | Waiting for the Hastelloy parts | bar: November 11 to November 15
26 |  | Radar level transmitter | See attachment | 316L | —— | unit | See attachment | Newly purchased | The request has been submitted; delivery date to be confirmed. | 20 |  |  |  |  | 18 |  | Loop check | [58 empty] | —— | 18 | Qualification | Commissioning
27 |  | Tuning-fork level switch | See attachment | 316L | —— | unit | See attachment | Newly purchased | The request has been submitted; delivery date to be confirmed. | 20 |  |  |  |  | 19 |  | OQ | [58 empty] | —— | 19 |  | Loop check | bar: November 11 to November 12
28 |  | Temperature instrument | See attachment | 316L | —— | unit | See attachment | Newly purchased | The request has been submitted; delivery date to be confirmed. | 20 |  |  |  |  | 20 |  | PQ | [58 empty] | —— | 20 |  | OQ | bar: November 21 to November 24
29 |  | pH instrument | See attachment | 316L | —— | unit | See attachment | Newly purchased | The request has been submitted; delivery date to be confirmed. | 42 |  |  |  |  | 21 | Equipment preparation | Cleaning | [58 empty] | —— | 21 |  | PQ | bar: November 25 to November 26
30 |  | Pressure instrument | See attachment | 316L | —— | unit | See attachment | Newly purchased | The request has been submitted; delivery date to be confirmed. | 21 | [66 empty] | 22 | Equipment preparation | Cleaning | bar: November 27 to November 28
31 |  | Manual diaphragm valve | See attachment | 316L | —— | unit | See attachment | Newly purchased | The request has been submitted; delivery date to be confirmed. | 45 | [66 empty] | 23 | Supplementary qualification | Supplementary IQ (materials, nameplates, P&ID) |  |  | December 17: No additional time needed
32 |  | BPE piping and fittings | See attachment | 316L | —— | unit | See attachment | Newly purchased | The request has been submitted; delivery date to be confirmed. | 35 |  |  |  |  | Retrofit of the fraction receiving area – replace the pumps (316L) and the BPE piping (316L). Open point: the TC connections on the existing site tanks were made in-house, so the customer's opinion is needed. | [61 empty] | 24 |  | Commissioning (pumps, software) | bar: December 17 to December 18
[15 empty] | No. | Activity | Equipment / material | Lead time / duration | Expected delivery date | October | [11 empty] | November | [29 empty] | December | [13 empty] | Remarks | 25 |  | OQ (pressure-hold leak test, pump flow accuracy) | bar: December 19
[20 empty] | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 |  | 26 |  | PQ (solution preparation confirmation)
Preparation system – Grade D area – equipment list – customer requirements | [14 empty] | 1 | Equipment procurement | Delivery of the centrifugal pumps (316L) | 42 | 25 Oct | [56 empty] | Not ordered yet, estimated delivery date | 27 | Equipment preparation | Cleaning | bar: October 20 to October 25
No. | Equipment tag | Equipment name | Technical parameters | Equipment material | Process medium | Unit | Quantity | Option |  | Modification requirement | Procurement lead time | Installation duration | Qualification duration | Total time | 2 |  | Procurement of control valves / instruments (316L) | 42 | 25 Oct | [56 empty] | Partly ordered, partly not ordered; estimated delivery date | bar: October 20 to October 25
1 | 1211-HPPC03-AT03 | Fraction receiving agitated vessel (jacketed) | 1. Working volume 8000 L; 2. Vessel design temperature −20 to 150 °C, jacket design temperature −25 to 180 °C; 3. Vessel design pressure −0.1 to 0.1 MPa; jacket operating pressure 0.6 MPa; | Product contact: 316L stainless steel; Jacket: 304 stainless steel; Insulation: perlite powder; Insulation cladding: 304 stainless steel; | Various organic solvents | unit | 1 | Existing installed equipment | Existing installed equipment | Acceptable | —— | 15 days of installation work after the equipment and materials arrive | 3d | 21d | 3 |  | Procurement of BPE fittings (316L) | 30 | 15 Oct | [56 empty] | Ordered | bar: October 20
2 | 1211-HPPC03-AT04/AT05 | Fraction receiving agitated vessel (jacketed) | 1. Working volume 3000 L; 2. Vessel design temperature −20 to 150 °C, jacket design temperature −25 to 180 °C; 3. Vessel design pressure −0.1 to 0.1 MPa; jacket operating pressure 0.6 MPa; | Product contact: 316L stainless steel; Jacket: 304 stainless steel; Insulation: perlite powder; Insulation cladding: 304 stainless steel; | Various organic solvents | unit | 2 | Existing installed equipment | Existing installed equipment | Acceptable | —— |  |  |  | 4 |  | BPE manual valves (316L) | 30 | 15 Oct | [56 empty] | Ordered | bar: October 20
3 | 1211-HPPC03-AT06 | Sample agitated vessel (jacketed) | 1. Working volume 1000 L; 2. Vessel design temperature −20 to 150 °C, jacket design temperature −25 to 180 °C; 3. Vessel design pressure −0.1 to 0.1 MPa; jacket operating pressure 0.6 MPa; | Product contact: 316L stainless steel; Jacket: 304 stainless steel; Insulation: perlite powder; Insulation cladding: 304 stainless steel; | Various organic solvents | unit | 1 | Existing installed equipment | Existing installed equipment | Acceptable | —— |  |  |  | 5 | On-site modification | Removal of the existing pumps and piping | 1 | [57 empty] | —— | bar: October 20
4 | 1211-HPPC03-T06 | Top-fraction sample agitated vessel (jacketed) | 1. Working volume 1000 L; 2. Vessel design temperature −20 to 150 °C, jacket design temperature −25 to 180 °C; 3. Vessel design pressure −0.1 to 0.1 MPa; jacket operating pressure 0.6 MPa; | Product contact: 316L stainless steel; Jacket: 304 stainless steel; Insulation: perlite powder; Insulation cladding: 304 stainless steel; | Various organic solvents | unit | 1 | Existing installed equipment | Existing installed equipment | Acceptable | —— |  |  |  | 6 |  | Replacement with new pumps and BPE piping | 15 | [57 empty] | —— | bar: October 21 to November 4
5 | *** | Fraction receiving storage tank (non-jacketed) | Working volume 100 L, operating temperature −20 to 100 °C, operating pressure −0.098 to 0.099 MPa | SS316L | Various organic solvents | unit | 12 | Existing installed equipment | Existing installed equipment | Acceptable | —— |  |  |  | 1 |  | Procurement of control valves / instruments (316L) | 42 | 25 Oct | December 1: Partly ordered, partly not ordered; estimated delivery date
| 1211-HPPC03-AT03-P01 | Sanitary centrifugal pump | Rated flow 12.5 m³/h, head 25 m, clamp connection, variable speed | SS316L | Various organic solvents | unit | 1 | New purchase required | Drawings are being confirmed; the contract will be chased today and tomorrow; delivery is expected in the second half of October. | 35 |  |  |  |  | 2 |  | Procurement of BPE fittings (316L) | 30 | 15 Oct | December 1: Ordered
| 1211-HPPC03-AT03-P02 | Sanitary centrifugal pump | Rated flow 2 m³/h, head 20 m, clamp connection, fixed speed | SS316L | Various organic solvents | unit | 1 | New purchase required | Drawings are being confirmed; the contract will be chased today and tomorrow; delivery is expected in the second half of October. | 35 |  |  |  |  | 3 |  | BPE manual valves (316L) | 30 | 15 Oct | December 1: Ordered
| 1211-HPPC03-AT04-P01 | Sanitary centrifugal pump | Rated flow 12.5 m³/h, head 25 m, clamp connection, variable speed | SS316L | Various organic solvents | unit | 1 | New purchase required | Drawings are being confirmed; the contract will be chased today and tomorrow; delivery is expected in the second half of October. | 35 |  |  |  |  | 4 |  | Replacement of BPE piping | 5 | bar: October 23 to October 27; December 1
| 1211-HPPC03-AT05-P01 | Sanitary centrifugal pump | Rated flow 12.5 m³/h, head 25 m, clamp connection, variable speed | SS316L | Various organic solvents | unit | 1 | New purchase required | Drawings are being confirmed; the contract will be chased today and tomorrow; delivery is expected in the second half of October. | 35 |  |  |  |  | 5 |  | Electrical and instrumentation installation | 3 | bar: October 25 to October 27; December 1
| 1211-HPPC03-AT06-P01 | Sanitary centrifugal pump | Rated flow 12.5 m³/h, head 25 m, clamp connection, variable speed | SS316L | Various organic solvents | unit | 1 | New purchase required | Drawings are being confirmed; the contract will be chased today and tomorrow; delivery is expected in the second half of October. | 35 |  |  |  |  | 6 |  | HVAC |  |  | October 28: Hot work is involved, so one at-rest and one in-operation monitoring run with 5-day incubation is required; December 1: IQ runs in parallel with installation
| 1211-HPPC03-T06-P01 | Sanitary centrifugal pump | Rated flow 3.2 m³/h, head 25 m, clamp connection, fixed speed | SS316L | Various organic solvents | unit | 1 | New purchase required | Drawings are being confirmed; the contract will be chased today and tomorrow; delivery is expected in the second half of October. | 35 |  |  |  |  | 7 |  | Storage tanks and piping | bar: October 29 to November 2; December 1
6 | *** | Pneumatic diaphragm pump | 5 m³/h, 25 m, quick-connect | SS316L | Various organic solvents | unit | 2 | Existing installed equipment | Existing installed equipment | Charging and discharging of the homogenisation vessel | 35 days |  |  |  | 8 |  | Cleaning | bar: November 3 to November 4
| *** | Sanitary centrifugal pump | Rated flow 2 m³/h, head 20 m, clamp connection, fixed speed | SS316L | In-spec fractions | unit | 1 |  | Drawings are being confirmed; the contract will be chased today and tomorrow; delivery is expected in the second half of October. | 35
| *** | Pneumatic diaphragm pump | Rated flow 5 m³/h, head 25 m, clamp connection | SS316L | Out-of-spec fractions | unit | 1 | [7 empty] | No. | Activity | Equipment / material | Lead time / duration | Expected delivery date | October 20: October; November 1: November; December 1: December | Remarks
7 | Components | Mass flow meter (quick-connect, BPE) | See attachment | 316L | —— | unit | See attachment | Existing installed equipment | The request has been submitted; delivery date to be confirmed. | Acceptable | —— | [8 empty] | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
8 |  | Pneumatic diaphragm control valve (quick-connect, BPE) | See attachment | 316L | —— | unit | See attachment | Existing installed equipment | The request has been submitted; delivery date to be confirmed. | Purchase quick-connect control valves | 42 days |  |  |  | 1 | Equipment procurement | Procurement of control valves / instruments (316L) | 42 | 25 Oct | [56 empty] | Partly ordered, partly not ordered; estimated delivery date | bar: October 20 to October 25
9 |  | Pneumatic diaphragm on/off valve (quick-connect, BPE) | See attachment | 316L | —— | unit | See attachment | Existing installed equipment | The request has been submitted; delivery date to be confirmed. | Purchase quick-connect on/off valves | 42 days |  |  |  | 2 |  | Procurement of BPE fittings (316L) | 30 | 15 Oct | [56 empty] | Ordered | bar: October 20
10 |  | Pneumatic control valve (quick-connect, BPE) | See attachment | 316L | —— | unit | See attachment | Existing installed equipment | The request has been submitted; delivery date to be confirmed. | Purchase quick-connect control valves | 35 days |  |  |  | 3 |  | BPE manual valves (316L) | 30 | 15 Oct | [56 empty] | Ordered | bar: October 20
11 |  | Pneumatic on/off valve (quick-connect, BPE) | See attachment | 316L | —— | unit | See attachment | Existing installed equipment | The request has been submitted; delivery date to be confirmed. | Purchase quick-connect on/off valves | 35 days |  |  |  | 4 | On-site modification | Replacement of BPE piping | 5 | [57 empty] | —— | bar: October 23 to October 27
12 |  | Radar level transmitter | See attachment | 316L | —— | unit | See attachment | Existing installed equipment | The request has been submitted; delivery date to be confirmed. |  | —— |  |  |  | 5 |  | Electrical and instrumentation installation | 3 | [57 empty] | —— | bar: October 25 to October 27
13 |  | Tuning-fork level switch | See attachment | 316L | —— | unit | See attachment | Existing installed equipment | The request has been submitted; delivery date to be confirmed. |  | —— |  |  |  | 6 | Qualification | HVAC |  |  | October 28: Hot work is involved, so one at-rest and one in-operation monitoring run with 5-day incubation is required | IQ runs in parallel with installation
14 |  | Temperature instrument | See attachment | 316L | —— | unit | See attachment | Existing installed equipment | The request has been submitted; delivery date to be confirmed. |  | —— | Installation duration | Qualification duration | Total time | 7 |  | Supplementary qualification | [58 empty] | —— | bar: October 29 to November 2
15 |  | pH instrument | See attachment | 316L | —— | unit | See attachment | Existing installed equipment | The request has been submitted; delivery date to be confirmed. |  | —— | Around 5 days of installation work after the fittings arrive | 3d | 11d | 8 | Equipment preparation | Cleaning | bar: November 3 to November 4
16 |  | Pressure instrument | See attachment | 316L | —— | unit | See attachment | Existing installed equipment | The request has been submitted; delivery date to be confirmed. |  | ——
17 |  | Manual diaphragm valve | See attachment | 316L | —— | unit | See attachment | Existing installed equipment | The request has been submitted; delivery date to be confirmed. |  | ——
18 |  | BPE piping and fittings | See attachment | 316L | —— | unit | See attachment | Existing installed equipment | The request has been submitted; delivery date to be confirmed. | The piping is replaced entirely to BPE standard, meeting the 2D and drainability requirements for Category 4 piping | BPE fittings 28 days; BPE valves 42 days
Ultrafiltration system equipment list – internal assessment | [14 empty] | Retrofit of the precipitation area – replace the 80 L storage tank (316L) and the BPE piping (316L). Open point: the TC connections on the existing site equipment (reactor, filter-dryer, storage tanks) were made in-house, so the customer's opinion is needed.
No. | Equipment tag | Equipment name | Technical parameters | Equipment material | Process medium | Unit | Quantity | Option | Status as of 09/17/2026 | Modification requirement | Procurement lead time |  |  |  | No. | Activity | Equipment / material | Lead time / duration | Expected delivery date | October 20: October; November 1: November; December 1: December | Remarks
1 | 1211-TFF01-T01 | Ultrafiltration receiving storage tank (jacketed) | 1. Working volume 1000 L; 2. Vessel design temperature −20 to 150 °C, jacket design temperature −25 to 180 °C; 3. Vessel design pressure −0.1 to 0.1 MPa; jacket operating pressure 0.6 MPa; | SS316L | Various organic solvents | unit | 1 | Existing installed equipment | Acceptable | Acceptable | —— | [8 empty] | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
2 | Components | Mass flow meter (quick-connect, BPE) | See attachment | 316L | —— | unit | See attachment | Existing installed equipment | Acceptable | Acceptable | —— | Installation duration | Qualification duration | Total time | 1 | Equipment procurement | Delivery of the YD storage tanks (316L) | 40 | 20 Oct | [56 empty] | Ordered | bar: October 20
3 |  | Pneumatic diaphragm control valve (quick-connect, BPE) | See attachment | 316L | —— | unit | See attachment | Existing installed equipment | Acceptable | Acceptable | —— | 15 days of installation work after the equipment and materials arrive |  |  | 2 |  | Delivery of the centrifugal pumps (316L) | 42 | 25 Oct | [56 empty] | Not ordered yet, estimated delivery date | bar: October 20 to October 25
4 |  | Pneumatic diaphragm on/off valve (quick-connect, BPE) | See attachment | 316L | —— | unit | See attachment | Existing installed equipment | Acceptable | Acceptable | —— |  | Option 1: 3 d Option 2: 7 d | Option 1: 21 d Option 2: 25 d | 3 |  | Procurement of control valves / instruments (316L) | 42 | 25 Oct | [56 empty] | Partly ordered, partly not ordered; estimated delivery date | bar: October 20 to October 25
5 |  | Manual diaphragm valve | See attachment | 316L | —— | unit | See attachment | Existing installed equipment | Acceptable | Acceptable | —— |  |  |  | 4 |  | Procurement of BPE fittings (316L) | 30 | 15 Oct | [56 empty] | Ordered | bar: October 20
6 |  | BPE piping and fittings | See attachment | 316L | —— | unit | See attachment | Existing installed equipment | The request has been submitted; delivery date to be confirmed. | Assess whether the methanol, acetonitrile / water and sodium hydroxide solution lines have to be changed to BPE piping. | BPE fittings 28 days; BPE valves 42 days |  |  |  | 5 |  | BPE manual valves (316L) | 30 | 15 Oct | [56 empty] | Ordered | bar: October 20
| *** | Pneumatic diaphragm pump | Rated flow 5 m³/h, head 25 m, clamp connection | SS316L |  | unit | 1 |  | Acceptable | [5 empty] | 6 |  | Removal / installation of the 80 L vessel, installation of the wet nitrogen supply | 1 | [57 empty] | Waiting for delivery of the storage tanks | bar: October 21
| TJ4S-1211-TFF02-WTK01-MP01 | Centrifugal pump | Rated flow 3.2 m³/h, head 20 m | 304 |  | unit | 1 | Existing installed equipment | Acceptable |  |  |  | 15d | 33d | 7 |  | Replacement of pumps and BPE piping | 15 | [57 empty] | —— | bar: October 21 to November 4
| TJ4S-1211-TFF02-WTK01-MP02 | Centrifugal pump | Rated flow 3.2 m³/h, head 20 m | 304 |  | unit | 1 | Existing installed equipment | Acceptable |  |  |  | - | - | 8 |  | Electrical and instrumentation installation | 7 | [57 empty] | —— | bar: October 29 to November 4
Precipitation reactor area equipment list – internal assessment | [14 empty] | 9 | Qualification | HVAC |  |  | November 5: Hot work is involved, so one at-rest and one in-operation monitoring run with 5-day incubation is required | IQ runs in parallel with installation
No. | Equipment tag | Equipment name | Technical parameters | Equipment material | Process medium | Unit | Quantity | Option |  | Modification requirement | Procurement lead time |  |  |  | 10 |  | Supplementary qualification | [58 empty] | —— | bar: November 6 to November 10
1 | 1211-R01 | Crystallizer | 1. Working volume 2000 L; 2. Reactor design temperature −25 to 200 °C, jacket design temperature −25 to 220 °C; 3. Reactor design pressure −0.1 to 0.4 MPa; jacket operating pressure 0.6 MPa; | Product contact: 304 stainless steel lined with C22 or C276; Jacket: 304 stainless steel; Insulation: perlite powder; Insulation cladding: 304 stainless steel; | Various organic solvents, acids, bases, etc. | unit | 1 | Existing installed equipment | Existing installed equipment | Acceptable | —— |  |  |  | 11 | Equipment preparation | Cleaning | bar: November 11 to November 12
3 | 1211-AT01 | Agitated vessel | 1. Working volume 600 L; 2. Vessel design temperature −25 to 200 °C, jacket design temperature −25 to 220 °C; 3. Vessel design pressure −0.1 to 0.1 MPa; jacket operating pressure 0.6 MPa; | Product contact: 316L stainless steel; Jacket: 304 stainless steel; Insulation: perlite powder; Insulation cladding: 304 stainless steel; | Various organic solvents, salt solutions, etc. | unit | 1 | Existing installed equipment | Existing installed equipment | The piping has to meet the BPE standard and is modified to the Category 4 piping requirements. Piping and drainability do not meet 2D | BPE fittings 28 days; BPE valves 42 days |  | 3d | 21d
4 | 1211-AT02 | Agitated vessel | 1. Working volume 80 L; 2. Vessel design temperature −25 to 200 °C, jacket design temperature −25 to 220 °C; 3. Vessel design pressure −0.1 to 0.1 MPa; jacket operating pressure 0.6 MPa; | Product contact: 316L stainless steel; Jacket: 304 stainless steel; Insulation: perlite powder; Insulation cladding: 304 stainless steel; | Various organic solvents, acids, bases, etc. | unit | 1 | Existing installed equipment | Existing installed equipment | There is a flange at the bottom outlet that has to be modified. It is confirmed that the caustic dosing line has to be changed to BPE piping. | Option 1: modify a Yingde stock tank, 40 days (provided the salt preparation vessel is not replaced) Option 2: the existing unit is Hastelloy, so the modification material takes 60 days; a pressure-vessel modification is involved
| TJ4S-1211-AT02-P02 | Pneumatic diaphragm pump | Rated flow 5 m³/h, head 25 m, clamp connection | SS316L |  | unit | 1 |  | Existing installed equipment
15 | TJ4S-1211-AT01-P01 | Sanitary four-head diaphragm pump | Rated flow 200 L/h, BPE connection, clamp connection | 316L |  | unit | 1 | New purchase required | The 316L units are ordered and are expected end of September; the request was raised by Production (Guo Zepeng). The Hastelloy units have a 3-month lead time and are expected in December; the order is placed. | Purchase replacement four-head diaphragm pumps | ——
16 | TJ4S-1211-AT02-P01 | Sanitary four-head diaphragm pump | Rated flow 20 L/h, BPE connection, clamp connection | 316L |  | unit | 1 | New purchase required | The 316L units are ordered and are expected end of September; the request was raised by Production (Guo Zepeng). The Hastelloy units have a 3-month lead time and are expected in December; the order is placed. |  | ——
5 | 1211-Fd01 | Filter-dryer | 1. Equipment size DN1200; 2. Vessel design temperature −25 to 200 °C, jacket design temperature −25 to 220 °C; 3. Vessel design pressure −0.1 to 0.1 MPa; jacket operating pressure 0.6 MPa; | Product contact: 304 stainless steel lined with C22 or C276; Jacket: 304 stainless steel; Insulation: perlite powder; Insulation cladding: 304 stainless steel; | Various organic solvents, acids, bases, etc. | unit | 1 | Existing installed equipment | Completed | Acceptable | ——
7 | *** | Rotary sifter | Throughput 200 kg/h. | SS316L | Solids | unit | 1 | Purchase new and install | Still being sourced on the market; | Still being sourced on the market; | ——
8 | Components | Mass flow meter (quick-connect, BPE) | See attachment | 316L | —— | unit | See attachment | Newly purchased | The request has been submitted; delivery date to be confirmed. | Acceptable | ——
9 |  | Pneumatic diaphragm control valve (quick-connect, BPE) | See attachment | 316L | —— | unit | See attachment | Newly purchased | The request has been submitted; delivery date to be confirmed. | Acceptable | ——
10 |  | Pneumatic diaphragm on/off valve (quick-connect, BPE) | See attachment | 316L | —— | unit | See attachment | Newly purchased | The request has been submitted; delivery date to be confirmed. | Acceptable | BPE fittings 28 days; BPE valves 42 days
11 |  | Manual diaphragm valve | See attachment | 316L | —— | unit | See attachment | Newly purchased | The request has been submitted; delivery date to be confirmed. | Acceptable
12 |  | BPE piping and fittings | See attachment | 316L | —— | unit | See attachment | Newly purchased | The request has been submitted; delivery date to be confirmed. | The spray piping of the filter-dryer does not meet BPE; the piping of the 600 L vessel does not comply; the piping has to meet the BPE standard and is modified to the Category 4 piping requirements. Piping and drainability do not meet 2D
| TJ4S-1211-FD01-Tr01-P01 | Pneumatic diaphragm pump | Rated flow 5 m³/h, head 30 m, clamp connection | Corrosion-resistant |  | unit | 1 |  | Completed
| TJ4S-1211-FD01-Tr01-P02 | Pneumatic diaphragm pump | Rated flow 5 m³/h, head 30 m, clamp connection | Corrosion-resistant |  | unit | 1 |  | Completed
| TJ4S-1212-FD06-Tr01-P01 | Pneumatic diaphragm pump | Rated flow 5 m³/h, head 30 m, clamp connection | Corrosion-resistant |  | unit | 1 |  | Completed
| *** | Sanitary centrifugal pump | Rated flow 2 m³/h, head 20 m, clamp connection, fixed speed | SS316L | Water for injection | unit | 2 | New purchase required | Drawings are being confirmed; the contract will be chased today and tomorrow; delivery is expected in the second half of October. | Water-for-injection pump

## 6. Option 3 - All New (hidden)
Peptide Building 2, replacement of existing equipment – purchasing list – covers replacement of existing equipment and piping only, excluding anything else (such as a new CIP system) | [70 empty] | i
Preparation system – continuous solution preparation – CNC area – equipment list
No. | Equipment tag | Equipment name | Technical parameters | Equipment material | Process medium | Unit | Quantity | Equipment source | Status as of 09/17/2026 | Procurement lead time (days) | Installation duration | Qualification duration | Total time | Technical requirements
1 | 1213-R05 | Hastelloy reactor | 3000 L Hastelloy reactor | C276 | Concentrated salt solution | unit | 1 | Newly purchased | Not purchased yet | 100 | 30 | 19 d (loop check 2 d, software commissioning 5 d + pump commissioning 3 d + qualification 9 d) IQ runs in parallel with installation; IQ is closed after the loop check and is completed during software commissioning |  | 1. The equipment shall comply with ASME BPE, including but not limited to: (1) NA-type connections meeting the 2D drainability requirement; connection sizes and quantities as per the approved drawings; (2) Spray port with spray ball, giving full coverage and passing the riboflavin coverage test; (3) Diaphragm valve welded to the outlet, meeting the 2D requirement; (4) External surface roughness < 0.8 µm, internal surface roughness < 0.4 µm; (5) Raw materials, components, manufacturing and acceptance strictly in line with ASME BPE, with the supporting documentation provided; 2. Motor and gearbox: (1) Well-known domestic brand; fully stainless-steel clad to sanitary standard; (2) Explosion protection Ex d IIB T4 Gb, ingress protection not lower than IP55; motor efficiency class 2 or better; 3. Double-end sanitary dry-running mechanical seal from a well-known domestic brand; 4. Agitator material identical to the vessel; agitator design as per the approved drawings; |  | Retrofit of the continuous solution preparation system – replace all storage tanks and pumps with new units (316L + Hastelloy) and convert to BPE piping (316L + Hastelloy)
2 | 1211-HPPC03-AT01 | Solution preparation agitated vessel (non-jacketed) | Working volume 500 L, operating temperature −20 to 100 °C, operating pressure −0.098 to 0.099 MPa | C22 or C276 | Concentrated salt solution | unit | 1 | Newly purchased | Under price negotiation; supplier not yet confirmed | 100 | [5 empty] | No. | Activity | Equipment / material | Lead time / duration | Expected delivery date | December | [30 empty] | January | [20 empty] | Remarks
3 | 1211-HPPC03-AT02 | Solution preparation agitated vessel (non-jacketed) | Working volume 500 L, operating temperature −20 to 100 °C, operating pressure −0.098 to 0.099 MPa | C22 or C276 | Concentrated salt solution | unit | 1 | Newly purchased | Under price negotiation; supplier not yet confirmed | 100 | [10 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21
4 | 1211-HPPC03-AT01 | Solution preparation agitated vessel (non-jacketed) | Working volume 500 L, operating temperature −20 to 100 °C, operating pressure −0.098 to 0.099 MPa | SS316L | Concentrated salt solution | unit | 1 | Newly purchased | Under price negotiation; supplier not yet confirmed | 90 | [5 empty] | 1 | Equipment procurement | Delivery of the newly purchased Hastelloy agitated vessel | 90 | 15 Dec | [52 empty] | Ordered | bar: December 1 to December 15
5 | 1211-HPPC03-AT02 | Solution preparation agitated vessel (non-jacketed) | Working volume 500 L, operating temperature −20 to 100 °C, operating pressure −0.098 to 0.099 MPa | SS316L | Concentrated salt solution | unit | 1 | Newly purchased | Under price negotiation; supplier not yet confirmed | 90 | [5 empty] | 2 |  | Delivery of the newly purchased storage tanks (316L) | 80 | 05 Dec | [52 empty] | Ordered | bar: December 1 to December 5
6 | 1211-HPPC03-T01 | Purified water storage tank (non-jacketed) | Working volume 1000 L, operating temperature −20 to 100 °C, operating pressure −0.098 to 0.099 MPa | SS316L | Purified water | unit | 1 | Newly purchased | Under price negotiation; supplier not yet confirmed | 80 |  |  |  | The equipment shall comply with ASME BPE, including but not limited to: (1) NA-type connections meeting the 2D drainability requirement; connection sizes and quantities as per the approved drawings; (2) Spray port with spray ball, giving full coverage and passing the riboflavin coverage test; (3) Diaphragm valve welded to the outlet, meeting the 2D requirement; (4) External surface roughness < 0.8 µm, internal surface roughness < 0.4 µm; (5) Raw materials, components, manufacturing and acceptance strictly in line with ASME BPE, with the supporting documentation provided; |  | 3 |  | Delivery of the centrifugal pumps (316L) | 42 | 25 Oct | [52 empty] | Not ordered yet, estimated delivery date
7 | 1211-HPPC03-T02 | Acetonitrile storage tank (non-jacketed) | Working volume 1000 L, operating temperature −20 to 100 °C, operating pressure −0.098 to 0.099 MPa | SS316L | Fresh acetonitrile, spare | unit | 2 | Newly purchased | Under price negotiation; supplier not yet confirmed | 80 | [5 empty] | 4 |  | Delivery of the four-head diaphragm pumps (316L) | 25 | 10 Oct | [52 empty] | Ordered
8 | 1211-HPPC03-T03 | Mobile phase A storage tank (non-jacketed) | Working volume 1000 L, operating temperature −20 to 100 °C, operating pressure −0.098 to 0.099 MPa | SS316L | Mobile phase A | unit | 1 | Newly purchased | Under price negotiation; supplier not yet confirmed | 80 | [5 empty] | 5 |  | Delivery of the four-head diaphragm pumps (Hastelloy) | 90 | 15 Dec | [52 empty] | Ordered | bar: December 1 to December 15
9 | 1211-HPPC03-T04 | Mobile phase B storage tank (non-jacketed) | Working volume 1000 L, operating temperature −20 to 100 °C, operating pressure −0.098 to 0.099 MPa | SS316L | Mobile phase B | unit | 1 | Newly purchased | Under price negotiation; supplier not yet confirmed | 80 | [5 empty] | 6 |  | Procurement of control valves / instruments (316L) | 42 | 25 Oct | [52 empty] | Partly ordered, partly not ordered; estimated delivery date
10 | 1211-HPPC03-T05 | Methanol storage tank (non-jacketed) | Working volume 1000 L, operating temperature −20 to 100 °C, operating pressure −0.098 to 0.099 MPa | SS316L | Methanol | unit | 1 | Newly purchased | Under price negotiation; supplier not yet confirmed | 80 | [5 empty] | 7 |  | Procurement of BPE fittings (316L) | 30 | 15 Oct | [52 empty] | Ordered
10 | 1211-HPPC03-T03-P01 | Sanitary centrifugal pump | Rated flow 2.5 m³/h, head 25 m, clamp connection | SS316L | Mobile phase A | unit | 1 |  | Use the pumps from Option 1 / Option 2 |  |  |  |  | The equipment shall comply with ASME BPE, including but not limited to: (1) NA-type connections meeting the 2D drainability requirement, with a fully drainable equipment body; (2) External surface roughness < 0.8 µm, internal surface roughness < 0.4 µm; (3) Raw materials, components, manufacturing and acceptance strictly in line with ASME BPE, with the supporting documentation provided; |  | 8 |  | BPE fittings (Hastelloy) | 60 | 10 Nov | [52 empty] | Ordered
11 | 1211-HPPC03-T03-P02 | Sanitary centrifugal pump | Rated flow 3.2 m³/h, head 25 m, clamp connection, fixed speed | SS316L | Mobile phase B | unit | 1 |  | Use the pumps from Option 1 / Option 2 | [6 empty] | 9 | On-site modification | Storage tank removal | 3 | [53 empty] | Cut the vessel nozzles in advance | bar: December 3 to December 5
12 | 1211-HPPC03-T04-P01 | Sanitary centrifugal pump | Rated flow 2.5 m³/h, head 25 m, clamp connection | SS316L | Mobile phase B / fresh acetonitrile | unit | 1 |  | Use the pumps from Option 1 / Option 2 | [6 empty] | 10 |  | Storage tank installation | 2 | [53 empty] | Waiting for delivery of the Hastelloy parts | bar: December 6; December 16
13 | 1211-HPPC03-WT01-P01 | Centrifugal pump | Rated flow 3.2 m³/h, head 20 m, clamp connection | 304 | Preparation waste liquid | unit | 1 |  | Use the pumps from Option 1 / Option 2 | [6 empty] | 11 |  | Installation of pumps and BPE piping | 20 | [53 empty] | Waiting for delivery of the storage tanks | bar: December 7 to December 26
14 | 1211-HPPC03-WT02-P01 | Centrifugal pump | Rated flow 3.2 m³/h, head 20 m, clamp connection | 304 | Preparation waste liquid | unit | 1 |  | Use the pumps from Option 1 / Option 2 | [6 empty] | 12 |  | Electrical and instrumentation installation | 10 | [53 empty] | —— | bar: December 18 to December 27
15 | 1211-HPPC03-AT01-P01 | Sanitary four-head diaphragm pump | Rated flow 3.0 L/min, BPE connection, clamp connection | 316L or C276 | Concentrated salt solution | unit | 1 |  | Use the pumps from Option 1 / Option 2 | [6 empty] | 13 |  | Floor work and sealant application | 5 | [53 empty] | —— | bar: December 28 to January 1
16 | 1211-HPPC03-AT02-P01 | Sanitary four-head diaphragm pump | Rated flow 2.0 L/min, BPE connection, clamp connection | 316L or C276 | Concentrated salt solution | unit | 1 |  | Use the pumps from Option 1 / Option 2 | [6 empty] | 14 | Qualification | Commissioning | [54 empty] | IQ runs in parallel with installation; IQ is closed after the loop check and is completed during software commissioning | bar: January 4 to January 8
17 | 1211-HPPC03-T01-P01 | Sanitary four-head diaphragm pump | Rated flow 35 L/min, BPE connection, clamp connection | SS316L | Purified water | unit | 1 |  | Use the pumps from Option 1 / Option 2 | [6 empty] | 15 |  | Loop check | [54 empty] | —— | bar: January 2 to January 3
18 | 1211-HPPC03-T01-P02 | Sanitary four-head diaphragm pump | Rated flow 3.0 L/min, BPE connection, clamp connection | SS316L | Purified water | unit | 1 |  | Use the pumps from Option 1 / Option 2 | [6 empty] | 16 |  | OQ | [54 empty] | —— | bar: January 9 to January 12
19 | 1211-HPPC03-T02-P01 | Sanitary four-head diaphragm pump | Rated flow 5.0 L/min, BPE connection, clamp connection | SS316L | Fresh acetonitrile | unit | 1 |  | Use the pumps from Option 1 / Option 2 | [6 empty] | 17 |  | PQ | [54 empty] | —— | bar: January 13 to January 14
20 | 1211-HPPC03-T02-P02 | Sanitary four-head diaphragm pump | Rated flow 35 L/min, BPE connection, clamp connection | SS316L | Fresh acetonitrile | unit | 1 |  | Use the pumps from Option 1 / Option 2 | [6 empty] | 18 | Equipment preparation | Cleaning | [54 empty] | —— | bar: January 15 to January 16
| TJ4S-1213-R05-P01 | Sanitary four-head diaphragm pump | Rated flow 35 L/min, BPE connection, clamp connection | 316L or C276 | Concentrated salt solution | unit | 1 |  | Use the pumps from Option 1 / Option 2 |  |  |  |  | BPE requirements
22 | Components | Mass flow meter (quick-connect, BPE) | See attachment | 316L | —— | unit | See attachment | Newly purchased | Use the components from Option 1 / Option 2 | 30
23 |  | Pneumatic diaphragm control valve (quick-connect, BPE) | See attachment | 316L | —— | unit | See attachment | Newly purchased | Use the components from Option 1 / Option 2 | 42 | [5 empty] | Retrofit of the fraction receiving vessels – replace all storage tanks and pumps with new units (316L) and convert to BPE piping (316L)
24 |  | Pneumatic diaphragm on/off valve (quick-connect, BPE) | See attachment | 316L | —— | unit | See attachment | Newly purchased | Use the components from Option 1 / Option 2 | 42 | [5 empty] | No. | Activity | Equipment / material | Lead time / duration | Expected delivery date | December 1: December; December 25: January | Remarks
25 |  | Pneumatic control valve (quick-connect, BPE) | See attachment | 316L | —— | unit | See attachment | Newly purchased | Use the components from Option 1 / Option 2 | 42 | [10 empty] | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 27 | 28 | 29 | 30 | 31
26 |  | Pneumatic on/off valve (quick-connect, BPE) | See attachment | 316L | —— | unit | See attachment | Newly purchased | Use the components from Option 1 / Option 2 | 42 | [5 empty] | 1 | Equipment procurement | Delivery of the purchased agitated storage tanks | 90 | 15 Dec | [52 empty] | Not ordered yet, estimated delivery date | bar: December 8 to December 15
27 |  | Radar level transmitter | See attachment | 316L | —— | unit | See attachment | Newly purchased | Use the components from Option 1 / Option 2 | 20 | [5 empty] | 2 |  | Delivery of the centrifugal pumps (316L) | 42 | 25 Oct | [52 empty] | Partly ordered, partly not ordered; estimated delivery date
28 |  | Tuning-fork level switch | See attachment | 316L | —— | unit | See attachment | Newly purchased | Use the components from Option 1 / Option 2 | 20 | [5 empty] | 3 |  | Procurement of control valves / instruments (316L) | 42 | 25 Oct | [52 empty] | Ordered
29 |  | Temperature instrument | See attachment | 316L | —— | unit | See attachment | Newly purchased | Use the components from Option 1 / Option 2 | 20 | [5 empty] | 4 |  | Procurement of BPE fittings (316L) | 30 | 15 Oct | [52 empty] | Ordered
30 |  | pH instrument | See attachment | 316L | —— | unit | See attachment | Newly purchased | Use the components from Option 1 / Option 2 | 42 | [5 empty] | 5 |  | BPE manual valves (316L) | 30 | 15 Oct | [52 empty] | ——
31 |  | Pressure instrument | See attachment | 316L | —— | unit | See attachment | Newly purchased | Use the components from Option 1 / Option 2 | 21 | [5 empty] | 6 | On-site modification | Removal of piping, electrics and sandwich panels | 3 | [53 empty] | —— | bar: December 8 to December 11
32 |  | Manual diaphragm valve | See attachment | 316L | —— | unit | See attachment | Newly purchased | Use the components from Option 1 / Option 2 | 45 | [5 empty] | 7 |  | Removal of the steel platform | 2 | [53 empty] | —— | bar: December 12 to December 13
33 |  | BPE piping and fittings | See attachment | 316L | —— | unit | See attachment | Newly purchased | Use the components from Option 1 / Option 2 | 35 | [5 empty] | 8 |  | Removal of the external wall | 1 | bar: December 14
Preparation system – Grade D area – equipment list | [10 empty] | Installation duration | Qualification duration | Total time | Technical requirements |  | 9 |  | Equipment removal | 1 | bar: December 15
No. | Equipment tag | Equipment name | Technical parameters | Equipment material | Process medium | Unit | Quantity | Option |  | Procurement lead time | 40 | Qualification 18 d (including HVAC qualification), 24 h, must not be affected by the floor work Commissioning 1 d, HVAC EOQ + OQ 5 d, PQ 12 d, dead time |  | 1. The equipment shall comply with ASME BPE, including but not limited to: (1) NA-type connections meeting the 2D drainability requirement; connection sizes and quantities as per the approved drawings; (2) Spray port with spray ball, giving full coverage and passing the riboflavin coverage test; (3) Diaphragm valve welded to the outlet, meeting the 2D requirement; (4) External surface roughness < 0.8 µm, internal surface roughness < 0.4 µm; (5) Raw materials, components, manufacturing and acceptance strictly in line with ASME BPE, with the supporting documentation provided; 2. Motor and gearbox: (1) Well-known domestic brand; fully stainless-steel clad to sanitary standard; (2) Explosion protection Ex d IIB T4 Gb, ingress protection not lower than IP55; motor efficiency class 2 or better; 3. Double-end sanitary dry-running mechanical seal from a well-known domestic brand; 4. Agitator material identical to the vessel; agitator design as per the approved drawings; 5. Insulation thickness to suit the temperature requirement; cladding in 3 mm stainless steel with an external surface roughness < 0.8 µm, |  | 10 |  | Equipment lifting and assembly | 2 | bar: December 16 to December 17
1 | 1211-HPPC03-AT03 | Fraction receiving agitated vessel (jacketed) | 1. Working volume 8000 L; 2. Vessel design temperature −20 to 150 °C, jacket design temperature −25 to 180 °C; 3. Vessel design pressure −0.1 to 0.1 MPa; jacket operating pressure 0.6 MPa; | Product contact: 316L stainless steel; Jacket: 304 stainless steel; Insulation: perlite powder; Insulation cladding: 304 stainless steel; | Various organic solvents | unit | 1 | Purchase new and install | Under price negotiation; supplier not yet confirmed | 90 | [5 empty] | 11 |  | Reinstatement of the steel platform and the external wall | 5 | bar: December 18 to December 22
2 | 1211-HPPC03-AT04/AT05 | Fraction receiving agitated vessel (jacketed) | 1. Working volume 3000 L; 2. Vessel design temperature −20 to 150 °C, jacket design temperature −25 to 180 °C; 3. Vessel design pressure −0.1 to 0.1 MPa; jacket operating pressure 0.6 MPa; | Product contact: 316L stainless steel; Jacket: 304 stainless steel; Insulation: perlite powder; Insulation cladding: 304 stainless steel; | Various organic solvents | unit | 2 | Purchase new and install | Under price negotiation; supplier not yet confirmed | 90 | [5 empty] | 12 |  | Reinstatement of the sandwich panels | 5 | bar: December 18 to December 22
3 | 1211-HPPC03-AT06 | Sample agitated vessel (jacketed) | 1. Working volume 1000 L; 2. Vessel design temperature −20 to 150 °C, jacket design temperature −25 to 180 °C; 3. Vessel design pressure −0.1 to 0.1 MPa; jacket operating pressure 0.6 MPa; | Product contact: 316L stainless steel; Jacket: 304 stainless steel; Insulation: perlite powder; Insulation cladding: 304 stainless steel; | Various organic solvents | unit | 1 | Purchase new and install | Under price negotiation; supplier not yet confirmed | 90 | [5 empty] | 13 |  | Installation of equipment and piping | 10 | [53 empty] | Consider prefabricating part of the piping in advance | bar: December 22 to December 31
4 | 1211-HPPC03-T06 | Top-fraction sample agitated vessel (jacketed) | 1. Working volume 1000 L; 2. Vessel design temperature −20 to 150 °C, jacket design temperature −25 to 180 °C; 3. Vessel design pressure −0.1 to 0.1 MPa; jacket operating pressure 0.6 MPa; | Product contact: 316L stainless steel; Jacket: 304 stainless steel; Insulation: perlite powder; Insulation cladding: 304 stainless steel; | Various organic solvents | unit | 1 | Purchase new and install | Under price negotiation; supplier not yet confirmed | 90 |  |  |  | The equipment shall comply with ASME BPE, including but not limited to: (1) NA-type connections meeting the 2D drainability requirement; connection sizes and quantities as per the approved drawings; (2) Spray port with spray ball, giving full coverage and passing the riboflavin coverage test; (3) Diaphragm valve welded to the outlet, meeting the 2D requirement; (4) External surface roughness < 0.8 µm, internal surface roughness < 0.4 µm; (5) Raw materials, components, manufacturing and acceptance strictly in line with ASME BPE, with the supporting documentation provided; |  | 14 |  | Electrical and instrumentation installation | 5 | bar: December 29 to January 2
5 | *** | Fraction receiving storage tank (non-jacketed) | Working volume 100 L, operating temperature −20 to 100 °C, operating pressure −0.098 to 0.099 MPa | SS316L | Various organic solvents | unit | 12 | Purchase new and install | Under price negotiation; supplier not yet confirmed | 90 |  |  |  | The equipment shall comply with ASME BPE, including but not limited to: (1) NA-type connections meeting the 2D drainability requirement, with a fully drainable equipment body; (2) External surface roughness < 0.8 µm, internal surface roughness < 0.4 µm; (3) Raw materials, components, manufacturing and acceptance strictly in line with ASME BPE, with the supporting documentation provided; |  | 15 |  | Floor work and sealant treatment | 7 | bar: January 3 to January 9
| 1211-HPPC03-AT03-P01 | Sanitary centrifugal pump | Rated flow 12.5 m³/h, head 25 m, clamp connection, variable speed | SS316L | Various organic solvents | unit | 1 |  | Use the pumps from Option 1 / Option 2 | [6 empty] | 16 | Qualification | HVAC |  |  | January 10: Hot work is involved, so one at-rest and one in-operation monitoring run with 5-day incubation is required
| 1211-HPPC03-AT03-P02 | Sanitary centrifugal pump | Rated flow 2 m³/h, head 20 m, clamp connection, fixed speed | SS316L | Various organic solvents | unit | 1 |  | Use the pumps from Option 1 / Option 2 | [6 empty] | 17 |  | Storage tanks and piping | [54 empty] | IQ runs in parallel with installation | bar: January 11 to January 15
| 1211-HPPC03-AT04-P01 | Sanitary centrifugal pump | Rated flow 12.5 m³/h, head 25 m, clamp connection, variable speed | SS316L | Various organic solvents | unit | 1 |  | Use the pumps from Option 1 / Option 2 | [6 empty] | 18 | Equipment preparation | Cleaning | bar: January 16 to January 17
| 1211-HPPC03-AT05-P01 | Sanitary centrifugal pump | Rated flow 12.5 m³/h, head 25 m, clamp connection, variable speed | SS316L | Various organic solvents | unit | 1 |  | Use the pumps from Option 1 / Option 2
| 1211-HPPC03-AT06-P01 | Sanitary centrifugal pump | Rated flow 12.5 m³/h, head 25 m, clamp connection, variable speed | SS316L | Various organic solvents | unit | 1 |  | Use the pumps from Option 1 / Option 2
| 1211-HPPC03-T06-P01 | Sanitary centrifugal pump | Rated flow 3.2 m³/h, head 25 m, clamp connection, fixed speed | SS316L | Various organic solvents | unit | 1 |  | Use the pumps from Option 1 / Option 2
6 | *** | Pneumatic diaphragm pump | 5 m³/h, 25 m, quick-connect | SS316L | Various organic solvents | unit | 2 |  | Use the pumps from Option 1 / Option 2
| *** | Sanitary centrifugal pump | Rated flow 2 m³/h, head 20 m, clamp connection, fixed speed | SS316L | In-spec fractions | unit | 1 |  | Use the pumps from Option 1 / Option 2
| *** | Pneumatic diaphragm pump | Rated flow 5 m³/h, head 25 m, clamp connection | SS316L | Out-of-spec fractions | unit | 1 |  | Use the pumps from Option 1 / Option 2
21 | Components | Mass flow meter (quick-connect, BPE) | See attachment | 316L | —— | unit | See attachment | Newly purchased | Use the components from Option 1 / Option 2 | 30
22 |  | Pneumatic diaphragm control valve (quick-connect, BPE) | See attachment | 316L | —— | unit | See attachment | Newly purchased | Use the components from Option 1 / Option 2 | 42
23 |  | Pneumatic diaphragm on/off valve (quick-connect, BPE) | See attachment | 316L | —— | unit | See attachment | Newly purchased | Use the components from Option 1 / Option 2 | 42
24 |  | Pneumatic control valve (quick-connect, BPE) | See attachment | 316L | —— | unit | See attachment | Newly purchased | Use the components from Option 1 / Option 2 | 42
25 |  | Pneumatic on/off valve (quick-connect, BPE) | See attachment | 316L | —— | unit | See attachment | Newly purchased | Use the components from Option 1 / Option 2 | 42
26 |  | Radar level transmitter | See attachment | 316L | —— | unit | See attachment | Newly purchased | Use the components from Option 1 / Option 2 | 20
27 |  | Tuning-fork level switch | See attachment | 316L | —— | unit | See attachment | Newly purchased | Use the components from Option 1 / Option 2 | 20 | Installation duration | Qualification duration | Total time | Technical requirements
28 |  | Temperature instrument | See attachment | 316L | —— | unit | See attachment | Newly purchased | Use the components from Option 1 / Option 2 | 20 | 10 | 6 d, 24 h IQ runs in parallel with installation and is closed during commissioning; commissioning 1 d, EOQ + OQ 3 d, PQ 2 d |  | The equipment shall comply with ASME BPE, including but not limited to: (1) NA-type connections meeting the 2D drainability requirement; connection sizes and quantities as per the approved drawings; (2) Spray port with spray ball, giving full coverage and passing the riboflavin coverage test; (3) Diaphragm valve welded to the outlet, meeting the 2D requirement; (4) External surface roughness < 0.8 µm, internal surface roughness < 0.4 µm; (5) Raw materials, components, manufacturing and acceptance strictly in line with ASME BPE, with the supporting documentation provided;
29 |  | pH instrument | See attachment | 316L | —— | unit | See attachment | Newly purchased | Use the components from Option 1 / Option 2 | 42 | [5 empty] | Retrofit of the ultrafiltration area – replace all storage tanks and pumps with new units (316L) and convert to BPE piping (316L)
30 |  | Pressure instrument | See attachment | 316L | —— | unit | See attachment | Newly purchased | Use the components from Option 1 / Option 2 | 21 | [5 empty] | No. | Activity | Equipment / material | Lead time / duration | Expected delivery date | December 8: December; January 8: January | Remarks
31 |  | Manual diaphragm valve | See attachment | 316L | —— | unit | See attachment | Newly purchased | Use the components from Option 1 / Option 2 | 45 | [10 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21
32 |  | BPE piping and fittings | See attachment | 316L | —— | unit | See attachment | Newly purchased | Use the components from Option 1 / Option 2 | 35 | [5 empty] | 1 | Equipment procurement | Delivery of the storage tanks (316L) | 80 | 05 Dec | [52 empty] | Ordered | bar: December 1 to December 6
Ultrafiltration system equipment list | [15 empty] | 2 |  | Procurement of control valves / instruments (316L) | 42 | 25 Oct | [52 empty] | Partly ordered, partly not ordered; estimated delivery date
No. | Equipment tag | Equipment name | Technical parameters | Equipment material | Process medium | Unit | Quantity | Option |  | Procurement lead time | [5 empty] | 3 |  | Procurement of BPE fittings (316L) | 30 | 15 Oct | [52 empty] | Ordered
1 | 1211-TFF01-T01 | Ultrafiltration receiving storage tank (jacketed) | 1. Working volume 1000 L; 2. Vessel design temperature −20 to 150 °C, jacket design temperature −25 to 180 °C; 3. Vessel design pressure −0.1 to 0.1 MPa; jacket operating pressure 0.6 MPa; | SS316L | Various organic solvents | unit | 1 | Purchase new and install | Under price negotiation; supplier not yet confirmed | 75 | Installation duration | Qualification duration | Total time | Technical requirements |  | 4 |  | BPE manual valves (316L) | 30 | 15 Oct | [52 empty] | Ordered
2 | Components | Mass flow meter (quick-connect, BPE) | See attachment | 316L | —— | unit | See attachment | Newly purchased | Use the components from Option 1 / Option 2 | 30 | 30 | 18 d (qualification 18 d), 24 h Reactor / filter-dryer Requalification required Commissioning 1 d, HVAC EOQ + OQ 5 d, PQ 12 d, dead time |  | 1. The equipment shall comply with ASME BPE, including but not limited to: (1) NA-type connections meeting the 2D drainability requirement; connection sizes and quantities as per the approved drawings; (2) Spray port with spray ball, giving full coverage and passing the riboflavin coverage test; (3) Diaphragm valve welded to the outlet, meeting the 2D requirement; (4) External surface roughness < 0.8 µm, internal surface roughness < 0.4 µm; (5) Raw materials, components, manufacturing and acceptance strictly in line with ASME BPE, with the supporting documentation provided; 2. Motor and gearbox: (1) Well-known domestic brand; fully stainless-steel clad to sanitary standard; (2) Explosion protection Ex d IIB T4 Gb, ingress protection not lower than IP55; motor efficiency class 2 or better; 3. Double-end sanitary dry-running mechanical seal from a well-known domestic brand; 4. Agitator material identical to the vessel; agitator design as per the approved drawings; 5. Insulation thickness to suit the temperature requirement; cladding in 3 mm stainless steel with an external surface roughness < 0.8 µm, |  | 5 | On-site modification | Removal of sandwich panels, | 1 | [53 empty] | Remove in advance | bar: December 5
3 |  | Pneumatic diaphragm control valve (quick-connect, BPE) | See attachment | 316L | —— | unit | See attachment | Newly purchased | Use the components from Option 1 / Option 2 | 42 | [5 empty] | 6 |  | Removal and installation of the storage tank | 1 | [53 empty] | —— | bar: December 6
4 |  | Pneumatic diaphragm on/off valve (quick-connect, BPE) | See attachment | 316L | —— | unit | See attachment | Newly purchased | Use the components from Option 1 / Option 2 | 42 | [5 empty] | 7 |  | Replacement of BPE piping | 5 | [53 empty] | —— | bar: December 5 to December 9
5 |  | Manual diaphragm valve | See attachment | 316L | —— | unit | See attachment | Newly purchased | Use the components from Option 1 / Option 2 | 45 | [5 empty] | 8 |  | Electrical and instrumentation installation | 3 | [53 empty] | —— | bar: December 7 to December 9
6 |  | BPE piping and fittings | See attachment | 316L | —— | unit | See attachment | Newly purchased | Use the components from Option 1 / Option 2 | 35 |  |  |  | 1. The equipment shall comply with ASME BPE, including but not limited to: (1) NA-type connections meeting the 2D drainability requirement; connection sizes and quantities as per the approved drawings; (2) Spray port with spray ball, giving full coverage and passing the riboflavin coverage test; (3) Diaphragm valve welded to the outlet, meeting the 2D requirement; (4) External surface roughness < 0.8 µm, internal surface roughness < 0.4 µm; (5) Raw materials, components, manufacturing and acceptance strictly in line with ASME BPE, with the supporting documentation provided; 2. Motor and gearbox: (1) Well-known domestic brand; fully stainless-steel clad to sanitary standard; (2) Explosion protection Ex d IIB T4 Gb, ingress protection not lower than IP55; motor efficiency class 2 or better; 3. Double-end sanitary dry-running mechanical seal from a well-known imported brand such as John Crane or Burgmann; 4. Agitator material identical to the vessel; agitator design as per the approved drawings; 5. Insulation thickness to suit the temperature requirement; cladding in 3 mm stainless steel with an external surface roughness < 0.8 µm, |  | 9 |  | Floor work and sealant treatment | 5 | [53 empty] | Equipment replacement; the floor is assumed to be redone | bar: December 10 to December 14
| *** | Pneumatic diaphragm pump | Rated flow 5 m³/h, head 25 m, clamp connection | SS316L |  | unit | 1 |  | Use the components from Option 1 / Option 2 | [6 empty] | 10 | Qualification | HVAC |  |  | December 15: Hot work is involved, so one at-rest and one in-operation monitoring run with 5-day incubation is required
| TJ4S-1211-TFF02-WTK01-MP01 | Centrifugal pump | Rated flow 3.2 m³/h, head 20 m | 304 |  | unit | 1 |  | Use the pumps from Option 1 / Option 2 | [6 empty] | 11 |  | Storage tanks and piping | [54 empty] | IQ runs in parallel with installation | bar: December 16 to December 20
| TJ4S-1211-TFF02-WTK01-MP02 | Centrifugal pump | Rated flow 3.2 m³/h, head 20 m | 304 |  | unit | 1 |  | Use the pumps from Option 1 / Option 2 |  |  |  |  | 1. The equipment shall comply with ASME BPE, including but not limited to: (1) External surface roughness < 0.8 µm, internal surface roughness < 0.4 µm; (2) Raw materials, components, manufacturing and acceptance strictly in line with ASME BPE, with the supporting documentation provided; | Requirement to be confirmed by Production | 12 | Equipment preparation | Cleaning | bar: December 21 to December 22
Precipitation reactor area equipment list
No. | Equipment tag | Equipment name | Technical parameters | Equipment material | Process medium | Unit | Quantity | Option |  | Procurement lead time
1 | 1211-R01 | Crystallizer | 1. Working volume 2000 L; 2. Reactor design temperature −25 to 200 °C, jacket design temperature −25 to 220 °C; 3. Reactor design pressure −0.1 to 0.4 MPa; jacket operating pressure 0.6 MPa; | Product contact: 304 stainless steel lined with C22 or C276; Jacket: 304 stainless steel; Insulation: perlite powder; Insulation cladding: 304 stainless steel; | Various organic solvents, acids, bases, etc. | unit | 1 | Purchase new and install | Under price negotiation; supplier not yet confirmed | 100
3 | 1211-AT01 | Agitated vessel | 1. Working volume 600 L; 2. Vessel design temperature −25 to 200 °C, jacket design temperature −25 to 220 °C; 3. Vessel design pressure −0.1 to 0.1 MPa; jacket operating pressure 0.6 MPa; | Product contact: 316L stainless steel; Jacket: 304 stainless steel; Insulation: perlite powder; Insulation cladding: 304 stainless steel; | Various organic solvents, salt solutions, etc. | unit | 1 | Purchase new and install | Under price negotiation; supplier not yet confirmed | 75
4 | 1211-AT02 | Agitated vessel | 1. Working volume 80 L; 2. Vessel design temperature −25 to 200 °C, jacket design temperature −25 to 220 °C; 3. Vessel design pressure −0.1 to 0.1 MPa; jacket operating pressure 0.6 MPa; | Product contact: 316L stainless steel; Jacket: 304 stainless steel; Insulation: perlite powder; Insulation cladding: 304 stainless steel; | Various organic solvents, acids, bases, etc. | unit | 1 | Purchase new and install | Under price negotiation; supplier not yet confirmed | 75
| TJ4S-1211-AT02-P02 | Pneumatic diaphragm pump | Rated flow 5 m³/h, head 25 m, clamp connection | SS316L |  | unit | 1 |  | Use the pumps from Option 1 / Option 2
15 | TJ4S-1211-AT01-P01 | Sanitary four-head diaphragm pump | Rated flow 200 L/h, BPE connection, clamp connection | 316L | Concentrated salt solution | unit | 1 |  | Use the pumps from Option 1 / Option 2
16 | TJ4S-1211-AT02-P01 | Sanitary four-head diaphragm pump | Rated flow 20 L/h, BPE connection, clamp connection | 316L | Concentrated salt solution | unit | 1 |  | Use the pumps from Option 1 / Option 2
5 | 1211-Fd01 | Filter-dryer | 1. Equipment size DN1200; 2. Vessel design temperature −25 to 200 °C, jacket design temperature −25 to 220 °C; 3. Vessel design pressure −0.1 to 0.1 MPa; jacket operating pressure 0.6 MPa; | Product contact: 304 stainless steel lined with C22 or C276; Jacket: 304 stainless steel; Insulation: perlite powder; Insulation cladding: 304 stainless steel; | Various organic solvents, acids, bases, etc. | unit | 1 | Purchase new and install | Under price negotiation; supplier not yet confirmed | 120
7 | *** | Rotary sifter | Throughput 200 kg/h. | SS316L | Solids | unit | 1 | Purchase new and install | Use the equipment from Option 1 / Option 2; all newly purchased | ?
8 | Components | Mass flow meter (quick-connect, BPE) | See attachment | 316L | —— | unit | See attachment | Newly purchased | Use the components from Option 1 / Option 2 | 30
9 |  | Pneumatic diaphragm control valve (quick-connect, BPE) | See attachment | 316L | —— | unit | See attachment | Newly purchased | Use the components from Option 1 / Option 2 | 42
10 |  | Pneumatic diaphragm on/off valve (quick-connect, BPE) | See attachment | 316L | —— | unit | See attachment | Newly purchased | Use the components from Option 1 / Option 2 | 42 | [5 empty] | Retrofit of the precipitation area – replace the precipitation reactor, filter-dryer (Hastelloy), 600 L storage tank and 80 L storage tank with new units and convert to BPE piping (316L)
11 |  | Manual diaphragm valve | See attachment | 316L | —— | unit | See attachment | Newly purchased | Use the components from Option 1 / Option 2 | 45 | [5 empty] | No. | Activity | Equipment / material | Lead time / duration | Expected delivery date | December 1: December; December 18: January; January 18: February
12 |  | BPE piping and fittings | See attachment | 316L | —— | unit | See attachment | Newly purchased | Use the components from Option 1 / Option 2 | 35
| TJ4S-1211-FD01-Tr01-P01 | Pneumatic diaphragm pump | Rated flow 5 m³/h, head 30 m, clamp connection | Corrosion-resistant |  | unit | 1 |  | Use the pumps from Option 1 / Option 2
| TJ4S-1211-FD01-Tr01-P02 | Pneumatic diaphragm pump | Rated flow 5 m³/h, head 30 m, clamp connection | Corrosion-resistant |  | unit | 1 |  | Use the pumps from Option 1 / Option 2
| TJ4S-1212-FD06-Tr01-P01 | Pneumatic diaphragm pump | Rated flow 5 m³/h, head 30 m, clamp connection | Corrosion-resistant |  | unit | 1 |  | Use the pumps from Option 1 / Option 2 | [11 empty] | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | Remarks
| *** | Sanitary centrifugal pump | Rated flow 2 m³/h, head 20 m, clamp connection, fixed speed | SS316L | Water for injection | unit | 2 |  | Use the pumps from Option 1 / Option 2 | [6 empty] | 1 | Equipment procurement | Delivery of the 2000 L Hastelloy reactor | 100 | 25 Dec | [52 empty] | Ordered | bar: December 1 to December 9
[16 empty] | 2 |  | Delivery of the DN1200 filter-dryer | 100 | 25 Dec | [52 empty] | Ordered | bar: December 1 to December 9
[16 empty] | 3 |  | Delivery of the storage tanks (316L) | 90 | 15 Dec | [52 empty] | Not ordered yet, estimated delivery date | bar: December 1
[16 empty] | 4 |  | Delivery of the centrifugal pumps (316L) | 42 | 25 Oct | [52 empty] | Not ordered yet, estimated delivery date
[16 empty] | 5 |  | Procurement of control valves / instruments (316L) | 42 | 25 Oct | [52 empty] | Partly ordered, partly not ordered; estimated delivery date
[16 empty] | 6 |  | Procurement of BPE fittings (316L) | 30 | 15 Oct | [52 empty] | Ordered
[16 empty] | 7 |  | BPE manual valves (316L) | 30 | 15 Oct | [52 empty] | Ordered
[16 empty] | 8 |  | BPE fittings (Hastelloy) | 60 | 30 Nov | [52 empty] | Ordered
[16 empty] | 9 | On-site modification | Removal of piping, electrics and sandwich panels | 4 | [53 empty] | Remove one week before the equipment arrives | bar: December 1 to December 4
[16 empty] | 10 |  | Removal of the steel platform | 2 | bar: December 5 to December 6
[16 empty] | 11 |  | Removal of the external wall | 1 | bar: December 7
[16 empty] | 12 |  | Equipment removal | 1 | bar: December 8
[16 empty] | 13 |  | Equipment lifting and assembly | 2 | [53 empty] | —— | bar: December 9 to December 10
[16 empty] | 14 |  | Reinstatement of the steel platform and the external wall | 5 | [53 empty] | —— | bar: December 11 to December 15
[16 empty] | 15 |  | Reinstatement of the sandwich panels | 5 | [53 empty] | —— | bar: December 11 to December 15
[16 empty] | 16 |  | Installation of equipment and piping | 10 | [53 empty] | —— | bar: December 14 to December 23
[16 empty] | 17 |  | Electrical and instrumentation installation | 5 | [53 empty] | —— | bar: December 20 to December 24
[16 empty] | 18 |  | Floor work and sealant treatment | 7 | [53 empty] | Large damaged area; the floor has to be redone, including detail work | bar: December 25 to December 31
[16 empty] | 19 | Qualification | HVAC |  |  | January 1: Hot work is involved, so one at-rest and one in-operation monitoring run with 5-day incubation is required
[16 empty] | 20 |  | Storage tanks and piping | bar: January 2 to January 6
[16 empty] | 21 | Equipment preparation | Cleaning | bar: January 7 to January 8

## 7. Customer Findings
[16 empty] | September | [13 empty] | October | [30 empty] | November
No. |  | Equipment tag | Equipment name | Technical parameters | Equipment material | Process medium | Unit | Quantity | Component | Internal assessment – rectification plan | Current status | Procurement time | Installation duration | Qualification and cleaning | Total time | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31
1 | Preparation / solution preparation | 1213-R05 | Hastelloy reactor | 3000 L Hastelloy reactor | C276 | Concentrated salt solution | unit | 1 | Equipment body | 1. Agitator: nut-fixed blades – change to a one-piece impeller 2. Top nozzles: 2.1 All nozzles are flanged; the pressure gauge and sight glass have to be changed to NA-type nozzles; material, nitrogen and off-gas nozzles to quick-connect 2.2 No dip tube – dosing above the liquid level – hydrochloric acid dosing: to be added 2.3 No in-line pH measurement – to be added 2.4 No in-line sampling port – to be added 2.5 Solids charging currently through a ball valve – to be changed to a butterfly valve; charging method: closed charging 2.6 Thermometer nozzle – thermowell type under discussion – closed thermowell 3. Bottom nozzle: 3.1 Diaphragm valve at the vessel bottom outlet 4. Side nozzles: N/A | 1. Concept fixed, IEPE is preparing the drawings, Materials / Engineering is confirming lead times, T-valves 6–7 weeks, modification 3 days. | 40 days | 10 days | 4 d (passivation 1 d + qualification 2 d + cleaning 1 d)
2 | [8 empty] | Piping | 1. Nitrogen: assessment shows no issue; raised by the customer on site 2. Off-gas: assessment shows no issue; raised by the customer on site 3. Solvent lines: no issue raised 4. Material lines: Reactor top lines: 4.1 Solvent lines in the tank farm – no question raised 4.2 139788-step3A-P01 purification line – design not suitable (valve 2D, slope, nitrogen purge, end-of-line sampling, end-of-line flush and drain, metered charging sequence control – SOP): rectified according to the standard reference diagram Reactor bottom lines: (expert assessment or a detailed discussion of the drain points with the customer is needed) 4.3 139788-step3A-P01: line from the R05 bottom outlet to 1211-HPPC03-AT01 / AT02 1. Add low-point drains upstream and downstream of the filter 2. Branch lines to the two units: 2D requirement for both valves 4.4 139788-step3A-P03: line from the R05 bottom outlet to 1211-HPPC03-AT01 1. Add a drain point at the root of the equipment: line flushing (expert assessment or a detailed discussion of the drain points with the customer is needed) 4.5 139788-step3A-P02: line from the R05 bottom outlet to 1211-HPPC03-AT02 1. No requirement raised | 1. Concept fixed, IEPE is preparing the drawings, Materials / Engineering is confirming lead times, the T-valve budget has been submitted, lead time 6–7 weeks, modification 5 days. 2. The purified-water drain is being redesigned; pre-use rinsing and draining and post-use blow-drying have to be ensured. The other drain lines have to be considered at the same time. 3. Prepare and prefabricate the additional hydrochloric acid charging line in advance. | 49 days | 5 days
3 | [8 empty] | Instruments | 1. Pressure: mount directly on the nozzle to keep 2D and delete the hand valve – rectification needed 2. Temperature: dip tube – must be closed – threaded sealing not allowed – rectification 3. pH: no side nozzle (measurement) – pH measured on a recirculation sample 4. Level: differential pressure / radar / tuning fork – none currently installed 5. Mass flow meter: mounting orientation – change to horizontal installation | The temperature and pressure instruments have been submitted for budget and purchase | 30 days | 1 day
4 | [8 empty] | Pumps | Not installed
5 | [8 empty] | Valves | Root valves of the nitrogen / off-gas lines: currently ball valves, to be replaced by Hastelloy diaphragm valves or blinds; all other valves to be replaced by Hastelloy diaphragm valves or blinds | The diaphragm valve budget has been submitted; the 316L and Hastelloy diaphragm valves are purchased together | 40 days 70 days
6 |  | 1211-HPPC03-AT01 | Solution preparation agitated vessel (non-jacketed) | Working volume 500 L, operating temperature −20 to 100 °C, operating pressure −0.098 to 0.099 MPa | C276 | Concentrated salt solution | unit | 1 | Equipment body | The tank is completely replaced by a Yingde 316L 600 L storage tank; 1. Agitator: one-piece impeller 2. Top nozzles: the nozzles do not meet the 2D requirement – the tank has to be replaced; 3. Bottom nozzle: assessment shows no issue; raised by the customer on site 4. Side nozzles: assessment shows no issue; raised by the customer on site | Ordered | 30 days + 20 days | 21 days | 1d
7 | [8 empty] | Piping | 1. Nitrogen: root ball valve – to be replaced by a diaphragm valve; 2. Off-gas: root ball valve – to be replaced by a diaphragm valve; 3. Solvent: not applicable 4. Material: 4.1 1211-HPPC03-AT01-P01 purification line design not suitable (valve 2D, slope, nitrogen purge, end-of-line sampling, end-of-line flush and drain, metered charging sequence control – SOP): rectified according to the standard reference diagram; 4.2 139788-step3A-P03 line from reactor R05 to 1211-HPPC03-AT01 material line valves to be replaced to BPE piping standard; 4.3 1211-HPPC03-AT01-P02: line from the AT01 bottom outlet to the inlet of 1211-HPPC03-AT01-P01 built to BPE piping standard – low-point drain in the line; 4.4 1211-HPPC03-T03-P01: line from 1211-HPPC03-AT01-P01 to T03 the static mixer, pH meter and conductivity meter installations have to be rectified to BPE requirements; a drain point has to be added at the pipe enlargement; Three-way on/off valve XV-HPPC03-T03-01: a check valve has to be added on the waste discharge line to the waste header | The BPE piping and diaphragm valves are purchased and ordered; construction is expected to start in mid-October | 28 days | 21 days
8 | [8 empty] | Instruments | 1. Pressure: delete the root valve – keep a 2D installation 2. Temperature: not applicable 3. pH: not applicable 4. Differential pressure / radar / tuning fork: differential pressure does not meet the 2D requirement and has to be changed to radar and tuning fork | The pressure, tuning-fork and radar instruments have been submitted for budget; supplier not yet selected | 30 days | 2 days
9 | [8 empty] | Pumps | Plunger metering pump: 1211-HPPC03-AT01-P01 Keep the low-point drains at the pump inlet and outlet: assessment shows no issue; raised by the customer on site | Four-head diaphragm pumps – being purchased in parallel
10 | [8 empty] | Valves | The line contains ball valves that have to be replaced by diaphragm valves | The 316L diaphragm valves are purchased and are expected on 20 October | 28 days | 21 days
11 |  | 1211-HPPC03-AT02 | Solution preparation agitated vessel (non-jacketed) | Working volume 300 L, operating temperature −20 to 100 °C, operating pressure −0.098 to 0.099 MPa | C276 | Concentrated salt solution | unit | 1 | Equipment body | The tank is completely replaced by a Yingde 316L 600 L storage tank; (the 300 L Hastelloy tank goes back to the factory to be converted to quick-connect nozzles) 1. Agitator: one-piece impeller 2. Top nozzles: the nozzles do not meet the 2D requirement – the tank has to be replaced; 3. Bottom nozzle: assessment shows no issue; raised by the customer on site 4. Side nozzles: assessment shows no issue; raised by the customer on site | Budget still to be submitted; return-to-factory modification of the Hastelloy tank takes 25 days | 30 days + 20 days | 21 days | 1d
12 | [8 empty] | Piping | 1. Nitrogen: root ball valve – to be replaced by a diaphragm valve; 2. Off-gas: root ball valve – to be replaced by a diaphragm valve; 3. Solvent: not applicable 4. Material: 4.1 1211-HPPC03-AT02-P01 purified-water line design not suitable (valve 2D, slope, nitrogen purge, end-of-line sampling, end-of-line flush and drain, metered charging sequence control – SOP): rectified according to the standard reference diagram 4.2 139788-step3A-P02 line from R05-P01 to 1211-HPPC03-AT02 built to BPE piping standard – low-point drain in the line; instrument valves meeting the 2D requirement; ball valves replaced by diaphragm valves 4.3 Line from the AT02 bottom outlet to the inlet of 1211-HPPC03-AT02-P01 built to BPE piping standard – low-point drain in the line; instrument valves meeting the 2D requirement; ball valves replaced by diaphragm valves | The BPE piping and diaphragm valves are purchased and ordered; construction is expected to start in mid-October | 28 days | 21 days
13 | [8 empty] | Instruments | 1. Pressure: delete the root valve – keep a 2D installation 2. Temperature: not applicable 3. pH: not applicable 4. Differential pressure / radar / tuning fork: differential pressure does not meet the 2D requirement and has to be changed to radar and tuning fork | The pressure, tuning-fork and radar instruments have been submitted for budget; supplier not yet selected | 30 days | 2 days
14 | [8 empty] | Pumps | Plunger metering pump: 1211-HPPC03-AT01-P02 Keep the low-point drains at the pump inlet and outlet: assessment shows no issue; raised by the customer on site | Four-head diaphragm pumps – being purchased in parallel
15 | [8 empty] | Valves | The line contains ball valves that have to be replaced by diaphragm valves | The 316L diaphragm valves are purchased and are expected on 20 October | 28 days | 21 days
16 |  | 1211-HPPC03-T01 | Purified water storage tank (non-jacketed) | Working volume 1000 L, operating temperature −20 to 100 °C, operating pressure −0.098 to 0.099 MPa | SS316L | Purified water | unit | 1 | Equipment body | The tank is completely replaced by a Yingde 316L 1500 L storage tank; 1. Agitator: not applicable 2. Top nozzles: nozzles do not meet 2D: 3. Bottom nozzle: nozzle does not meet 2D: 4. Side nozzles: nozzles do not meet 2D: | Replace with a Yingde tank; the tank budget is under final approval. | 30+20 |  | 5 d (qualification 4 d + cleaning 1 d)
17 | [8 empty] | Piping | 1. Nitrogen: not applicable 2. Off-gas: root ball valve – to be replaced by a diaphragm valve; 3. Solvent: not applicable 4. Material: 4.1 1211-HPPC03-T01-P01 purified-water line design not suitable (valve 2D, slope, nitrogen purge, end-of-line sampling, end-of-line flush and drain, metered charging sequence control – SOP): rectified according to the standard reference diagram 4.2 1211-HPPC03-T01-P02 line from the outlet of pump 1211-HPPC03-T03-P01 to storage tank 1211-HPPC03-T01 has to be changed to BPE piping; dead legs and drainability (dead-leg assessment to be carried out) 4.3 Line from the T01 tank bottom outlet to the inlet of pump 1211-HPPC03-T01-P01 has to be changed to BPE piping; dead legs and drainability (dead-leg assessment to be carried out) 4.4 1211-HPPC03-T01-P04 line from the T01 tank bottom outlet to the inlet of pump 1211-HPPC03-T01-P02 has to be changed to BPE piping; dead legs and drainability (dead-leg assessment to be carried out) 4.5 1211-HPPC03-T01-P05 line from the T01 tank bottom outlet to the inlets of pumps 1211-HPPC03-T03-P01 and 1318-HPPC03-T03-P02 has to be changed to BPE piping; dead legs and drainability (dead-leg assessment to be carried out) | 1. The size and quantity of the valves on the tank top have to be verified 2. The BPE piping is purchased and is expected on 20 October | 28 days | 21 days
18 | [8 empty] | Instruments | 1. Pressure: delete the root valve – keep a 2D installation 2. Temperature: not applicable 3. pH: not applicable 4. Differential pressure / radar / tuning fork: the differential-pressure level measurement does not meet 2D and is deleted; the radar level transmitter is installed to meet 2D and a tuning fork is added | The pressure, tuning-fork and radar instruments have been submitted for budget; supplier not yet selected | 30 days | 2 days
19 | [8 empty] | Pumps | Plunger metering pumps: 1211-HPPC03-T01-P01 / 1211-HPPC03-T01-P02 Keep the low-point drains at the pump inlet and outlet: assessment shows no issue; raised by the customer on site | Four-head diaphragm pumps – being purchased in parallel
20 | [8 empty] | Valves | The line contains ball valves that have to be replaced by diaphragm valves | The 316L diaphragm valves are purchased and are expected on 20 October | 28 days | 21 days
21 |  | 1211-HPPC03-T02 | Acetonitrile storage tank (non-jacketed) | Working volume 1000 L, operating temperature −20 to 100 °C, operating pressure −0.098 to 0.099 MPa | SS316L | Fresh acetonitrile, spare | unit | 1 | Equipment body | 1. Agitator: not applicable 2. Top nozzles: assessment shows no issue; raised by the customer on site 3. Bottom nozzle: assessment shows no issue; raised by the customer on site 4. Side nozzles: assessment shows no issue; raised by the customer on site | N/A | 30+20 |  | 5 d (qualification 4 d + cleaning 1 d)
22 | [8 empty] | Piping | 1. Nitrogen: assessment shows no issue; raised by the customer on site 2. Off-gas: assessment shows no issue; raised by the customer on site 3. Solvent: 3.1 Fresh acetonitrile charging line 4. Material – assessment shows no issue; raised by the customer on site 4.1 1211-HPPC03-T02-P01 line from the outlet of pump 1211-HPPC03-T04-P01 to acetonitrile storage tank 1211-HPPC03-T02 4.2 Line from the T02 tank bottom outlet to the inlet of pump 1211-HPPC03-T02-P01 4.3 Line from the T02 tank bottom outlet to the inlet of pump 1211-HPPC03-T02-P02 4.3 1211-HPPC03-T02-P04 line from the T02 tank bottom outlet to the inlet of pump 1211-HPPC03-T04-P01 | 1. The size and quantity of the valves on the tank top have to be verified 2. The BPE piping is purchased and is expected on 20 October | 28 days | 21 days
23 | [8 empty] | Instruments | 1. Pressure: assessment shows no issue; raised by the customer on site 2. Temperature: not applicable 3. pH: not applicable 4. Differential pressure / radar / tuning fork: radar is acceptable; the root valve of the differential-pressure level transmitter is deleted | Raise a change to remove the valve on site |  | 2 days
24 | [8 empty] | Pumps | Assessment shows no issue; raised by the customer on site | Four-head diaphragm pumps – being purchased in parallel
25 | [8 empty] | Valves | Assessment shows no issue; raised by the customer on site | 1. The size and quantity of the valves on the tank top have to be verified 2. The BPE piping is purchased and is expected on 20 October | 28 days | 21 days
26 |  | 1211-HPPC03-T03 | Mobile phase A storage tank (non-jacketed) | Working volume 1000 L, operating temperature −20 to 100 °C, operating pressure −0.098 to 0.099 MPa | SS316L | Mobile phase A | unit | 1 | Equipment body | 1. Agitator: not applicable 2. Top nozzles: some nozzles do not meet 2D: 3. Bottom nozzle: nozzle does not meet the 2D requirement 4. Side nozzles: nozzles do not meet the 2D requirement |  |  |  | 5 d (qualification 4 d + cleaning 1 d)
27 | [8 empty] | Piping | 1. Nitrogen: root ball valve – to be replaced by a diaphragm valve; 2. Off-gas: root ball valve – to be replaced by a diaphragm valve; 3. Solvent: not applicable 4. Material 4.1 1211-HPPC03-T03-P01 charging line for the mobile phases downstream of the static mixer; change to BPE piping; dead legs and drainability (dead-leg assessment to be carried out) 4.2 1211-HPPC03-T03-P05 recirculation line from the outlet of pump 1318-HPPC03-T03-P02 to tank T03 change to BPE piping; dead legs and drainability (dead-leg assessment to be carried out) 4.3 Line from the T03 tank bottom outlet to the inlet of pump 1211-HPPC03-T03-P01 change to BPE piping; dead legs and drainability (dead-leg assessment to be carried out) 4.4 Line from the T03 tank bottom outlet to the inlet of pump 1211-HPPC03-T03-P02 change to BPE piping; dead legs and drainability (dead-leg assessment to be carried out) | The BPE piping and diaphragm valves are purchased and ordered; construction is expected to start in mid-October | 28 days | 21 days
28 | [8 empty] | Instruments | 1. Pressure: delete the root valve – keep a 2D installation 2. Temperature: not applicable 3. pH: has to be changed to a type that can be exchanged and calibrated in-line; quotations for the new instrument type are being obtained 4. Differential pressure / radar / tuning fork: radar is acceptable; the root valve of the differential-pressure level transmitter is deleted | The pH instrument is purchased; the mounting sleeve is being replaced and the design is being confirmed |  | 2 days
29 | [8 empty] | Pumps | 1211-HPPC03-T03-P02 replace to BPE standard | The centrifugal pumps are purchased and ordered; delivery is expected in the second half of October | 35 days
30 | [8 empty] | Valves | The automated ball valves have to be replaced by automated diaphragm valves – installed to the 2D requirement XV-HPPC03-T03-P01-02 XV-HPPC03-T03-P01-03 XV-HPPC03-T03-P01-04 XV-HPPC03-T03-01 | The 316L diaphragm valves are purchased and are expected on 20 October The budget for the automated ball valves has been submitted; the supplier is not yet confirmed, lead time 8 weeks | 28 days 56 days | 21 days
31 |  | 1211-HPPC03-T04 | Mobile phase B storage tank (non-jacketed) | Working volume 1000 L, operating temperature −20 to 100 °C, operating pressure −0.098 to 0.099 MPa | SS316L | Acetonitrile | unit | 1 | Equipment body | 1. Agitator: not applicable 2. Top nozzles: some nozzles do not meet 2D: 3. Bottom nozzle: nozzle does not meet the 2D requirement 4. Side nozzles: nozzles do not meet the 2D requirement | The BPE piping and diaphragm valves are purchased and ordered; construction is expected to start in mid-October | 30+20 |  | 5 d (qualification 4 d + cleaning 1 d)
32 | [8 empty] | Piping | 1. Nitrogen: root ball valve – to be replaced by a diaphragm valve; 2. Off-gas: root ball valve – to be replaced by a diaphragm valve; 3. Solvent: 3.1 Fresh acetonitrile charging line 4. Material 4.1 1211-HPPC03-T04-P01 charging line for the mixed mobile phases via the static mixer change to BPE piping; dead legs and drainability (dead-leg assessment to be carried out) 4.2 Recirculation line from the outlet of pump 1211-HPPC03-T04-P01 to tank T04 change to BPE piping; dead legs and drainability (dead-leg assessment to be carried out) 4.3 1211-HPPC03-T04-P02 line from the T04 tank bottom outlet to the inlet of pump 1211-HPPC03-T04-P01 change to BPE piping; dead legs and drainability (dead-leg assessment to be carried out) | The BPE piping and diaphragm valves are purchased and ordered; construction is expected to start in mid-October | 28 days | 21 days
33 | [8 empty] | Instruments | 1. Pressure: delete the root valve – keep a 2D installation 2. Temperature: not applicable 3. pH: has to be changed to a type that can be exchanged and calibrated in-line; quotations for the new instrument type are being obtained 4. Differential pressure / radar / tuning fork: radar is acceptable; the root valve of the differential-pressure level transmitter is deleted | The pH instrument is purchased; the mounting sleeve is being replaced and the design is being confirmed |  | 2 days
34 | [8 empty] | Pumps | Not applicable | N/A
35 | [8 empty] | Valves | The automated ball valves have to be replaced by automated diaphragm valves – installed to the 2D requirement XV-HPPC03-T04-P01-02 XV-HPPC03-T04-P01-03 XV-HPPC03-T04-P01-04 XV-HPPC03-T04-01 | The 316L diaphragm valves are purchased and are expected on 20 October The budget for the automated ball valves has been submitted; the supplier is not yet confirmed, lead time 8 weeks | 28 days 56 days | 21 days
36 |  | Other | Mass flow meter (quick-connect, BPE) | See attachment | 316L | —— | unit | See attachment | Existing installed equipment | Adjust the installation angle so that the installation is drainable and the receiving equipment is installed close by. To be rectified together with the BPE piping retrofit. | Confirm the site conditions and adjust the angle | 0 |  | 3 d (passivation 2 d + qualification 1 d)
37 | [8 empty] | Existing installed equipment | A double valve arrangement has to be added on the nitrogen line; the valve type has to be agreed with the customer (the valves of the other utilities are confirmed at the same time) | The valve budget has been submitted; the supplier is not yet confirmed; lead time 15 days for the two-piece type and 40 days for the forged type
38 |  |  | Pressure instrument | See attachment | 316L | —— | unit | See attachment | Existing installed equipment | Install separately from the off-gas nozzle; included in the storage tank and BPE piping rectification. | A detailed concept will be defined on site
39 | Preparation system | 1211-HPPC03 | High-pressure preparative (prep-HPLC) system | ADC1000 |  |  |  |  | Equipment body | 1. The customer does not accept the existing threaded and compression-fitting connections and requires quick-connect fittings; the vendor's assessment is that this is not recommended for high-pressure piping: BPE piping is rated for 0.7 MPa while the preparative system operates at 7 MPa with a design pressure of 10 MPa, so it does not meet the requirement. 2. The ball valves on the unit are of the partly encapsulated type and have to be replaced by fully encapsulated ones – replacement is planned via procurement. 3. Side-wall sampling has to be added to the fraction collection drums. | 1. The assessment has to be explained to the customer. 2. The fully encapsulated valves are purchased and will be replaced on 10/15/2026 after delivery 3. Fit sampling valves and modify the drums. 10/20/2026
40 | [8 empty] | Piping | 1. Nitrogen: assessment shows no issue; raised by the customer on site 2. Off-gas: assessment shows no issue; raised by the customer on site 3. Solvent: not applicable 4. Material: 4.1 From the preparative system to the receiving drums: 1211-HPPC03-P01 to P10 are non-BPE lines – all to be rebuilt to BPE standard later 4.2 1211-HPPC03-P11 is a non-BPE line with many valves; the tees and similar do not meet the minimum dead-leg requirement, so the line will be rebuilt as BPE piping and the non-compliant points replaced by T-valves. 4.3 139788-step3A-P06 to AT06 is a non-BPE line with many valves; the tees and similar do not meet the minimum dead-leg requirement, so the line will be rebuilt as BPE piping and the non-compliant points replaced by T-valves. 4.4 Add one fixed BPE line for the homogenisation vessel | 4. The BPE piping components are purchased; the T-valves that have to be replaced are being re-ordered; the modification work is expected on 10/15/2026
41 | [8 empty] | Instruments | 1. Pressure: assessment shows no issue; raised by the customer on site 2. Temperature: assessment shows no issue; raised by the customer on site | N/A
42 | [8 empty] | Pumps | The three three-head high-pressure pumps on the unit lack drain points; it has to be discussed with the vendor whether they can be modified; One unit transfers in-spec fractions and one transfers waste liquid; assessment shows no issue and the customer raised no point on site | Ask the vendor's technical team tomorrow whether a drain can be added
43 | [8 empty] | Valves | The high-pressure preparative system has ball valves that are not fully encapsulated; they have to be replaced by fully encapsulated ball valves. | The fully encapsulated valves are purchased and are expected on 10/10/2026; the replacement takes 2 weeks
44 |  | 1211-HPPC03-AT03 | Fraction receiving agitated vessel (jacketed) | 1. Working volume 8000 L; 2. Vessel design temperature −20 to 150 °C, jacket design temperature −25 to 180 °C; 3. Vessel design pressure −0.1 to 0.1 MPa; jacket operating pressure 0.6 MPa; | Product contact: 316L stainless steel; Jacket: 304 stainless steel; Insulation: perlite powder; Insulation cladding: 304 stainless steel; | Various organic solvents | unit | 1 | Equipment body | 1. Agitator: fully welded design without screws, acceptable. 2. Top nozzles: nitrogen port, off-gas / pressure gauge port, two spray ports, acetonitrile port, in-spec fraction port – the connections do not meet the minimum dead-leg requirement, so T-valves and BPE piping have to be fitted. One unused quick-connect butterfly valve has to be removed. 3. Bottom nozzle: straight quick-connect nozzle; assessment shows no issue and the customer raised no point. 4. Side nozzles: the tuning-fork port does not meet 2D and has to be welded closed, with the instrument changed to a top-inserted design; the pH port does not meet 2D and has to be welded closed. | Items 2 and 4 will be modified during the 10/15/2026 works, the execution method for the reducers is being assessed new tuning-fork level switches meeting 2D have to be purchased the nozzle modification method has to be confirmed with the vendor in a meeting
45 | [8 empty] | Piping | 1. Nitrogen: the nitrogen piping is assessed as compliant and the customer raised no point. 2. Off-gas: the piping is assessed as compliant and the customer raised no point. 3. Solvent: the piping is assessed as compliant and the customer raised no point. 4. Material: 4.1 1211-HPPC03-AT03-P01 acetonitrile line: there is a flanged control valve; a quick-connect control valve will be purchased as a replacement. 4.2 1211-HPPC03-AT03-P02 recirculation line: non-BPE piping, has to be changed to BPE piping; dead legs are present and T-valves have to be fitted to control the minimum dead leg; 4.3 139788-step3A-P05 fraction transfer line to AT04: non-BPE piping, has to be changed to BPE piping; dead legs are present and T-valves have to be fitted to control the minimum dead leg; 4.4 139788-step3A-P09 fraction transfer line to ultrafiltration: dead legs are present and T-valves have to be fitted to control the minimum dead leg; | 4. The BPE piping components are purchased The newly identified quick-connect control valves and T-valves have to be re-ordered The modification is expected on 10/15/2026 | 28 days | 21 days
46 | [8 empty] | Instruments | 1. Pressure: assessment shows no issue; the customer raised no point on site 2. Temperature: assessment shows no issue; the customer raised no point on site 3. pH: has to be changed to a type that can be exchanged and calibrated in-line; quotations for the new instrument type are being obtained 4. Differential pressure / radar / tuning fork: the tuning-fork port does not meet 2D, so the instrument has to be changed to a top-inserted design and the original port has to be welded closed. 5. The mass flow meter meets the requirement, with no hold-up | 3. Sourcing a pH instrument that meets the customer's requirement. 4. New tuning-fork level switches will be purchased later Modification on 10/15/2026.
47 | [8 empty] | Pumps | 1211-HPPC03-AT03-P01: the pneumatic diaphragm pump used for recirculation and transfer to tank AT04 has to be replaced by a sanitary centrifugal pump. 1211-HPPC03-AT03-P01: the pump transferring the in-spec pool to ultrafiltration is a diaphragm pump that cannot be drained and has to be replaced by a sanitary centrifugal pump. To be confirmed with the customer whether this pump is acceptable. | The centrifugal pumps are purchased; delivery is expected in the second half of October, and the modification and installation start on 10/15/2026 | 35 days | 21 days
48 | [8 empty] | Valves | All are diaphragm valves and meet the requirement. | N/A
49 |  | 1211-HPPC03-AT04 | Loading vessel (jacketed) | 1. Working volume 3000 L; 2. Vessel design temperature −20 to 150 °C, jacket design temperature −25 to 180 °C; 3. Vessel design pressure −0.1 to 0.1 MPa; jacket operating pressure 0.6 MPa; | Product contact: 316L stainless steel; Jacket: 304 stainless steel; Insulation: perlite powder; Insulation cladding: 304 stainless steel; | Various organic solvents | unit | 2 | Equipment body | 1. Agitator: fully welded design, meets the requirement. 2. Top nozzles: two spray ball ports, one off-gas port, one spare port, one pressure transmitter port, one nitrogen port and one acetonitrile port; there is a reducer below the valve, which does not meet 2D, so BPE piping has to be fitted; 3. Bottom nozzle: straight quick-connect design; assessment shows no issue and the customer raised no point on site. 4. Side nozzles: the tuning-fork port does not meet 2D and does not allow in-line exchange, so the instrument has to be changed to a top-inserted design and the original port has to be welded closed. | Items 2 and 4 will be modified during the 10/15/2026 works, the execution method for the reducers is being assessed new tuning-fork level switches meeting 2D have to be purchased the nozzle modification method has to be confirmed with the vendor in a meeting | 0 |  | 4 d (passivation 1 d + qualification 2 d + cleaning 1 d)
50 | [8 empty] | Piping | 1. Nitrogen: the nitrogen piping is assessed as compliant and the customer raised no point. 2. Off-gas: the piping is assessed as compliant and the customer raised no point. 3. Solvent: the piping is assessed as compliant and the customer raised no point. 4. Material: 4.1 1211-HPPC03-AT04-P01 acetonitrile line: there is a flanged control valve; a quick-connect control valve will be purchased as a replacement. 4.2 Purified-water line: rinsing / drain points and a T-valve tee have to be added. 4.3 1211-HPPC03-AT04-P02 loading line: non-BPE piping, has to be changed to BPE piping, and dead-leg tees and similar have to be replaced to meet the minimum dead-leg requirement. 4.4 1211-HPPC03-AT04-P03 recirculation line: non-BPE piping, has to be changed to BPE piping, and dead-leg tees and similar have to be replaced to meet the minimum dead-leg requirement. | 4. The BPE piping components are purchased The newly identified quick-connect control valves and T-valves have to be re-ordered The modification is expected on 10/15/2026 | 28 days | 21 days
51 | [8 empty] | Instruments | 1. Pressure: assessment shows no issue; the customer raised no point on site 2. Temperature: assessment shows no issue; the customer raised no point on site 3. pH: has to be changed to a type that can be exchanged and calibrated in-line; quotations for the new instrument type are being obtained 4. Differential pressure / radar / tuning fork: the tuning fork is side-inserted and has to be changed to top-inserted. | 3. Sourcing a pH instrument that meets the customer's requirement. 4. New tuning-fork level switches will be purchased later Modification on 10/15/2026.
52 | [8 empty] | Pumps | 1211-HPPC03-AT04-P01: one pneumatic diaphragm pump used for recirculation cleaning cannot be drained and has to be replaced by a centrifugal pump. | The centrifugal pumps are purchased; delivery is expected in the second half of October, and the modification and installation start on 10/15/2026 | 35 days | 21 days
53 | [8 empty] | Valves | All are diaphragm valves and meet the requirement. | N/A
54 |  | 1211-HPPC03-AT05 | Fraction collection vessel | "1. Working volume 3000 L; 2. Vessel design temperature −20 to 150 °C, jacket design temperature −25 to 180 °C; 3. Vessel design pressure −0.1 to 0.1 MPa; jacket operating pressure 0.6 MPa;" |  |  |  |  | Equipment body | 1. Agitator: the agitator has bolted parts, so the vendor has to come on site for hot-work welding. 2. Top nozzles: two spray ball ports, one off-gas port, one spare port, one pressure transmitter port, one nitrogen port and one acetonitrile port; there is a reducer below the valve, which does not meet 2D, so BPE piping has to be fitted; one solids charging port is missing and has to be added by hot-work modification; 3. Bottom nozzle: straight quick-connect design; assessment shows no issue and the customer raised no point on site. 4. Side nozzles: the tuning-fork port does not meet 2D and does not allow in-line exchange, so a new type of tuning-fork instrument has to be purchased as a replacement. | Items 2 and 4 will be modified during the 10/15/2026 works, the execution method for the reducers is being assessed new tuning-fork level switches meeting 2D have to be purchased the nozzle modification method has to be confirmed with the vendor in a meeting | 0
55 | [8 empty] | Piping | 1. Nitrogen: the nitrogen piping is assessed as compliant and the customer raised no point. 2. Off-gas: the piping is assessed as compliant and the customer raised no point. 3. Solvent: the piping is assessed as compliant and the customer raised no point. 4. Material: 4.1 1211-HPPC03-AT05-P01: there is a flanged control valve; a quick-connect control valve will be purchased as a replacement. 4.2 Purified-water line: rinsing / drain points and a T-valve tee have to be added. 4.3 139788-step3A-P04, the recirculation line and the line to AT03: non-BPE piping, has to be changed to BPE piping, and dead-leg tees and similar have to be replaced to meet the minimum dead-leg requirement. | 4. The BPE piping components are purchased The newly identified quick-connect control valves and T-valves have to be re-ordered The modification is expected on 10/15/2026 | 28 days | 21 days
56 | [8 empty] | Instruments | 1. Pressure: assessment shows no issue; the customer raised no point on site 2. Temperature: assessment shows no issue; the customer raised no point on site 3. pH: has to be changed to a type that can be exchanged and calibrated in-line; quotations for the new instrument type are being obtained 4. Differential pressure / radar / tuning fork: the tuning-fork port does not meet 2D and does not allow in-line exchange, so the instrument has to be changed to a top-inserted design and the original port has to be welded closed. | 3. Sourcing a pH instrument that meets the customer's requirement. 4. New tuning-fork level switches will be purchased later Modification on 10/15/2026.
57 | [8 empty] | Pumps | 1211-HPPC03-AT05-P01: the pneumatic diaphragm pump has to be replaced by a centrifugal pump. | The centrifugal pumps are purchased; delivery is expected in the second half of October, and the modification and installation start on 10/15/2026 | 35 days | 21 days
58 | [8 empty] | Valves | All are diaphragm valves and meet the requirement. | N/A
59 |  | 1211-HPPC03-AT06 | 1000 L fraction collection vessel | 1000L |  |  |  |  | Equipment body | 1. Agitator: fully welded design, meets the requirement. 2. Top nozzles: two spray ball ports, one off-gas / pressure transmitter port, one nitrogen port, one acetonitrile port, one purified-water port and one in-spec fraction port; there is a reducer below the valve, which does not meet 2D, so BPE piping has to be fitted; in addition one port has to be added for a separate pressure gauge, which requires hot-work modification on site; 3. Bottom nozzle: straight quick-connect design; assessment shows no issue and the customer raised no point on site. 4. Side nozzles: the tuning-fork port does not meet 2D and does not allow in-line exchange, so the instrument has to be changed to a top-inserted design and the original port has to be welded closed. The differential-pressure port has to be deleted and the level measured by radar instead. | Items 2 and 4 will be modified during the 10/15/2026 works, the execution method for the reducers is being assessed new tuning-fork level switches meeting 2D have to be purchased the nozzle modification method has to be confirmed with the vendor in a meeting | 0
60 | [8 empty] | Piping | 1. Nitrogen: the nitrogen piping is assessed as compliant and the customer raised no point. 2. Off-gas: the piping is assessed as compliant and the customer raised no point. 3. Solvent: the piping is assessed as compliant and the customer raised no point. 4. Material: 4.1 1211-HPPC03-AT06-P01 purified-water line: rinsing / drain points and a T-valve tee have to be added. 4.2 1211-HPPC03-AT06-P02 recirculation line: non-BPE piping, has to be changed to BPE piping, and dead-leg tees and similar have to be replaced to meet the minimum dead-leg requirement. 4.3 139788-step3A-P07 transfer line for in-spec fractions to AT03: non-BPE piping, has to be changed to BPE piping, and dead-leg tees and similar have to be replaced to meet the minimum dead-leg requirement. | 4. The BPE piping components are purchased The newly identified quick-connect control valves and T-valves have to be re-ordered The modification is expected on 10/15/2026 | 28 days | 21 days
61 | [8 empty] | Instruments | 1. Pressure: assessment shows no issue; the customer raised no point on site 2. Temperature: assessment shows no issue; the customer raised no point on site 3. pH: has to be changed to a type that can be exchanged and calibrated in-line; quotations for the new instrument type are being obtained 4. Differential pressure / radar / tuning fork: the tuning-fork port does not meet 2D and does not allow in-line exchange, so the instrument has to be changed to a top-inserted design and the original port has to be welded closed. | 3. Sourcing a pH instrument that meets the customer's requirement. 4. New tuning-fork level switches will be purchased later Modification on 10/15/2026.
62 | [8 empty] | Pumps | 1211-HPPC03-AT06-P01: for recirculation and transfer of in-spec fractions the pneumatic diaphragm pump does not meet the drainability requirement and is replaced by a sanitary centrifugal pump. | The centrifugal pumps are purchased; delivery is expected in the second half of October, and the modification and installation start on 10/15/2026 | 35 days | 21 days
63 | [8 empty] | Valves | All are diaphragm valves and meet the requirement | N/A
64 |  | 1211-HPPC03-T06 | 1000 L top-sample vessel | 1000L |  |  |  |  | Equipment body | 1. Agitator: none. 2. Top nozzles: one spray ball port, one nitrogen port, one acetonitrile port, one temperature dip-tube port, one radar port, one tuning-fork port and one pressure / off-gas port; they do not meet 2D, so BPE piping has to be fitted; in addition one port has to be added for a separate pressure gauge, which requires hot-work modification on site; 3. Bottom nozzle: straight quick-connect design; assessment shows no issue and the customer raised no point on site. 4. Side nozzles: not applicable. | To be modified during the 10/15/2026 works, the execution method for the reducers is being assessed new tuning-fork level switches meeting 2D have to be purchased the nozzle modification method has to be confirmed with the vendor in a meeting | 0
65 | [8 empty] | Piping | 1. Nitrogen: the nitrogen piping is assessed as compliant and the customer raised no point. 2. Off-gas: the piping is assessed as compliant and the customer raised no point. 3. Solvent: the piping is assessed as compliant and the customer raised no point. 4. Material: 4.1 1211-HPPC03-T06-P01 recirculation line: non-BPE piping, has to be changed to BPE piping, and dead-leg tees and similar have to be replaced to meet the minimum dead-leg requirement. 4.2 1211-HPPC03-T06-P02 line to AT04: non-BPE piping, has to be changed to BPE piping, and dead-leg tees and similar have to be replaced to meet the minimum dead-leg requirement. 4.3 1211-HPPC03-T06-P03 line to the preparative system: non-BPE piping, has to be changed to BPE piping, and dead-leg tees and similar have to be replaced to meet the minimum dead-leg requirement. | 4. The BPE piping components are purchased The newly identified quick-connect control valves and T-valves have to be re-ordered The modification is expected on 10/15/2026 | 28 days | 21 days
66 | [8 empty] | Instruments | 1. Pressure: shares a nozzle with the off-gas line, which does not meet the cleanability requirement; a 1-to-2 splitter valve has to be fitted, see the customer's link; 2. Temperature: assessment shows no issue; the customer raised no point on site 3. Differential pressure / radar / tuning fork: the tuning-fork port does not meet 2D and does not allow in-line exchange, so the instrument has to be changed to a top-inserted design and the original port has to be welded closed. 4. The mass flow meter has to be side- or inverted-mounted to avoid hold-up, so the installation angle has to be readjusted. | 3. Sourcing a pH instrument that meets the customer's requirement. 4. New tuning-fork level switches will be purchased later Modification on 10/15/2026.
67 | [8 empty] | Pumps | 1211-HPPC03-T06-P01: used for recirculation and top sampling; non-BPE piping, has to be changed to BPE piping, and dead-leg tees and similar have to be replaced to meet the minimum dead-leg requirement. | The centrifugal pumps are purchased; delivery is expected in the second half of October, and the modification and installation start on 10/15/2026 | 35 days | 21 days
68 | [8 empty] | Valves | Tank C3: ball valves may be used, some diaphragm valves are fitted, meets the requirement. | N/A
69 |  |  | Nitrogen line valves inside the area | Single quick-connect shut-off valve |  |  |  |  | Piping | A double valve arrangement has to be added on the nitrogen line | Valves being purchased
70 |  |  | BPE piping and fittings | See attachment | 316L | —— | unit | See attachment | Existing installed equipment | The whole line to 2D standard, with T-valves and minimum dead legs; the tank nozzle positions have to be reworked. Drainability has to be considered at the in-line filters, reducers and similar points. Every tank should have a small waste drain at the solution inlet nozzle so that the line can be drained there when it is flushed. | Confirm the site conditions and adjust the angles; waiting for the IEPE concept, engineering confirmation of the works, and joint confirmation of feasibility by Production and QA. |  |  | 5 d (passivation 2 d + qualification 2 d + cleaning 1 d)
71 | Ultrafiltration | 1211-TFF01 | 30 m² ultrafiltration skid | 30 m² |  |  |  |  | Equipment body | 1. Discuss the agitator design of the ultrafiltration vessel with the customer and whether it should be changed to a top-mounted agitator. 2. About 50 of the existing 0.6 m² cassettes are stacked; the customer mentioned that 10 cassettes of 3 m² could be used instead. We have to contact Sartorius about 3 m² cassettes (2 kD). 3. Add a flow meter downstream of the rotary lobe pump and upstream of the cassette assembly. 4. Because the customer is worried about product loss through back-suction: it is strongly recommended to delete valve V305, or to keep V305 but add another line back into the recirculation vessel (see photo, marked 3 with a red circle). 5. In the P&ID the methanol dip tube on the left inside the recirculation vessel has to be inserted deeper, extended to just above the liquid level (90 L level), and the liquid has to be directed onto the wall of the recirculation vessel (see photo, marked 5 with a blue circle). (The customer is worried that the methanol is dosed in very small amounts while nitrogen is fed at the same time, creating a risk of evaporation.) | To be confirmed with the customer
72 | [8 empty] | Piping | 1. Nitrogen: the customer has not been on site to confirm yet 2. Off-gas: the customer has not been on site to confirm yet 3. Solvent: the customer has not been on site to confirm yet 4. Material: the customer has not been on site to confirm yet | To be confirmed with the customer
73 | [8 empty] | Instruments | 1. Pressure: the customer has not been on site to confirm yet 2. Temperature: the customer has not been on site to confirm yet 3. pH: the customer has not been on site to confirm yet 4. Load cells: the customer has not been on site to confirm yet 5. Conductivity: the customer has not been on site to confirm yet | To be confirmed with the customer
74 | [8 empty] | Pumps | The rotary lobe pump and the four-head diaphragm pump meet the requirement; | N/A
75 | [8 empty] | Valves | All are diaphragm valves and meet the requirement. | N/A
76 |  | 1211-TFF01-T01 | Ultrafiltration receiving storage tank (jacketed) | 1. Working volume 1000 L; 2. Vessel design temperature −20 to 150 °C, jacket design temperature −25 to 180 °C; 3. Vessel design pressure −0.1 to 0.1 MPa; jacket operating pressure 0.6 MPa; | SS316L | Various organic solvents | unit | 1 | Equipment body | 1. Agitator: none 2. Top nozzles: all quick-connect, some do not meet 2D 3. Bottom nozzle: quick-connect, no issue 4. Side nozzles: do not meet 2D, mainly the differential-pressure port. | All tank nozzles are converted to 2D; the concept and lead time are being confirmed with Chengxin; |  |  | 5 d (qualification 4 d + cleaning 1 d)
77 | [8 empty] | Piping | 1. Nitrogen: no issue 2. Off-gas: no issue 3. Solvent: non-BPE piping, has to be changed to BPE piping 4. Material: no issue; BPE piping and the slope are also acceptable | The BPE piping and diaphragm valves are purchased and ordered; construction is expected to start in mid-October | 28 days | 21 days
78 | [8 empty] | Instruments | 1. Pressure: shares one nozzle with the off-gas line; it has to be rearranged or a tee has to be fitted; 2. Temperature: no issue; 3. pH: none; 4. Differential pressure / radar / tuning fork: the tuning fork and the differential pressure do not meet the BPE 2D requirement | Delete the differential pressure and change to radar; new radar level transmitters have to be purchased
79 | [8 empty] | Pumps | None | N/A
80 | [8 empty] | Valves | The valves on the solvent piping have to be replaced by BPE diaphragm valves | The 316L diaphragm valves are purchased and are expected on 20 October | 28 days | 21 days
81 | Precipitation | 1211-R01 | Crystallizer | 1. Working volume 2000 L; 2. Reactor design temperature −25 to 200 °C, jacket design temperature −25 to 220 °C; 3. Reactor design pressure −0.1 to 0.4 MPa; jacket operating pressure 0.6 MPa; | Product contact: 304 stainless steel lined with C22 or C276; Jacket: 304 stainless steel; Insulation: perlite powder; Insulation cladding: 304 stainless steel; | Various organic solvents, acids, bases, etc. | unit | 1 | Equipment body | 1. Agitator: no issue 2. Top nozzles: the thermometer nozzle is too long 3. Bottom nozzle: quick-connect design, does not meet 2D 4. Side nozzles: none | Adjusted together with the BPE piping retrofit. |  |  | 4 d (passivation 1 d + qualification 2 d + cleaning 1 d)
82 | [8 empty] | Piping | 1. Nitrogen: the reactor nozzle piping is too long 2. Off-gas: the reactor nozzle piping is too long 3. Solvent: the reactor nozzle piping is too long 4. Material: does not meet 2D; the bottom outlet has a double tee | Adjusted together with the BPE piping retrofit. The reducer design has to be confirmed | 28 days | 21 days
83 | [8 empty] | Instruments | 1. Pressure: no dedicated nozzle; a separate nozzle has to be fitted 2. Temperature: the probe stem is too long , the thermometer has to be replaced; 3. pH: none 4. Differential pressure / radar / tuning fork: none | The thermometer is purchased Adjusted together with the BPE piping retrofit. | 28 days | 21 days
84 | [8 empty] | Pumps | None | N/A
85 | [8 empty] | Valves | All are diaphragm valves and meet the requirement; for the ball valves on the solvent piping it has to be confirmed with the customer whether diaphragm valves are required as for CIP piping. | Purchase one more pneumatic quick-connect diaphragm valve | 56 days | 2
86 |  | 1211-AT01 | Agitated vessel | 1. Working volume 600 L; 2. Vessel design temperature −25 to 200 °C, jacket design temperature −25 to 220 °C; 3. Vessel design pressure −0.1 to 0.1 MPa; jacket operating pressure 0.6 MPa; | Product contact: 316L stainless steel; Jacket: 304 stainless steel; Insulation: perlite powder; Insulation cladding: 304 stainless steel; | Various organic solvents, salt solutions, etc. | unit | 1 | Equipment body | 1. Agitator: no issue 2. Top nozzles: do not meet 2D 3. Bottom nozzle: does not meet 2D 4. Side nozzles: do not meet 2D; the large vessel flange uses a flat gasket seal, which does not meet the requirement | Modification is not feasible; the plan is to use a Tofflon or Yingde tank; the drawings have been requested and will be checked. |  |  | 5 d (qualification 4 d + cleaning 1 d)
87 | [8 empty] | Piping | 1. Nitrogen: no issue 2. Off-gas: no issue 3. Solvent: no issue 4. Material: no issue | N/A
88 | [8 empty] | Instruments | 1. Pressure: no dedicated nozzle 2. Temperature: does not meet 2D 3. pH: none 4. Differential pressure / radar / tuning fork: differential pressure and radar do not meet 2D | Adjusted together with the BPE piping retrofit. The reducer design has to be confirmed | 28 days | 21 days
89 | [8 empty] | Pumps | The metering pump does not meet the drainability requirement and is planned to be replaced by a four-head diaphragm pump; | Adjusted together with the BPE piping retrofit. The reducer design has to be confirmed; some nozzles and fittings are too small to buy, and this is being discussed with the vendor | 28 days | 21 days
90 | [8 empty] | Valves | All are diaphragm valves and meet the requirement | N/A
91 |  | 1211-AT02 | Agitated vessel | 1. Working volume 80 L; 2. Vessel design temperature −25 to 200 °C, jacket design temperature −25 to 220 °C; 3. Vessel design pressure −0.1 to 0.1 MPa; jacket operating pressure 0.6 MPa; | Product contact: 316L stainless steel; Jacket: 304 stainless steel; Insulation: perlite powder; Insulation cladding: 304 stainless steel; | Various organic solvents, acids, bases, etc. | unit | 1 | Equipment body | The tank is planned to be replaced: 1. Agitator: no issue 2. Top nozzles: do not meet 2D overall 3. Bottom nozzle: the flange does not meet the requirement; 4. Side nozzles: none The large vessel flange has an O-ring seal, which meets the requirement | Replaced by a Yingde 150 L vessel. The original 80 L vessel has a long lead time and is not worth modifying (2 months at the factory). |  |  | 5 d (qualification 4 d + cleaning 1 d)
92 | [8 empty] | Piping | 1. Nitrogen: no issue 2. Off-gas: no issue 3. Solvent: non-BPE piping, has to be changed to BPE piping 4. Material: non-BPE piping, has to be changed to BPE piping | Adjusted together with the BPE piping retrofit. The reducer design has to be confirmed | 28 days | 21 days
93 | [8 empty] | Instruments | 1. Pressure: the configuration is acceptable 2. Temperature: the configuration is acceptable 3. pH: the configuration is acceptable 4. Differential pressure / radar / tuning fork: the configuration is acceptable | The instruments for the new tank are purchased; the supplier is not yet confirmed
94 | [8 empty] | Pumps | The metering pump does not meet the drainability requirement and is planned to be replaced by a four-head diaphragm pump; | Adjusted together with the BPE piping retrofit. The reducer design has to be confirmed; some nozzles and fittings are too small to buy, and this is being discussed with the vendor | 28 days | 21 days
95 | [8 empty] | Valves | All are diaphragm valves and meet the requirement | N/A
96 |  | 1211-Fd01 | Filter-dryer | 1. Equipment size DN1200; 2. Vessel design temperature −25 to 200 °C, jacket design temperature −25 to 220 °C; 3. Vessel design pressure −0.1 to 0.1 MPa; jacket operating pressure 0.6 MPa; | Product contact: 304 stainless steel lined with C22 or C276; Jacket: 304 stainless steel; Insulation: perlite powder; Insulation cladding: 304 stainless steel; | Various organic solvents, acids, bases, etc. | unit | 1 | Equipment body | 1. Agitator: there was a gap between the bellows and the agitator; this has already been modified. 2. Top nozzles: do not meet 2D, there are 3 flanged nozzles 3. Bottom nozzles: the mother liquor outlet and the equalising line nozzle are both flanged 4. Side nozzles: none | The concept is confirmed and the drawings have been returned to the vendor. The return-to-factory modification takes 25 days; |  |  | 2 d (qualification 1 d, cleaning 1 d)
97 | [8 empty] | Piping | 1. Nitrogen: the wet nitrogen piping does not meet the 2D requirement and is not cleanable; the piping has to be redesigned; 2. Off-gas: no issue 3. Solvent: one pneumatic quick-connect ball valve has to be replaced by a pneumatic diaphragm valve; 4. Material: no issue. | Adjusted together with the BPE piping retrofit. The reducer design has to be confirmed; some nozzles and fittings are too small to buy, and this is being discussed with the vendor | 28 days | 21 days
98 | [8 empty] | Instruments | 1. Pressure: no issue 2. Temperature: no issue 3. pH: none 4. Differential pressure / radar / tuning fork: none | N/A
99 | [8 empty] | Pumps | None | N/A
100 | [8 empty] | Valves | Two pneumatic quick-connect ball valves (solvent line, equalising valve) have to be replaced by pneumatic diaphragm valves | The valves are purchased, the supplier is not yet confirmed, lead time 8 weeks |  | 2 days
101 |  | Wet nitrogen | Wet nitrogen | 2 × 100 L |  |  |  |  | Equipment body | 1. The equipment is of flanged design; the control valve and the mixer are flange-connected. This does not meet the BPE requirements. 2. There are many cleaning dead legs overall and the unit is hard to clean – complete replacement; the newly purchased unit arrives this week. | One unit has arrived; the second unit arrives this week for installation and commissioning
102 | [8 empty] | Piping | The piping does not meet the BPE standard; it is GB-standard 316L.
103 | [8 empty] | Instruments | The instruments do not meet the BPE standard,
104 | [8 empty] | Pumps | Not applicable
105 | [8 empty] | Valves | The valves are ball valves and do not meet BPE
106 | [8 empty] | Assessment | 1. Study of the hold time for changing the water of the wet nitrogen system every 2 days 2. Study of the storage hold time of the wet nitrogen water vessel | The trial on the old unit failed; the plan is to use the new unit. Expected completion: mid-October
107 | [9 empty] | Assessment of the transfer for the wet nitrogen water change, of the filling method and of the protection during filling; one option is to use a dedicated filling vessel under local protection, the second is to transfer using sterile bags. | The local exhaust arrives end of September, the sterile bags arrive end of September
108 |  | Single-shaft rotary sifter | Rotary sifter | Throughput 200 kg/h. | SS316L | Solids | unit | 1 | Equipment body | The customer has not yet assessed and confirmed whether it is fit for use; at present it does not meet the BPE requirements; the electrical panel is large and has many dead legs, so the overall hygienic design is not acceptable; | To be discussed with the customer in a dedicated session
109 | [8 empty] | Piping | 1. Material: the customer agrees that the charging should be directly at the outlet of the filter-dryer; this is currently not the case and the height has to be lowered; the details still have to be discussed and confirmed with the customer. | To be discussed with the customer in a dedicated session
110 | [8 empty] | Instruments | 1. Temperature: there is no temperature probe, although there is a risk of overheating when the powder is compressed during the process. 2. Oxygen content: in-line measurement is fitted, but the connection is long and does not meet the 2D requirement. | To be discussed with the customer in a dedicated session
111 | [8 empty] | Pumps | Not fitted | N/A
112 | [8 empty] | Valves | Split-body butterfly valve fitted | N/A
113 |  |  | Nitrogen line valves inside the area | Single quick-connect shut-off valve |  |  |  |  | Piping | A double valve arrangement has to be added on the nitrogen line | Valves being purchased

## 8. Open Work & Site Punch List (hidden)
9788 retrofit work packages and construction plan
|  | Activity | Item | Equipment name | Equipment number | Estimated duration | Current status | Influencing factors | Supplier | Remarks
1 | Scope of the first retrofit | Preparation | Piping of the preparation system (change from 2-phase to 3-phase solution preparation), modification of the metering pump inlets and outlets | Preparation / solution system | HPPC03 | Completed | The missing metering pump part was modified in-house and has been installed | Equipment and piping are being installed; three units were completed on the 5th; for the metering pump that was delivered incorrectly, an urgent assessment was made to switch to 316L and it is now installed, but the control valve, pulsation dampener and other parts will only arrive and be installed on the 15th | Tongbo
2 |  |  | Diaphragm valve replacement |  |  | Completed | Fully delivered and installed.
3 |  |  | Storage tank modification (nozzle replacement, polishing) | 500 L coated agitated vessel | HPPC03-AT01 | Completed | Flow meter and instrument installation and wiring completed |  | Zhejiang Chengxin
4 |  |  |  | 500 L coated agitated vessel | HPPC03-AT02 | Completed | Flow meter and instrument installation and wiring completed
5 |  |  |  | 316L agitated vessel | HPPC03-AT03 | Completed | Tank top polishing completed, piping completed, instrument installation completed
6 |  |  |  | 316L agitated vessel | HPPC03-AT04 | Completed
7 |  |  |  | 316L agitated vessel | HPPC03-AT05 | Completed
8 |  |  |  | 316L agitated vessel | HPPC03-AT06 | Completed | Tank top polishing completed, instrument installation completed, the piping from the system to the storage tank fully completed
9 |  |  |  | Purified water tank | HPPC03-T01 | Completed | Tank top polishing completed, piping completed, instrument installation completed, the roughness report has been issued, the vendor is collecting the BPE documentation;
10 |  |  |  | Acetonitrile tank | HPPC03-T02 | Completed
11 |  |  |  | Mobile phase A | HPPC03-T03 | Completed
12 |  |  |  | Mobile phase B | HPPC03-T04 | Completed
13 |  |  |  | Fraction tank | HPPC03-T05 | Completed
14 |  |  |  | Top-sample tank | HPPC03-T06 | Completed
15 |  |  |  | Waste liquid tank | HPPC03-WTK01 | Completed | Modification completed
16 |  |  |  | Waste liquid tank | HPPC03-WTK02 | Completed | Completed
18 |  | Ultrafiltration | Installation of storage tanks and equipment | 1000 L storage tank | TFF02 | Completed | Completed | The floor has been redone | Longma
19 |  |  | Storage tank nozzle modification | 316L storage tank | TFF02-T01 | Completed | Tank top polishing completed, piping completed, instrument installation completed | The floor has been redone | Chengxin
20 |  | Precipitation | Nozzle modification | 2000 L Hastelloy reactor | 1211-R01 | Completed |  | Floor work in progress | Chengxin
21 |  |  |  | 600 L agitated vessel | 1211-AT01 | Completed | All piping is completed; the jacket piping for the additional stand-alone hot / cold TCU is still being fabricated and is expected to be finished on 09/03/2026. | Floor work in progress | Zhejiang Chengxin
22 |  |  |  | DN1200 Hastelloy filter-dryer | 1211-FD01 | Completed | Tank top polishing completed, piping completed, instrument installation completed | Floor work in progress | Longma
23 |  | Clean area | Concealed works modification | Explosion-proof lighting |  | Completed | Replacement completed
24 |  |  |  | Explosion-proof circuit breaker |  | Completed | Installation completed
25 |  |  |  | Temperature / humidity sensor |  | Completed | Installation completed
26 |  |  |  | Interlocks |  | Completed | Replacement completed
27 |  |  |  | Stainless-steel instruments |  | Completed | Replacement completed
28 |  |  |  | Wi-Fi access point, telephone |  | Completed | Replacement completed
29 |  |  |  | Fire-fighting installations |  | Completed | Replacement completed
30 | Additional requirements, second round | Preparation | Add one TCU |  | HPP03-TCU03 | Completed | TCU01 / 02 / 03 are being commissioned on site |  | Tongbo
31 |  |  | The two original 500 L Halar-lined salt tanks are changed to a 300 L and a 500 L Hastelloy salt tank – BLA requirement on the equipment material; |  |  | Completed | Completed |  | Tongbo
32 |  |  | Swap the installation of the solution transfer pumps of the two salt tanks; |  |  | Completed | Completed |  | Tongbo
33 |  |  | Add a mass flow meter for the transfer from the 3000 L fraction tank to the 8000 L fraction tank. |  |  | Completed | Cancelled in the drawings |  | Tongbo
34 |  |  | Add a filter in the line from the 8000 L fraction tank to the loading vessel, |  |  | Completed | Cancelled in the drawings |  | Tongbo
35 |  |  | Fraction receiving port 4 no longer feeds the fraction drum; receiving port 9 is changed from the waste liquid tank to the fraction drum; receiving port 10 feeds the high-impurity / low-impurity streams, with an additional tee for switching |  |  | Completed | Rectification completed |  | Tongbo
36 |  | Ultrafiltration | Add 2 solvent lines |  |  | Completed | Rectification completed |  | Longma
37 |  | Precipitation | Add the 80 L and 600 L agitated vessels |  |  | Completed | All piping completed | The pump shipment was 6 days late and the safety accessories 10 days late; | Longma
38 |  |  | Add the wet nitrogen system |  |  | Completed | Tie-in points completed |  | Longma
39 |  | Material transfer | Add one 3000 L Hastelloy reactor, together with the transfer piping to the solution preparation room, add an in-line pH meter, and change the pneumatic on/off valve and control valve of the purified water to manual valves; |  |  | 2026-09-17 | The purified-water line is installed, the flow meter is installed and waiting for wiring; the pipe material for the distilled-water line has arrived but the work has not started yet | The vendor is being consulted; converting the reactor bottom outlet to a BPE quick-connect does not match the size, so a flanged connection is used first; as a pressure-vessel matter, the vendor will carry out the modification on site | Tongbo
40 |  |  | Material transfer line from the preparative system to ultrafiltration |  |  | Completed | The slope has been adjusted |  | Longma
41 |  |  | Add the material transfer line from ultrafiltration to the reactor |  |  | Completed | The slope has been adjusted |  | Longma
42 |  |  | From the prepared solution to the preparative unit and the collection tank system |  |  | Completed | Some fittings were removed for pickling and passivation of the piping; the slope will be readjusted once pickling and passivation are finished | HPPC03-AT03, HPPC03-AT04, HPPC03-AT05
43 |  |  | Equipment transfer piping of the ultrafiltration and precipitation systems |  |  | Completed | The ultrafiltration system is finished; the precipitation system is ongoing | TFF02, TFF02-T01, 1211-R01
44 | Additional requirements, third round | Preparation | Swap the functions and the installation positions of the 1000 L storage tank and the 1000 L agitated vessel |  |  | Completed | Modification completed |  | Tongbo
45 |  |  | Add acetonitrile line tie-ins for the 1000 L fraction agitated vessel / 3000 L loading vessel |  |  | Completed | Modification completed |  | Tongbo
46 |  |  | Add purified-water line tie-ins for the 1000 L fraction agitated vessel / 3000 L loading vessel |  |  | Completed | Modification completed |  | Tongbo
47 |  |  | Add the line transferring in-spec fractions from the fraction receiving drum to the 1000 L fraction agitated vessel |  |  | Completed | Modification completed |  | Tongbo
48 |  |  | Add a 3000 L recirculation cleaning line to the transfer line from the 3000 L fraction tank to the 8000 L fraction tank |  |  | Completed | Modification completed |  | Tongbo
49 |  |  | Add a mass flow meter in the line from the 8000 L fraction tank to the 1000 L intermediate tank of the TFF skid |  |  | Completed | Expected on 10 September | Delivered and inspected; installation will be completed once the workshop is released for personnel access | Tongbo
1. Preparation area: construction finished on the 5th (piping installation finished on the 3rd; the pump parts arrived late on the 4th, completion expected on the 5th) 2. Ultrafiltration area: finished on the 10th; the flow meter is expected on the 10th (piping installation finished on the 1st) 3. Precipitation area: construction finished on the 5th (piping installation finished on the 3rd; the pump parts arrived late on the 4th, completion expected on the 5th) 4. The new material transfer line from the level-4 reactor to the preparative system is expected to be finished before the 15th (required date); the flow meter is expected on the 10th; the CNC area does not affect the qualification of area C 5. Ultrafiltration floor on the 1st, precipitation area floor on the 2nd, floors of the retrofit areas on levels 3 and 4 on the 3rd
|  | Activity | Item | Equipment name | Equipment number | Estimated duration | Current status | Influencing factors | Supplier | Remarks
50 | Additional requirements, fourth round | Preparation | Subsequent change of the preparation / solution system, ultrafiltration and precipitation equipment to BPE design | Storage tanks, reactors, filter-dryer, associated piping, pumps, meters and valves | N/A | Equipment procurement lead time 100 days, installation 3 weeks, total installation 4 months, qualification expected to take 2–3 weeks. | All BPE fittings for the preparation area have been issued for purchase and are being quoted, lead time 5 weeks; of the pumps to be replaced, the 316L four-head diaphragm pumps are purchased, lead time approx.; the 316L sanitary centrifugal pumps are purchased and expected in the second half of October; the automated valves are under price negotiation and the vendor is not yet confirmed; the flow meters are ordered, arriving on 18 October; the automation instruments are ordered, arriving on 15 October; | The customer broadly accepts the reactors, filter-dryer and storage tanks; reactor R05 and tanks AT01 and AT02 have flanged connections that have to be changed to quick-connect; as pressure vessels are involved, the vendor will carry out the modification on site; the modification concept is largely confirmed and the vendor is expected on site on 15 October | Li Yanlong Zhang Bao Wang Zhiheng
51 |  |  | Preparation system | Preparative chromatography unit | Purification / separation HPPC03 | The valves are ordered and expected on 10 October; construction 10–15 days | Confirmed with the vendor that the requirement is not met; the parts are being purchased and the vendor is asked to come and modify the unit; | Explain why ball valves and non-TC connections are acceptable on the preparative system itself; the ball valves have to be of the cavity-filled type without hold-up – this was never mentioned before, an assessment has been arranged, and the current design does not comply | Fan Xingtao Gao Lei
52 |  |  | Preparation / solution system | HPPC03 | In-line three-phase mobile phase preparation of the preparative system | BPE fittings 28 days; BPE valves 42 days; 15 days of construction after the equipment and materials arrive | All BPE fittings for the preparation area have been issued for purchase; the first batch of 316L material is expected on 10 October, no lead time given for the second batch; the first batch of Hastelloy material is expected on 13 November, no lead time given for the second batch; 20 T-valves were purchased for the 2D drain points, expected on 25 October; | There are flanged connections in the lines, including flanged control valves; the metering pumps in the lines and the associated pulsation dampeners, control valves and safety valves do not meet the hygienic requirements; the lines do not meet the BPE standard; the drain points and tees do not meet the 2D standard | Song Jinzhu / Tongbo
53 |  |  | 3000 L Hastelloy reactor | 1213-R05 | Preparation of 1 M concentrated salt solution (Tris and ammonium acetate) | Option 1: reuse the unit from Peptide Building 3, expected end of October Option 2: return-to-factory modification, 60 days (the vendor has not confirmed an exact time; based on Peptide Building 3). Repeated discussions with the vendor confirmed that on-site modification is not possible. Option 3: buy new, 100 days; BPE fittings 28 days; BPE valves 42 days; 15 days of construction after the equipment and materials arrive | The flanged reactor bottom outlet is converted to quick-connect in Hastelloy; the concept is agreed with the vendor; the parts are expected on 15 October for the on-site modification, which takes 10 days; the bottom outlet piping is installed to 316L BPE standard and is already finished | There are flanged connections in the lines, including flanged control valves; the metering pumps in the lines and the associated pulsation dampeners, control valves and safety valves do not meet the hygienic requirements; the lines do not meet the BPE standard; the drain points and tees do not meet the 2D standard | Song Jinzhu / Tongbo / Chengxin
54 |  |  | 300 L Hastelloy agitated vessel | HPPC03-AT01 | Storage of 1 M concentrated salt solution (Tris and ammonium acetate) | Option 1: modify a Yingde 316L storage tank, 40 days (provided that 316L is acceptable; under assessment by Production) Option 2: return-to-factory modification, 60 days (the vendor has not confirmed an exact time; based on Peptide Building 3) Option 3: buy new, 100 days: BPE fittings 28 days; BPE valves 42 days; 15 days of construction after the equipment and materials arrive | The flanged top and bottom nozzles of the vessel are converted to quick-connect in Hastelloy; the concept is agreed with the vendor; the parts are expected on 15 October for the on-site modification, which takes 10 days; | There are flanged connections in the lines, including flanged control valves; the metering pumps in the lines and the associated pulsation dampeners, control valves and safety valves do not meet the hygienic requirements; the lines do not meet the BPE standard; the drain points and tees do not meet the 2D standard | Song Jinzhu / Tongbo / Chengxin
55 |  |  | 500 L Hastelloy agitated vessel | HPPC03-AT02 | Storage of 250 mM concentrated salt solution (Tris and ammonium acetate) |  | The flanged top and bottom nozzles of the vessel are converted to quick-connect in Hastelloy; the concept is agreed with the vendor; the parts are expected on 15 October for the on-site modification, which takes 10 days; | There are flanged connections in the lines, including flanged control valves; the metering pumps in the lines and the associated pulsation dampeners, control valves and safety valves do not meet the hygienic requirements; the lines do not meet the BPE standard; the drain points and tees do not meet the 2D standard | Song Jinzhu / Tongbo / Chengxin
56 |  |  | Surface roughness | 1000 L storage tank |  | Completed | Complete the polishing as soon as possible | There are weld marks on the upper head at the agitator and the local polishing is incomplete. | Song Jinzhu
57 |  |  | Valve selection | Ultrafiltration system |  | The valves in the ultrafiltration and preparation rooms are adjusted; the crystallisation room will be adjusted on the 16th | The valve quantities per room have been counted; the valves are purchased and quotations are being obtained | The waste drain valves are quick-connect valves with cleaning dead legs on the surface | QA / Song Jinzhu
58 |  |  | Replacement of the ultrafiltration filter | Ultrafiltration system |  | Completed | There is a redundant filter downstream, so this filter is simply replaced by a spool piece. | Replacing the ultrafiltration feed filter would expose the product | Song Jinzhu
59 |  |  | Bottom magnetic agitator motor | Ultrafiltration recirculation vessel |  | Completed | All items have been checked and the rust removal is completed | Some bolts show rust | Guo Zepeng
60 |  |  | Valve installation angle | Ultrafiltration system |  | Completed | The valves in the ultrafiltration and preparation rooms are adjusted; the crystallisation room will be adjusted on the 16th | The diaphragm valves are being adjusted on site | Song Jinzhu / Longma
61 |  | Precipitation | 600 L agitated vessel | 1211-AT01 | Salt formation of the system | During the customer's latest visit a drainability requirement was raised; the Ailipu metering pumps can be used | The new BPE vessels are submitted for budget and purchase; quotations are being obtained | The lines contain metering pumps whose pulsation dampeners, control valves and safety valves do not meet the hygienic requirements; the drain points and tees do not meet the 2D standard | Song Jinzhu Wang Zhiheng
62 |  |  | Nitrogen humidifier | Final product drying in the filter-dryer | Wet nitrogen for the final product drying in the filter-dryer | The concept is confirmed and the budget is under approval; the new nitrogen humidifier has arrived and qualification will be scheduled | The magnetic starter is installed; the laminar flow protection is configured and arrives on the 16th; | After the wet nitrogen unit is installed, the water filling protection and the laminar flow configuration of the new humidifier will be added | Li Yanlong Zhou Hongru Song Jinzhu
63 |  |  | Piping installation standard | Filter-dryer | 1211-FD01 | Completed | The DN25 transfer line on the filter-dryer platform is installed slightly out of line, probably because of the dimensions during installation | Realign the piping | Song Jinzhu / Longma
64 |  |  | Hose selection | Filter-dryer agitator | 1211-FD01 | Completed | The line is a metal-braided hose, which has cleaning dead legs | Change to a design without dead legs | Song Jinzhu
65 |  |  | Pipe support standard | 2000 L Hastelloy reactor |  | Completed | Some old pipe supports with dead legs are still in place | Change to the design used in the current rectification | Song Jinzhu
66 |  |  | DN1200 Hastelloy filter-dryer | 1211-FD01 | Filtration and drying | Completed | The vendor has completed the welding and grinding | There is a gap at the agitator shaft of the filter-dryer, with a risk of hold-up in the dead leg | Fan Xingtao Gao Lei
67 |  | Concealed works modification in the clean area | Floor drain | Clean area | Workshop environment requirement | Completed | QA has to assess and review the requirement | New points raised on site: 1. No preferred solution is available yet for the floor drain in the Grade C area 2. Insulate the HVAC return air duct to avoid condensation; 3. The gearbox and motor covers have been sealed with silicone 4. Caps have been made for the foot bolts and sealed with silicone 5. The diaphragm valve angles are being adjusted according to the qualification requirements 6. For the insulation prepared on site, the jacket is filled with foam 7. All DCS aseptic keyboards have been replaced 8. All pipe supports for the purified-water lines have been made 9. The customer considers that the wall and platform penetrations have cleaning dead legs, so an alternative design has to be considered. | Song Jinzhu
68 |  |  | Return air duct |  | Workshop environment requirement | Modification in 2–3 weeks | Add insulation; can be deferred and done once the urgent priorities are solved |  | Song Jinzhu
69 |  |  | Gearbox cover |  | Workshop environment requirement | Completed | The homogenisation vessel is rectified |  | Song Jinzhu
70 |  |  | Pneumatic pump installation |  | Workshop environment requirement | Completed | Pneumatic pumps: the foot bolt caps are installed |  | Song Jinzhu
71 |  |  | Diaphragm valve orientation |  | Workshop environment requirement | Completed | The clean room cannot be entered |  | Song Jinzhu Guo Zepeng
72 |  |  | Insulation |  | Workshop environment requirement | Completed | The insulation removal is completed |  | Guo Zepeng
73 |  |  | Keyboards |  | Workshop environment requirement | Completed | Replacement completed on the 14th |  | Song Jinzhu Fan Xingtao
74 |  |  | Purified-water pipe supports |  | Workshop environment requirement | Completed | Installation completed |  | Song Jinzhu
75 |  |  | Wall penetration sleeve |  | Workshop environment requirement | Sourcing the sleeves; expected 09/13/2026 | The modification design will be confirmed after the customer's inspection and then executed as hot work |  | Song Jinzhu Fan Xingtao
76 |  |  | Earthing flat bar |  | Workshop environment requirement | Keep the current design for now; the customer did not raise it again during the inspection on 15 September | The earthing flat bar looks rather obtrusive; the customer was asked whether there is a better design. | The customer will check the standard at Eli Lilly again | Li Gengkai
77 |  |  | Nitrogen connection |  | Workshop environment requirement | Valves are being purchased; a double valve arrangement will be added | The request for the quick-connect valves has been submitted | Quotations and lead times are being confirmed | Li Gengkai Song Jinzhu
78 |  |  | Sprinklers and smoke detectors |  | Workshop environment requirement | Completed | There should be a concealed type; the current one is not | Not usable in a Class A (explosive) area | Song Jinzhu
79 |  |  | Piping installation standard |  | Workshop environment requirement | Reduce unnecessary quick-connect clamps; completed | Minimise the number of quick-connect connections, for example a very short straight pipe with several quick-connect clamps; piping made in future shall be welded wherever possible | Reduce quick-connect connections in future piping and use automatic welding wherever possible | Song Jinzhu
81 |  |  | Covers for emergency lights and escape route signs |  | Workshop environment requirement | Completed | Removal and rectification completed | 09/07/2026 | Song Jinzhu

## 9. Auxiliary Equipment (hidden)
Auxiliary equipment
I. Equipment purchasing list
No. | Equipment / instrument / valve | Technical parameters | Unit | Quantity | Remarks | Remarks
1 | Filter housing | Single cartridge, 5 inch, BPE | unit | 50
2 | Filter housing | Single cartridge, 10 inch, BPE | unit | 20
3 | Filter housing | Triple cartridge, 10 inch, BPE | unit | 20
4 | Local laminar flow unit | Grade C standard, | unit | 1
5 | Water-for-injection hose | Platinum-cured silicone, BPE | piece | 20
6 | Filter cartridge | PTFE hydrophilic, 10 inch | piece | 100
7 | Filter cartridge | PTFE hydrophobic, 10 inch | piece | 60