## Action Trancker
ID | Visit Day | Area | Action Item | Priority | Suggested Owner | Status | Due Date | Notes
BLA-004 | Day 1 | Cleaning Validation | Cleaning validation and verification strategy needs presented. Including: strategy for determining appropriate cleaning solution and conditions (time, temp etc), how these are tranlasted to the operational record to ensure proper execution in a repeatable manner. Additionaly need to share how small parts and manual cleaned components are managed and integrated into cleaning records. Additionally, how are rinse and swab limits, sampling instructions, and results recorded. | High | Operations / QA | Open |  | General review item from visit notes
BLA-009 | Day 1 | AFD | Install or verify nameplate on rupture disk | Low | Engineering | Open
BLA-011 | Day 1 | Precipitation | Confirm inlet line sizing meets the 200 L/h process requirement | Low | Process Engineering | Open
BLA-012 | Day 1 | Equipment / Piping Standards | During field walkthroughs several lines visual appeard slopped in undesired location. Confirm all lines are sloped to appropriate low points with proper drain point. | High | Engineering / CQV | Open |  | Highlighted in source notes
BLA-013 | Day 1 | Equipment / Piping Standards | Provide adequate lighting for adequate visual inspection of all process tanks | Low | Facilities | Open
BLA-016 | Day 2 | Mobile Phase Formulation | Review HCl charging dip-tube arrangement and confirm material of construction | Low | Process Engineering | Open |  | Source note suggests HC; confirm exact alloy/specification
BLA-021 | Day 2 | Mobile Phase Formulation | Update MOR or SOP to require mobile-scale reading after the peristaltic pump empties the flexible connection | Low | Operations / QA | Open
BLA-022 | Day 2 | Mobile Phase Formulation | Document and verify the cleaning sequence: rinse, disassemble, clean, visually inspect, reassemble, final rinse, and pre-use rinse | Low | Operations / QA | Open
BLA-025 | Day 2 | ACN Supply | Add check valve near the three-way connector in the drain loop | Medium | Engineering | Open
BLA-035 | Day 3 | Facility / MOM | Assess short term actions to reduce risk associate with the lack of a CNC material-flow buffer zone and differential-pressure interlock in Workshop 12 | High | Facilities / QA | Open
BLA-042 | Day 3 | Hose Management | Validate or justify the one-month service life for dedicated PW hoses | Medium | Engineering / QA | Open |  | Notes state assessment exists but no validation
BLA-043 | Day 3 | Hose Management | Review cleaning frequency and lifecycle management for dedicated fresh-solvent corrugated hoses | Medium | Engineering / QA | Open
BLA-044 | Day 3 | Hose Management | Review pre-use cleaning and batch-disposal strategy for process-solution transfer hoses | Medium | Engineering / QA | Open
BLA-045 | Day 3 | Hose Management | Upgrade hose connections to smooth-bore internal design, considering Pharmaline N | High | Engineering | Open |  | Highlighted in source notes
BLA-051 | Days 1–3 | M+53 / DIPEA | Demonstrate reliable sourcing of DIPEA containing less than 50 ppm acetaldehyde | High | Supply Chain / QC / Process | Open |  | Executive-summary Priority 1 follow-up
BLA-052 | Days 1–3 | M+53 / DIPEA | Complete evaluation of internal DIPEA processing options to further reduce acetaldehyde content | High | Process Development / QC | Open |  | Executive-summary Priority 1 follow-up
BLA-053 | Days 1–3 | M+53 Investigation | Complete remaining M+53 fault-tree investigations and document supported conclusions | High | Process Development / QA | Open |  | Executive-summary Priority 1 follow-up
BLA-054 | Days 1–3 | M+53 Investigation | Assess the impact of extended DIPEA exposure and process hold times on impurity formation | High | Process Development | Open |  | Include deprotection and coupling operations
BLA-055 | Days 1–3 | M+53 / DIPEA | Reduce DIPEA charging and exposure duration where technically feasible and document the control strategy | High | Process Engineering / Operations | Open |  | Executive-summary Priority 1 follow-up
BLA-056 | Days 1–3 | HCN Removal | Evaluate increased nitrogen sparge rates for SC coupling | High | Process Development / Engineering | Open |  | Current equipment reportedly supports up to ~40 m³/h; current operating limit ~20 m³/h
BLA-057 | Days 1–3 | HCN Removal | Assess feasibility and effectiveness of nitrogen sweep operation during SC coupling | High | Process Development / Engineering | Open |  | Executive-summary Priority 1 follow-up
BLA-058 | Days 1–3 | HCN Removal | Demonstrate manufacturing-scale HCN removal equivalent to development and pivotal-batch conditions | High | Process Development / MSAT | Open |  | Scale-up justification required
BLA-059 | Days 1–3 | HCN Removal | Evaluate direct dissolved-HCN measurement for process characterization | High | Process Development / Analytical | Open |  | Focus on solution concentration rather than sparge-rate comparison alone
BLA-060 | Days 1–3 | HCN Removal | Confirm equipment limitations and establish the qualified operating envelope for higher nitrogen sparging rates | High | Engineering / Process Safety | Open |  | Include filter-plate protection constraints
BLA-061 | Days 1–3 | Passivation | Complete planned passivation of GG917 and LAARA process lines | High | Engineering / QA | Open |  | Executive-summary Priority 1 follow-up
BLA-062 | Days 1–3 | Passivation | Provide a remediation plan and timeline for solvent headers not included in the current passivation scope | High | Engineering / QA | Open |  | Executive-summary Priority 1 follow-up
BLA-063 | Days 1–3 | Passivation | Define remediation for bulk solvent tanks and solvent distribution systems that have not been passivated | High | Engineering / QA | Open |  | Bulk tanks reportedly in service for approximately two years
BLA-065 | Days 1–3 | Raw Material Handling | Develop interim administrative controls for raw material receipt and transfer into CNC areas to minimize potential exposure to outdoor conditions. | High | Operations / QA / EHS | Open |  | Address uncontrolled ingress pending a long-term solution
BLA-066 | Days 1–3 | Raw Material Handling | Evaluate long-term facility modifications to provide an airlock or physical segregation for CNC material transfer | Medium | Facilities / Engineering / QA | Open |  | Executive-summary Priority 2 follow-up
BLA-070 | Days 1–3 | CCS / Cross-Contamination | Provide and complete review of the site multiproduct cross-contamination risk assessment and incorporate high leve summary of risk and midigations into the process specific CCS docments. | Medium | QA / Technical Operations | Open |  | Executive-summary Priority 2 follow-up
BLA-074 | Days 1–3 | Hose Management | Replace silicone water hoses with PTFE hoses or provide a documented technical justification | Low | Engineering / QA | Open |  | Executive-summary Priority 3 follow-up
BLA-076 | Days 1–3 | Hose Management | Require immediate hose disconnection and controlled storage after use | Medium | Operations / QA | Open |  | Executive-summary Priority 3 follow-up
BLA-077 | Days 1–3 | Filtration Strategy | Create and approve a site-wide, risk-based filtration philosophy | Medium | Process / QA | Open |  | Executive-summary Priority 3 follow-up
BLA-078 | Days 1–3 | Filtration Strategy | Add filtration location, type, and justification diagrams or tables to CCS documentation for each process step | Medium | Process / QA | Open |  | Executive-summary Priority 3 follow-up
BLA-079 | Days 1–3 | Filtration Strategy | Define risk-based filter replacement criteria | Low | Process / QA | Open |  | Executive-summary Priority 3 follow-up
BLA-080 | Days 1–3 | Filtration Strategy | Reassess and document justification for 75-micron filtration of SPPS raw material drum charging. Filtration of liquid raw materials is required for all process steps. | High | Process / QA | Open |  | Executive-summary Priority 3 follow-up
BLA-081 | Days 1–3 | Glovebox Cleaning | Revise glovebox cleaning practices to use approved alcohol wipes rather than water wipes in dispensing areas | High | Operations / QA | Open |  | Executive-summary Priority 3 follow-up
BLA-083 | Days 1–3 | Facility / Humidity Control | Complete planned upgrades and demonstrate CNC relative humidity remains below 60% during summer conditions | Low | Facilities / Engineering / CQV | Open |  | Executive-summary Priority 3 follow-up
BLA-084 | Days 1–3 | Vent Header | Asymchem to provide vent header drawings and designs to Lilly for review | Medium | Engineering / Lilly Team | Open |  | Added per follow-up request
BLA-085 | Days 1–3 | CCS / Cross-Contamination | Evaluate process-specific cross-contamination risks from process connections and utility lines, then develop a long-term remediation plan to isolate nonessential connections or otherwise mitigate identified risks. Assess shared-utility and equipment-isolation requirements for GG917 and LAARA operations | High | QA / Engineering / Technical Operations | Open |  | Assess connection-specific risks as part of CCS and establish sustainable remediation controls
BLA-086 | Days 1–3 | Hose Management | Implement the use of permeable film to cover the ends of process and water hoses while stored for drying | High | Operations / QA | Open |  | Apply during drying and storage to protect hose ends while allowing ventilation
BLA-087 | Days 1–3 | Hose Management | Use a process-compatible solvent rather than water for the initial rinsing of new hoses | Medium | Operations / QA / Process | Open |  | Initial rinse recommendation for newly introduced hoses
BLA-088 | Days 1–3 | PD Pumps | Install low-point drains on the inlet and outlet of all PD pumps used in Category 4 systems, and add pre- and post-cleaning steps to drain from these points and nitrogen-purge through the pump to the outlet drain | High | Engineering / Operations / QA | Open |  | Attachment Sheet1 row 3; short-term requirement
BLA-089 | Days 1–3 | PD Pumps | Update the cleaning program for PD pumps so recovery factors account for large-area soft parts and include a representative pump swab location for product-contact applications | High | Cleaning Validation / QA | Open |  | Attachment Sheet1 row 3; short-term requirement
BLA-090 | Days 1–3 | PD Pumps | Evaluate long-term replacement of PD pumps with pressure transfer or hygienic centrifugal pumps with low-point casing drains; where PD pumps remain necessary, assess more drainable designs | Medium | Engineering / Process | Open |  | Attachment Sheet1 row 3; long-term requirement
BLA-091 | Days 1–3 | Equipment / Piping Standards | Several non-compliant items still exist against equipment/piping standards. For example, ball valves on Category 4 equipment/piping, long tank nozzles on vessel heads and/or branches off tank nozles that will not be cleanable during CIP, diptubes supported by hooks that form crevices, missing drains at low points (especially around filters), non-hygienic/cleanable instrument designs (level, temperature), flow meters installed in non-drainable, flanged connections on category 3 and 4 equipment/piping, bolted agitator blades, deadlegs in various locations due to use of non-zero-static valving/non-minimum distance tees, etc. Conduct a comprehensive gap assessment against equipment and piping standards and prioritize remediation of high-risk Category 3 and 4 systems before production start | High | Engineering / QA / CQV | Open |  | Attachment Sheet1 row 4; prioritize AFD, humidifier, and growth-promoting solution systems
BLA-092 | Days 1–3 | Equipment / Piping Standards | For equipment and piping gaps not remediated before production, establish direct traceability in cleaning documentation, including manual cleaning, targeted inspection, and cleaning or draining instructions for dead legs | High | Operations / Cleaning Validation / QA | Open |  | Attachment Sheet1 row 4; interim control pending alignment with Lilly and ASME BPE expectations
BLA-093 | Days 1–3 | Purified Water System | Purified Water header throughout the facility does not meet industry guidance - sample point is not representative of POU, no means of pre-use flushing/blowing, etc. Additionally, POU filtration should be provided for any PW supplied to a growth promoting solution via hose connection (upstream of drain line). These filters should have time in use tracked and be replaced frequently (NMT 24 hours). | High | Engineering / Utilities / QA | Open |  | Attachment Sheet1 row 5; short-term requirement
Implement point-of-use flushing directly to waste and post-use draining and drying for purified-water lines using zero-static valves or minimum-distance tees without creating dead legs
BLA-094 | Days 1–3 | Purified Water System | Install point-of-use filters for purified water supplied by hose to growth-promoting solutions, track time in use, and replace filters no later than 24 hours | High | Engineering / Operations / QA | Open |  | Attachment Sheet1 row 5; short-term requirement
BLA-095 | Days 1–3 | Purified Water System | Assess representative sampling from new point-of-use drains and determine whether formal revalidation or an informal verification study is required to confirm water-system quality | High | QC / Validation / Utilities | Open |  | Attachment Sheet1 row 5; short-term requirement
BLA-096 | Days 1–3 | Changeover Strategy | Provide Lilly with the changeover strategy and governance for reused equipment, including cleaning limits, normally uncleaned lines, soft and hard-to-clean components, and replacement of filters, membranes, and resins | High | QA / Operations / Cleaning Validation | Open |  | Attachment Sheet1 row 6; short-term requirement
BLA-097 | Days 1–3 | New Equipment Readiness | Define and document release controls for new equipment that demonstrate removal of fabrication and construction residues, debris and particulates, and acceptable bioburden before production use | High | Engineering / CQV / QA | Open |  | Attachment Sheet1 row 6; include wiping or swabbing and catch-point inspection as appropriate
BLA-098 | Days 1–3 | Cleaning Validation | Execute spray coverage testing for all product-contact and growth-promoting equipment and incorporate qualified pressure, time, alarm limits, flow durations, and manual cleaning or swabbing of hard-to-clean areas into operating instructions | High | Cleaning Validation / Operations / QA | Open |  | Attachment Sheet1 row 7; short-term requirement
BLA-099 | Days 1–3 | Gowning | Determine and implement a means for visitors to wear a dedicated base layer in classified areas | Medium | EHS / QA / Facilities | Open |  | Attachment Sheet1 row 8; recommendation
BLA-100 | Days 1–3 | Access Control | Provide Lilly with the operations access-control strategy and governance, including required training, approval criteria, and periodic roster review to remove or flag inappropriate access | Medium | Operations / QA / Site Security | Open |  | Attachment Sheet1 row 9; short-term requirement
BLA-101 | Days 1–3 | Temporary Storage | Conduct hold-time studies for all portable vessels used for temporary water or growth-promoting solution storage, confirm complete drainability, and incorporate hold-time and draining requirements into operating documents | High | Process / Validation / Operations | Open |  | Attachment Sheet1 row 10; short-term requirement
BLA-102 | Days 1–3 | Mobile Phase Systems | Define controls that ensure only acceptable mobile phase is supplied to the process and specify the system response to out-of-range temperature, composition, or pH | Low | Process / Automation / QA | Open |  | Attachment Sheet1 row 11; technical follow-up
BLA-103 | Days 1–3 | Filter Integrity Testing | Provide the final pre-use and post-use filter integrity testing strategy | Low | Process / Validation / QA | Open |  | Attachment Sheet1 row 12; technical follow-up
BLA-104 | Days 1–3 | AFD | Confirm AFD stroke height prevents blades from being submerged during displacement washes | Low | Process Engineering / CQV | Open |  | Attachment Sheet1 row 13; technical follow-up
BLA-105 | Days 1–3 | API Mill | Define the mill operating strategy for final drug-substance sampling, inerting, target drum weight without overfill, screen-temperature monitoring, and operator ergonomics | Medium | Process / Operations / EHS | Open |  | Attachment Sheet1 row 14; technical follow-up
BLA-106 | Days 1–3 | Hose Management | Store hose ends at least 6 inches off the floor and provide a clear visual indicator confirming compliant storage position | High | Operations / QA | Open |  | Attachment Sheet1 row 15; complements existing permeable-cover action
BLA-107 | Days 1–3 | Solids Charging | Require contained devices for all solids-charging operations to prevent residual powder exposure to rooms and personnel. Require split valve charging strategy for all steps (including SPPS and cleavage). | High | Engineering / Operations / EHS | Open |  | Attachment Sheet1 row 16; site-wide short-term requirement
BLA-108 | Days 1–3 | Diaphragm Valves | Walk down all lines containing diaphragm valves, verify correct installation angle for drainability, and correct noncompliant installations | High | Engineering / CQV | Open |  | Attachment Sheet1 row 17; short-term requirement
BLA-109 | Days 1–3 | Tank Inspection | Install tank lights where needed to enable effective internal visual inspection | Medium | Facilities / Engineering / QA | Open |  | Attachment Sheet1 row 18; recommendation
BLA-110 | Days 1–3 | Process Sampling | Ensure representative sampling capability exists for every required process sample while minimizing product loss | Medium | Process Engineering / Operations / QA | Open |  | Attachment Sheet1 row 19; technical follow-up
BLA-111 | Days 1–3 | pH Probes | Update calibration instructions to keep tanks capped while non-retractable pH probes are calibrated, and evaluate replacement with retractable probe housings | Medium | Operations / Engineering / QA | Open |  | Attachment Sheet1 row 20; short-term requirement and recommendation

## Sheet2
BLA Visit Action Tracker Summary
Metric | Count | Priority | Count
Total Actions | 66 | High | 36
High Priority | 36 | Medium | 18
Open | 66 | Low | 12
In Progress | 0
Blocked | 0
Completed | 0

## 按Area分类（中英对照）
ID | Visit Day 检查日 | Area 区域 | 区域（中文） | Action Item 行动项（英文原文） | 行动项（中文翻译） | Priority 优先级 | Suggested Owner 建议负责人 | Status 状态 | Due Date 截止日期 | Notes 备注 | 备注（中文）
BLA-025 | Day 2 | ACN Supply | 乙腈（ACN）供应 | Add check valve near the three-way connector in the drain loop | 在排放回路的三通接头附近增设止回阀 | Medium | Engineering | Open
BLA-009 | Day 1 | AFD | 搅拌过滤干燥机（AFD） | Install or verify nameplate on rupture disk | 在爆破片上安装铭牌，或核实其铭牌信息 | Low | Engineering | Open
BLA-104 | Days 1–3 | AFD | 搅拌过滤干燥机（AFD） | Confirm AFD stroke height prevents blades from being submerged during displacement washes | 确认搅拌过滤干燥机（AFD）的行程高度在置换洗涤期间能够防止桨叶浸没 | Low | Process Engineering / CQV | Open |  | Attachment Sheet1 row 13; technical follow-up 附件Sheet1第13行；技术跟进项
BLA-105 | Days 1–3 | API Mill | API粉碎机 | Define the mill operating strategy for final drug-substance sampling, inerting, target drum weight without overfill, screen-temperature monitoring, and operator ergonomics | 定义粉碎机操作策略，涵盖最终原料药取样、惰性化保护、目标桶重且不过量填充、筛网温度监测及操作人员工效学 | Medium | Process / Operations / EHS | Open |  | Attachment Sheet1 row 14; technical follow-up 附件Sheet1第14行；技术跟进项
BLA-100 | Days 1–3 | Access Control | 访问控制 | Provide Lilly with the operations access-control strategy and governance, including required training, approval criteria, and periodic roster review to remove or flag inappropriate access | 向礼来提供运营访问控制策略和管理机制，包括所需培训、审批标准，以及定期审查人员名单以移除或标记不当访问权限 | Medium | Operations / QA / Site Security | Open |  | Attachment Sheet1 row 9; short-term requirement 附件Sheet1第9行；短期要求
BLA-070 | Days 1–3 | CCS / Cross-Contamination | CCS（污染控制策略）/交叉污染 | Provide and complete review of the site multiproduct cross-contamination risk assessment and incorporate high leve summary of risk and midigations into the process specific CCS docments. | 提供并完成工厂多产品交叉污染风险评估的审查，并将风险及缓解措施的高层级摘要纳入工艺特定CCS（污染控制策略）文件。 | Medium | QA / Technical Operations | Open |  | Executive-summary Priority 2 follow-up 执行摘要中的优先级2跟踪项
BLA-085 | Days 1–3 | CCS / Cross-Contamination | CCS（污染控制策略）/交叉污染 | Evaluate process-specific cross-contamination risks from process connections and utility lines, then develop a long-term remediation plan to isolate nonessential connections or otherwise mitigate identified risks. Assess shared-utility and equipment-isolation requirements for GG917 and LAARA operations | 评估工艺连接与公用工程管线带来的工艺特定交叉污染风险，然后制定长期整改计划，隔离非必要连接或以其他方式缓解已识别风险。评估GG917和LAARA操作的共用公用工程及设备隔离要求 | High | QA / Engineering / Technical Operations | Open |  | Assess connection-specific risks as part of CCS and establish sustainable remediation controls 作为CCS的一部分评估各连接的具体风险，并建立可持续的整改控制措施
BLA-096 | Days 1–3 | Changeover Strategy | 换产策略 | Provide Lilly with the changeover strategy and governance for reused equipment, including cleaning limits, normally uncleaned lines, soft and hard-to-clean components, and replacement of filters, membranes, and resins | 向礼来提供重复使用设备的换产策略和管理机制，包括清洁限度、常规不清洗管线、软性及难以清洁部件，以及过滤器、膜和树脂的更换 | High | QA / Operations / Cleaning Validation | Open |  | Attachment Sheet1 row 6; short-term requirement 附件Sheet1第6行；短期要求
BLA-004 | Day 1 | Cleaning Validation | 清洁验证 | Cleaning validation and verification strategy needs presented. Including: strategy for determining appropriate cleaning solution and conditions (time, temp etc), how these are tranlasted to the operational record to ensure proper execution in a repeatable manner. Additionaly need to share how small parts and manual cleaned components are managed and integrated into cleaning records. Additionally, how are rinse and swab limits, sampling instructions, and results recorded. | 需要提交清洁验证与清洁确认策略，包括：确定合适清洁溶液及清洁条件（时间、温度等）的策略；如何将这些要求落实到操作记录中，确保以可重复的方式正确执行；此外，还需说明小部件及手工清洁部件如何管理并纳入清洁记录；以及冲洗与擦拭限度、取样说明和结果如何记录。 | High | Operations / QA | Open |  | General review item from visit notes 来自检查纪要的一般性审查项
BLA-098 | Days 1–3 | Cleaning Validation | 清洁验证 | Execute spray coverage testing for all product-contact and growth-promoting equipment and incorporate qualified pressure, time, alarm limits, flow durations, and manual cleaning or swabbing of hard-to-clean areas into operating instructions | 对所有产品接触和促生长设备执行喷淋覆盖测试，并将经确认的压力、时间、报警限值、冲洗时长及难清洁区域的手工清洁或擦拭要求纳入操作规程 | High | Cleaning Validation / Operations / QA | Open |  | Attachment Sheet1 row 7; short-term requirement 附件Sheet1第7行；短期要求
BLA-108 | Days 1–3 | Diaphragm Valves | 隔膜阀 | Walk down all lines containing diaphragm valves, verify correct installation angle for drainability, and correct noncompliant installations | 逐一巡查所有含隔膜阀的管线，核实安装角度是否正确以保证可排净性，并纠正不符合要求的安装 | High | Engineering / CQV | Open |  | Attachment Sheet1 row 17; short-term requirement 附件Sheet1第17行；短期要求
BLA-012 | Day 1 | Equipment / Piping Standards | 设备/管道标准 | During field walkthroughs several lines visual appeard slopped in undesired location. Confirm all lines are sloped to appropriate low points with proper drain point. | 现场巡查发现多条管线在非预期位置存在视觉可见的坡度（倾斜）。需确认所有管线均向合适的低点倾斜，并配置正确的排净点。 | High | Engineering / CQV | Open |  | Highlighted in source notes 源纪要中已重点标注
BLA-013 | Day 1 | Equipment / Piping Standards | 设备/管道标准 | Provide adequate lighting for adequate visual inspection of all process tanks | 为所有工艺罐提供充足的照明，以便进行充分的外观检查 | Low | Facilities | Open
BLA-091 | Days 1–3 | Equipment / Piping Standards | 设备/管道标准 | Several non-compliant items still exist against equipment/piping standards. For example, ball valves on Category 4 equipment/piping, long tank nozzles on vessel heads and/or branches off tank nozles that will not be cleanable during CIP, diptubes supported by hooks that form crevices, missing drains at low points (especially around filters), non-hygienic/cleanable instrument designs (level, temperature), flow meters installed in non-drainable, flanged connections on category 3 and 4 equipment/piping, bolted agitator blades, deadlegs in various locations due to use of non-zero-static valving/non-minimum distance tees, etc. Conduct a comprehensive gap assessment against equipment and piping standards and prioritize remediation of high-risk Category 3 and 4 systems before production start | 设备/管道标准方面仍存在多项不符合项，例如：4类设备/管道上使用球阀；罐体封头上有较长罐口接管及/或从罐口引出的分支，无法在CIP期间得到有效清洁；浸入管用挂钩支撑形成缝隙；低点缺少排放口（尤其是过滤器周围）；仪器设计不符合卫生/可清洁要求（液位、温度）；流量计安装位置不可排净；3类和4类设备/管道使用法兰连接；搅拌桨叶用螺栓固定；由于采用非零静压阀/非最小距离三通等原因造成多处死角等。需对照设备与管道标准开展全面差距评估，并在投产前优先完成高风险3类和4类系统的整改。 | High | Engineering / QA / CQV | Open |  | Attachment Sheet1 row 4; prioritize AFD, humidifier, and growth-promoting solution systems 附件Sheet1第4行；优先处理AFD、加湿器和促生长溶液系统
BLA-092 | Days 1–3 | Equipment / Piping Standards | 设备/管道标准 | For equipment and piping gaps not remediated before production, establish direct traceability in cleaning documentation, including manual cleaning, targeted inspection, and cleaning or draining instructions for dead legs | 对于投产前未完成整改的设备与管道差距项，在清洁文件中建立直接追溯，包括手工清洁、针对性检查，以及死角的清洁或排水说明 | High | Operations / Cleaning Validation / QA | Open |  | Attachment Sheet1 row 4; interim control pending alignment with Lilly and ASME BPE expectations 附件Sheet1第4行；在与礼来和ASME BPE要求对齐前采取的临时控制措施
BLA-083 | Days 1–3 | Facility / Humidity Control | 厂房/湿度控制 | Complete planned upgrades and demonstrate CNC relative humidity remains below 60% during summer conditions | 完成计划内改造，并证明夏季条件下CNC区域相对湿度保持在60%以下 | Low | Facilities / Engineering / CQV | Open |  | Executive-summary Priority 3 follow-up 执行摘要中的优先级3跟踪项
BLA-035 | Day 3 | Facility / MOM | 厂房/生产运行管理（MOM） | Assess short term actions to reduce risk associate with the lack of a CNC material-flow buffer zone and differential-pressure interlock in Workshop 12 | 评估短期措施，以降低12号车间缺乏CNC（受控未分级）物料流转缓冲区及压差联锁所带来的风险 | High | Facilities / QA | Open
BLA-103 | Days 1–3 | Filter Integrity Testing | 过滤器完整性测试 | Provide the final pre-use and post-use filter integrity testing strategy | 提供最终的使用前和使用后过滤器完整性测试策略 | Low | Process / Validation / QA | Open |  | Attachment Sheet1 row 12; technical follow-up 附件Sheet1第12行；技术跟进项
BLA-077 | Days 1–3 | Filtration Strategy | 过滤策略 | Create and approve a site-wide, risk-based filtration philosophy | 制定并批准全厂范围的基于风险的过滤理念 | Medium | Process / QA | Open |  | Executive-summary Priority 3 follow-up 执行摘要中的优先级3跟踪项
BLA-078 | Days 1–3 | Filtration Strategy | 过滤策略 | Add filtration location, type, and justification diagrams or tables to CCS documentation for each process step | 在每个工艺步骤的CCS文件中补充过滤位置、过滤类型及论证依据的图表 | Medium | Process / QA | Open |  | Executive-summary Priority 3 follow-up 执行摘要中的优先级3跟踪项
BLA-079 | Days 1–3 | Filtration Strategy | 过滤策略 | Define risk-based filter replacement criteria | 定义基于风险的过滤器更换标准 | Low | Process / QA | Open |  | Executive-summary Priority 3 follow-up 执行摘要中的优先级3跟踪项、
BLA-080 | Days 1–3 | Filtration Strategy | 过滤策略 | Reassess and document justification for 75-micron filtration of SPPS raw material drum charging. Filtration of liquid raw materials is required for all process steps. | 重新评估SPPS（固相多肽合成）原料桶加料的75微米过滤依据并形成文件。所有工艺步骤的液体原料均需过滤。 | High | Process / QA | Open |  | Executive-summary Priority 3 follow-up 执行摘要中的优先级3跟踪项
BLA-081 | Days 1–3 | Glovebox Cleaning | 手套箱清洁 | Revise glovebox cleaning practices to use approved alcohol wipes rather than water wipes in dispensing areas | 修订手套箱清洁规程，称量分装区域使用经批准的醇类擦拭布，而非水湿擦拭布 | High | Operations / QA | Open |  | Executive-summary Priority 3 follow-up 执行摘要中的优先级3跟踪项
BLA-099 | Days 1–3 | Gowning | 更衣 | Determine and implement a means for visitors to wear a dedicated base layer in classified areas | 确定并落实来访人员在洁净区域内穿着专用内层衣物（基础层）的方式 | Medium | EHS / QA / Facilities | Open |  | Attachment Sheet1 row 8; recommendation 附件Sheet1第8行；建议
BLA-056 | Days 1–3 | HCN Removal | HCN（氰化氢）去除 | Evaluate increased nitrogen sparge rates for SC coupling | 评估提高SC偶联工序氮气鼓泡（sparge）速率 | High | Process Development / Engineering | Open |  | Current equipment reportedly supports up to ~40 m³/h; current operating limit ~20 m³/h 据报告现有设备支持最高约40 m³/h；当前运行限值约20 m³/h
BLA-057 | Days 1–3 | HCN Removal | HCN（氰化氢）去除 | Assess feasibility and effectiveness of nitrogen sweep operation during SC coupling | 评估SC偶联期间氮气吹扫操作的可行性和有效性 | High | Process Development / Engineering | Open |  | Executive-summary Priority 1 follow-up 执行摘要中的优先级1跟踪项
BLA-058 | Days 1–3 | HCN Removal | HCN（氰化氢）去除 | Demonstrate manufacturing-scale HCN removal equivalent to development and pivotal-batch conditions | 证明生产规模下HCN（氰化氢）去除效果与开发及关键批次条件相当 | High | Process Development / MSAT | Open |  | Scale-up justification required 需要提供放大依据
BLA-059 | Days 1–3 | HCN Removal | HCN（氰化氢）去除 | Evaluate direct dissolved-HCN measurement for process characterization | 评估直接测定溶解态HCN用于工艺表征 | High | Process Development / Analytical | Open |  | Focus on solution concentration rather than sparge-rate comparison alone | 重点关注溶液浓度，而非仅比较鼓泡速率
BLA-060 | Days 1–3 | HCN Removal | HCN（氰化氢）去除 | Confirm equipment limitations and establish the qualified operating envelope for higher nitrogen sparging rates | 确认设备限制，并建立更高氮气鼓泡速率的合格操作范围 | High | Engineering / Process Safety | Open |  | Include filter-plate protection constraints | 包括滤板保护约束
BLA-042 | Day 3 | Hose Management | 软管管理 | Validate or justify the one-month service life for dedicated PW hoses | 对专用纯化水（PW）软管一个月使用寿命进行验证，或提供合理的书面依据 | Medium | Engineering / QA | Open |  | Notes state assessment exists but no validation | 纪要表明已有评估但未经验证
BLA-043 | Day 3 | Hose Management | 软管管理 | Review cleaning frequency and lifecycle management for dedicated fresh-solvent corrugated hoses | 审查专用新鲜溶剂波纹软管的清洁频率和全生命周期管理 | Medium | Engineering / QA | Open
BLA-044 | Day 3 | Hose Management | 软管管理 | Review pre-use cleaning and batch-disposal strategy for process-solution transfer hoses | 审查工艺溶液转移软管的使用前清洁与批次使用后处理策略 | Medium | Engineering / QA | Open
BLA-045 | Day 3 | Hose Management | 软管管理 | Upgrade hose connections to smooth-bore internal design, considering Pharmaline N | 将软管接头升级为内孔光滑（smooth-bore）设计，考虑采用Pharmaline N软管 | High | Engineering | Open |  | Highlighted in source notes | 源纪要中已重点标注
BLA-074 | Days 1–3 | Hose Management | 软管管理 | Replace silicone water hoses with PTFE hoses or provide a documented technical justification | 将硅胶水管更换为PTFE（聚四氟乙烯）软管，或提供书面技术论证 | Low | Engineering / QA | Open |  | Executive-summary Priority 3 follow-up | 执行摘要中的优先级3跟踪项
BLA-076 | Days 1–3 | Hose Management | 软管管理 | Require immediate hose disconnection and controlled storage after use | 要求软管使用后立即断开，并按受控方式存放 | Medium | Operations / QA | Open |  | Executive-summary Priority 3 follow-up | 执行摘要中的优先级3跟踪项
BLA-086 | Days 1–3 | Hose Management | 软管管理 | Implement the use of permeable film to cover the ends of process and water hoses while stored for drying | 实施在工艺软管和水管干燥存放期间使用透气薄膜包覆管口的做法 | High | Operations / QA | Open |  | Apply during drying and storage to protect hose ends while allowing ventilation | 在干燥和存放期间使用，保护管口同时允许通风
BLA-087 | Days 1–3 | Hose Management | 软管管理 | Use a process-compatible solvent rather than water for the initial rinsing of new hoses | 新软管首次冲洗使用与工艺相容的溶剂，而非水 | Medium | Operations / QA / Process | Open |  | Initial rinse recommendation for newly introduced hoses | 针对新投用软管的首次冲洗建议
BLA-106 | Days 1–3 | Hose Management | 软管管理 | Store hose ends at least 6 inches off the floor and provide a clear visual indicator confirming compliant storage position | 软管端部存放离地至少6英寸（约15厘米），并提供清晰的目视标识以确认符合要求的存放位置 | High | Operations / QA | Open |  | Attachment Sheet1 row 15; complements existing permeable-cover action | 附件Sheet1第15行；与现有透气包覆措施互补
BLA-051 | Days 1–3 | M+53 / DIPEA | M+53杂质 / DIPEA（二异丙基乙胺） | Demonstrate reliable sourcing of DIPEA containing less than 50 ppm acetaldehyde | 证明能够稳定采购乙醛含量低于50 ppm的DIPEA（二异丙基乙胺） | High | Supply Chain / QC / Process | Open |  | Executive-summary Priority 1 follow-up | 执行摘要中的优先级1跟踪项
BLA-052 | Days 1–3 | M+53 / DIPEA | M+53杂质 / DIPEA（二异丙基乙胺） | Complete evaluation of internal DIPEA processing options to further reduce acetaldehyde content | 完成内部DIPEA处理方案的评估，以进一步降低乙醛含量 | High | Process Development / QC | Open |  | Executive-summary Priority 1 follow-up | 执行摘要中的优先级1跟踪项
BLA-055 | Days 1–3 | M+53 / DIPEA | M+53杂质 / DIPEA（二异丙基乙胺） | Reduce DIPEA charging and exposure duration where technically feasible and document the control strategy | 在技术可行的情况下缩短DIPEA加料及暴露时间，并将控制策略形成文件 | High | Process Engineering / Operations | Open |  | Executive-summary Priority 1 follow-up | 执行摘要中的优先级1跟踪项
BLA-053 | Days 1–3 | M+53 Investigation | M+53杂质调查 | Complete remaining M+53 fault-tree investigations and document supported conclusions | 完成剩余M+53杂质故障树调查，并将有证据支持的结论形成文件 | High | Process Development / QA | Open |  | Executive-summary Priority 1 follow-up | 执行摘要中的优先级1跟踪项
BLA-054 | Days 1–3 | M+53 Investigation | M+53杂质调查 | Assess the impact of extended DIPEA exposure and process hold times on impurity formation | 评估DIPEA长时间暴露及工艺中间体暂存时间对杂质生成的影响 | High | Process Development | Open |  | Include deprotection and coupling operations | 包括脱保护和偶联工序
BLA-016 | Day 2 | Mobile Phase Formulation | 流动相配制 | Review HCl charging dip-tube arrangement and confirm material of construction | 审查HCl（盐酸）加料浸入管的布置，并确认其材质 | Low | Process Engineering | Open |  | Source note suggests HC; confirm exact alloy/specification | 源纪要提示采用HC（哈氏合金C）；请确认具体合金牌号/规格
BLA-021 | Day 2 | Mobile Phase Formulation | 流动相配制 | Update MOR or SOP to require mobile-scale reading after the peristaltic pump empties the flexible connection | 更新MOR（批操作记录）或SOP，要求蠕动泵排空柔性连接管后进行移动秤读数 | Low | Operations / QA | Open
BLA-022 | Day 2 | Mobile Phase Formulation | 流动相配制 | Document and verify the cleaning sequence: rinse, disassemble, clean, visually inspect, reassemble, final rinse, and pre-use rinse | 记录并验证清洁顺序：冲洗、拆卸、清洁、目视检查、重新组装、最终冲洗及使用前冲洗 | Low | Operations / QA | Open
BLA-102 | Days 1–3 | Mobile Phase Systems | 流动相系统 | Define controls that ensure only acceptable mobile phase is supplied to the process and specify the system response to out-of-range temperature, composition, or pH | 定义控制措施，确保只有合格的流动相供给工艺，并明确系统对温度、组成或pH超范围时的响应 | Low | Process / Automation / QA | Open |  | Attachment Sheet1 row 11; technical follow-up | 附件Sheet1第11行；技术跟进项
BLA-097 | Days 1–3 | New Equipment Readiness | 新设备投产就绪 | Define and document release controls for new equipment that demonstrate removal of fabrication and construction residues, debris and particulates, and acceptable bioburden before production use | 定义并记录新设备的放行控制，证明生产使用前已清除制造和施工残留物、碎屑和颗粒物，且生物负载可接受 | High | Engineering / CQV / QA | Open |  | Attachment Sheet1 row 6; include wiping or swabbing and catch-point inspection as appropriate | 附件Sheet1第6行；酌情包括擦拭或涂抹取样及收集点检查
BLA-088 | Days 1–3 | PD Pumps | 容积泵（PD泵） | Install low-point drains on the inlet and outlet of all PD pumps used in Category 4 systems, and add pre- and post-cleaning steps to drain from these points and nitrogen-purge through the pump to the outlet drain | 在4类（Category 4）系统所有容积泵（PD泵）的进出口安装低点排放口，并在清洁前后增加从这些排放口排水、以氮气吹扫通过泵体至出口排放的操作步骤 | High | Engineering / Operations / QA | Open |  | Attachment Sheet1 row 3; short-term requirement | 附件Sheet1第3行；短期要求
BLA-089 | Days 1–3 | PD Pumps | 容积泵（PD泵） | Update the cleaning program for PD pumps so recovery factors account for large-area soft parts and include a representative pump swab location for product-contact applications | 更新容积泵清洁方案，使回收率系数涵盖大面积软性部件，并针对产品接触应用纳入代表性泵擦拭取样点 | High | Cleaning Validation / QA | Open |  | Attachment Sheet1 row 3; short-term requirement | 附件Sheet1第3行；短期要求
BLA-090 | Days 1–3 | PD Pumps | 容积泵（PD泵） | Evaluate long-term replacement of PD pumps with pressure transfer or hygienic centrifugal pumps with low-point casing drains; where PD pumps remain necessary, assess more drainable designs | 评估以压力转移泵或带低点泵壳排放口的卫生型离心泵长期替代容积泵；如需保留容积泵，评估更具可排净性的设计 | Medium | Engineering / Process | Open |  | Attachment Sheet1 row 3; long-term requirement | 附件Sheet1第3行；长期要求
BLA-061 | Days 1–3 | Passivation | 钝化 | Complete planned passivation of GG917 and LAARA process lines | 完成GG917和LAARA工艺管线的计划内钝化 | High | Engineering / QA | Open |  | Executive-summary Priority 1 follow-up | 执行摘要中的优先级1跟踪项
BLA-062 | Days 1–3 | Passivation | 钝化 | Provide a remediation plan and timeline for solvent headers not included in the current passivation scope | 针对未纳入当前钝化范围的溶剂总管，提供整改方案和时间表 | High | Engineering / QA | Open |  | Executive-summary Priority 1 follow-up | 执行摘要中的优先级1跟踪项
BLA-063 | Days 1–3 | Passivation | 钝化 | Define remediation for bulk solvent tanks and solvent distribution systems that have not been passivated | 明确未钝化的大宗溶剂储罐及溶剂分配系统的整改方案 | High | Engineering / QA | Open |  | Bulk tanks reportedly in service for approximately two years | 据报告大宗储罐已投入使用约两年
BLA-011 | Day 1 | Precipitation | 沉淀工序 | Confirm inlet line sizing meets the 200 L/h process requirement | 确认进料管线尺寸满足200 L/h工艺要求 | Low | Process Engineering | Open
BLA-110 | Days 1–3 | Process Sampling | 工艺取样 | Ensure representative sampling capability exists for every required process sample while minimizing product loss | 确保每个必需工艺取样点具备代表性取样能力，同时最大限度减少产品损失 | Medium | Process Engineering / Operations / QA | Open |  | Attachment Sheet1 row 19; technical follow-up | 附件Sheet1第19行；技术跟进项
BLA-093 | Days 1–3 | Purified Water System | 纯化水系统 | Purified Water header throughout the facility does not meet industry guidance - sample point is not representative of POU, no means of pre-use flushing/blowing, etc. Additionally, POU filtration should be provided for any PW supplied to a growth promoting solution via hose connection (upstream of drain line). These filters should have time in use tracked and be replaced frequently (NMT 24 hours). Implement point-of-use flushing directly to waste and post-use draining and drying for purified-water lines using zero-static valves or minimum-distance tees without creating dead legs | 全厂纯化水总管不符合行业指南要求：取样点不能代表使用点（POU），无使用前冲洗/吹扫手段等。此外，通过软管连接供应给促生长溶液的纯化水应提供使用点过滤（位于排放管线上游）。这些过滤器应跟踪使用时间并频繁更换（不超过24小时）。实施使用点直接排放冲洗，并使用零静压阀或最小距离三通对纯化水管线进行使用后排净和干燥，避免形成死角 | High | Engineering / Utilities / QA | Open |  | Attachment Sheet1 row 5; short-term requirement | 附件Sheet1第5行；短期要求
BLA-094 | Days 1–3 | Purified Water System | 纯化水系统 | Install point-of-use filters for purified water supplied by hose to growth-promoting solutions, track time in use, and replace filters no later than 24 hours | 为通过软管向促生长溶液供应的纯化水安装使用点过滤器，跟踪使用时间，过滤器更换周期不超过24小时 | High | Engineering / Operations / QA | Open |  | Attachment Sheet1 row 5; short-term requirement | 附件Sheet1第5行；短期要求
BLA-095 | Days 1–3 | Purified Water System | 纯化水系统 | Assess representative sampling from new point-of-use drains and determine whether formal revalidation or an informal verification study is required to confirm water-system quality | 评估从新增使用点排放口取样的代表性，确定是否需要正式再验证或非正式确认研究，以确认水系统质量 | High | QC / Validation / Utilities | Open |  | Attachment Sheet1 row 5; short-term requirement | 附件Sheet1第5行；短期要求
BLA-065 | Days 1–3 | Raw Material Handling | 原料处理 | Develop interim administrative controls for raw material receipt and transfer into CNC areas to minimize potential exposure to outdoor conditions. | 制定原料接收及转入CNC（受控未分级）区域的临时管理控制措施，以最大程度减少暴露于室外环境的风险。 | High | Operations / QA / EHS | Open |  | Address uncontrolled ingress pending a long-term solution | 在长期解决方案落地前，处理不受控的进入（物料流入）问题
BLA-066 | Days 1–3 | Raw Material Handling | 原料处理 | Evaluate long-term facility modifications to provide an airlock or physical segregation for CNC material transfer | 评估长期厂房改造方案，为CNC物料转移提供气锁间或物理隔离 | Medium | Facilities / Engineering / QA | Open |  | Executive-summary Priority 2 follow-up | 执行摘要中的优先级2跟踪项
BLA-107 | Days 1–3 | Solids Charging | 固体加料 | Require contained devices for all solids-charging operations to prevent residual powder exposure to rooms and personnel. Require split valve charging strategy for all steps (including SPPS and cleavage). | 要求所有固体加料操作使用密闭（遏制）装置，防止残余粉体暴露于房间和人员。要求所有工序（包括SPPS和裂解）采用分体阀（split valve）加料策略。 | High | Engineering / Operations / EHS | Open |  | Attachment Sheet1 row 16; site-wide short-term requirement | 附件Sheet1第16行；全厂范围短期要求
BLA-109 | Days 1–3 | Tank Inspection | 储罐检查 | Install tank lights where needed to enable effective internal visual inspection | 在需要的位置安装罐内照明，以便进行有效的内部目视检查 | Medium | Facilities / Engineering / QA | Open |  | Attachment Sheet1 row 18; recommendation | 附件Sheet1第18行；建议
BLA-101 | Days 1–3 | Temporary Storage | 临时储存 | Conduct hold-time studies for all portable vessels used for temporary water or growth-promoting solution storage, confirm complete drainability, and incorporate hold-time and draining requirements into operating documents | 对所有用于临时储存水或促生长溶液的移动容器开展存放时限（hold-time）研究，确认完全可排净，并将存放时限和排净要求纳入操作文件 | High | Process / Validation / Operations | Open |  | Attachment Sheet1 row 10; short-term requirement | 附件Sheet1第10行；短期要求
BLA-084 | Days 1–3 | Vent Header | 排气总管 | Asymchem to provide vent header drawings and designs to Lilly for review | 凯莱英（Asymchem）向礼来提供排气总管图纸和设计方案供审查 | Medium | Engineering / Lilly Team | Open |  | Added per follow-up request | 根据后续跟进要求新增
BLA-111 | Days 1–3 | pH Probes | pH电极 | Update calibration instructions to keep tanks capped while non-retractable pH probes are calibrated, and evaluate replacement with retractable probe housings | 更新校准说明，要求在非伸缩式pH电极校准时保持罐盖关闭，并评估更换为可伸缩式电极护套 | Medium | Operations / Engineering / QA | Open |  | Attachment Sheet1 row 20; short-term requirement and recommendation | 附件Sheet1第20行；短期要求和建议